## Tasks
TaskId | Phase | Workstream | Category | SuggestedRole | Title | EstimateHours | DependsOn | Status | Assignee | Description
T001 | 0 | W0 - Decisions & Architecture | Decision | Architect / PM | Architecture Decision Workshop - Track B (OI-35 B1-B8) | 6 |  | NotStarted |  | Blue Ridge-owned. Resolve partitioning (B2), columnstore (B3), LotGenealogy closure table (B4), materialized TotalInProcess/InventoryAvailable (B5), IdentifierSequence locking (B6), OperationLog split (B7), filtered indexes (B8). Items 2/4/5/7 MUST be in the Phase-1 CREATE migration. Assumed defaults accepted per this validation
T002 | 0 | W0 - Decisions & Architecture | Decision | Architect / PM | Customer Validation Gate - Track A (A1-A9) | 6 |  | NotStarted |  | MPP-owned workshop. A1 OI-31 identifier cutover; A2 WorkOrder BIT-flags; A3 historical migration; A4 ShotCount semantics; A5 DefaultScreen+ConfirmationMethod seeding; A6 AIM Hold/Update contract; A7 label template scope; A8 OI-32 material allocation; A9 OI-33 AIM empty-pool hard-fail
T003 | 0 | W0 - Decisions & Architecture | Decision | Architect / PM | Finalize per-table retention classes (B1) with MPP IT | 3 | T001 | NotStarted |  | Negotiate 20yr vs 7yr per table. Honda traceability (Lots.* events, ContainerSerial, ShippingLabel, LotGenealogy) stays 20yr; push back on OperationLog/FailureLog/InterfaceLog/DowntimeEvent/ConfigLog. Drives FDS-11 retention amendment
T004 | 0 | W0 - Decisions & Architecture | Decision | Architect / PM | Confirm WorkOrder BIT-flag enumeration (A2 / FDS-06-030) | 2 | T002 | NotStarted |  | Which Flexware flags are live (IsCameraProcessingEnabled, IsScaleProcessingEnabled, GroupTargetWeight+tol+UOM, RecipeNumber, TrayQuantity, ReturnableDunnageCode, Customer). Dead flags do not ship in Phase-1 WorkOrder CREATE
T005 | 0 | W0 - Decisions & Architecture | Decision | Architect / PM | Confirm Workstation DefaultScreen + ConfirmationMethod seeding (A5) | 2 | T002 | NotStarted |  | Per-Cell terminal-function Perspective views + per-Cell ConfirmationMethod (Vision/Barcode/Both). Phase-1 seed data for B11 routing + FDS-10-013
T006 | 0 | W0 - Decisions & Architecture | Decision | Architect / PM | Confirm label template scope (A7/S-09) + AIM Hold/Update contract (A6) | 2 | T002 | NotStarted |  | Flexware 3 templates (CONTAINER/LOT/CONTAINER_HOLD) + any new (Sort Cage/Hold/Void). AIM PlaceOnHold/ReleaseFromHold/UpdateAim signatures + error recovery
T007 | 0 | W0 - Decisions & Architecture | Decision | Architect / PM | Lock identifier-sequence cutover + format/reset/rollover policy (A1/OI-31/S-10) | 2 | T002 | NotStarted |  | Final cutover seed values + keep MESL/MESI vs mint new + reset + 9,999,999 rollover policy + Ben rollout-shape (single-line vs full-cutover vs shadow). Wrong seed = LTT collisions at cutover
T008 | 0 | W0 - Decisions & Architecture | Decision | Architect / PM | Resolve UJ-03 sublot even-split default + UJ-05 serial migration direction | 2 | T002 | NotStarted |  | UJ-03: auto-prompt 50/50 even split default (confirm all parts split or only some). UJ-05: update-in-place + ContainerSerialHistory default; awaits MPP Quality + Honda affirmation
T009 | 0 | W0 - Decisions & Architecture | Documentation | Architect / PM | Phase 0 sign-off - decision log + Data Model + FDS amendments | 4 | T001,T002,T003,T004,T005,T006,T007,T008 | NotStarted |  | Phase-0 GATE. Decision log appended to OIR with signed-off dates; Data Model bump adds sec Scaling Decisions (drives Phase-1 migration content); FDS-11 retention paragraph drafted; B10 serial-migration convention finalized. Unblocks all Phase 1
T010 | 1 | W1 - Foundation & LOT Core | Migration | SQL Engineer | Write migration 0020 CREATE core Workorder event tables | 5 | T009 | NotStarted |  | 0020_arc2_phase1_shop_floor_foundation.sql. CREATE Workorder.WorkOrder, WorkOrderOperation, ProductionEvent, ProductionEventValue, ConsumptionEvent, RejectEvent. BIGINT IDENTITY PKs, FK to Lots/Parts/Oee.Shift. XDEP: Phase 0 complete; OI-35 architecture gate resolved
T011 | 1 | W1 - Foundation & LOT Core | Migration | SQL Engineer | Write migration 0020 CREATE Lots.Lot with Tool/Cavity columns | 4 | T010 | NotStarted |  | CRITICAL B-2: Lots.Lot does NOT exist (Arc 1 only built Lots code tables). CREATE Lots.Lot incl ToolId + ToolCavityId FK columns built in, plus materialized TotalInProcess/InventoryAvailable columns (B5) + CrtActive BIT NOT NULL DEFAULT 0 (FDS-10-012 Controlled Run Tag hook; CRT workflow in Phase 9).
T012 | 1 | W1 - Foundation & LOT Core | Migration | SQL Engineer | Write migration 0020 CREATE Lots history tables (LotStatusHistory + LotMovement) | 3 | T011 | NotStarted |  | CREATE Lots.LotStatusHistory and Lots.LotMovement append-only event tables. Phase-1 Lot_UpdateStatus/Lot_MoveTo procs write to them
T013 | 1 | W1 - Foundation & LOT Core | Migration | SQL Engineer | Write migration 0020 CREATE Lots.IdentifierSequence table | 2 | T010 | NotStarted |  | CREATE Lots.IdentifierSequence (sequence-name keyed, current value, format template). Row-locked _Next proc reads/updates it (B6)
T014 | 1 | W1 - Foundation & LOT Core | Migration | SQL Engineer | Write migration 0020 CREATE Lots.LotGenealogyClosure closure table | 3 | T011 | NotStarted |  | B4 closure table: AncestorLotId/DescendantLotId/Depth. Adjacency-list genealogy materialized as closure for fast subtree queries
T015 | 1 | W1 - Foundation & LOT Core | Migration | SQL Engineer | Write migration 0020 CREATE split Lots.LotEventLog table | 2 | T011 | NotStarted |  | B7: dedicated high-volume Lots.LotEventLog split out of Audit.ConfigLog; Audit_LogOperation routes lot-scoped events here
T016 | 1 | W1 - Foundation & LOT Core | Migration | SQL Engineer | Write migration 0020 partition functions + schemes on high-volume event tables | 5 | T010,T015 | NotStarted |  | OI-35 B2: partition functions+schemes (date/range sliding window) on ProductionEvent, ProductionEventValue, ConsumptionEvent, RejectEvent, LotEventLog. PartitionMaintenance script maintains windows
T017 | 1 | W1 - Foundation & LOT Core | Migration | SQL Engineer | Write migration 0020 filtered indexes on event + lot tables | 3 | T011,T012,T016 | NotStarted |  | OI-35 B8 filtered indexes (active/non-deprecated/in-process predicates). Includes IpAddress attribute index for Terminal_GetByIpAddress lookup
T018 | 1 | W1 - Foundation & LOT Core | Migration | SQL Engineer | Write migration 0020 CREATE Parts.v_EffectiveItemLocation view | 2 | T010 | NotStarted |  | CREATE VIEW resolving effective item-at-location (item master x location attribute overrides). Read by Cell Context Selector + frontend
T019 | 1 | W1 - Foundation & LOT Core | Seed | SQL Engineer | Seed Terminal + Cell LocationAttributeDefinition rows | 2 |  | NotStarted |  | Terminal-tier: DefaultScreen, RequiresCompletionConfirm. Cell-tier: ConfirmationMethod, CoupledDownstreamCellLocationId. Also IpAddress attribute. XDEP: needs LocationTypeDefinition Terminal/Cell tiers from Arc 1
T020 | 1 | W1 - Foundation & LOT Core | Seed | SQL Engineer | Seed IdentifierSequence + fallback Terminal Location rows | 2 | T013,T019 | NotStarted |  | IdentifierSequence seed: Lot MESL{0:D7}, SerializedItem MESI{0:D7} from S-10 cutover values. Plus fallback Terminal Location row for unresolved-IP sessions. ASCII-only; byte-scan before apply
T021 | 1 | W1 - Foundation & LOT Core | StoredProc | SQL Engineer | Write Terminal_GetByIpAddress + Terminal_List procs | 3 | T017,T019 | NotStarted |  | Location.Terminal_GetByIpAddress (IpAddress attr index lookup, returns terminal + DefaultScreen + coupled cell), Location.Terminal_List. Read procs, no OUTPUT params, empty set = not found
T022 | 1 | W1 - Foundation & LOT Core | StoredProc | SQL Engineer | Write AppUser initials/AD auth + roles procs | 4 |  | NotStarted |  | Location.AppUser_GetByInitials, AppUser_AuthenticateAd, AppUser_GetRoles. Initials attribution + per-action AD elevation. XDEP: AppUser table from Arc 1
T023 | 1 | W1 - Foundation & LOT Core | StoredProc | SQL Engineer | Write Oee Shift lifecycle procs | 4 | T010 | NotStarted |  | Oee.Shift_Start, Shift_End, Shift_GetActive, Shift_GetOpen. Start/End are mutation procs (status-row pattern); GetActive/GetOpen read procs
T024 | 1 | W1 - Foundation & LOT Core | StoredProc | SQL Engineer | Write Lots.IdentifierSequence_Next row-locked proc | 2 | T013,T020 | NotStarted |  | B6: row-locked (UPDLOCK/ROWLOCK) sequence increment, formats via template (MESL{0:D7}). Returns next identifier string. Called inside Lot_Create txn
T025 | 1 | W1 - Foundation & LOT Core | StoredProc | SQL Engineer | Write Lots.Lot_Create proc with genealogy + closure | 4 | T011,T014,T015,T024 | NotStarted |  | Complex txn: insert Lot, call IdentifierSequence_Next, populate LotGenealogyClosure (B4) from parent lots, write LotEventLog via Audit_LogOperation, init materialized totals (B5). Mutation pattern
T026 | 1 | W1 - Foundation & LOT Core | StoredProc | SQL Engineer | Write Lots.Lot_Get + Lot_List read procs | 2 | T011,T018 | NotStarted |  | Lots.Lot_Get (single, w/ resolved Tool/Cavity/Location names), Lot_List (filtered). Read procs, no OUTPUT params
T027 | 1 | W1 - Foundation & LOT Core | StoredProc | SQL Engineer | Write Lots.Lot_UpdateStatus + Lot_MoveTo procs | 4 | T012,T025 | NotStarted |  | Lot_UpdateStatus writes LotStatusHistory; Lot_MoveTo writes LotMovement + updates materialized totals (B5). Both call Audit_LogOperation. Mutation pattern
T028 | 1 | W1 - Foundation & LOT Core | StoredProc | SQL Engineer | Write Lots.Lot_AssertNotBlocked guard proc | 2 | T011 | NotStarted |  | B2 guard: raises three-tier error if lot is on AIM/quality hold (BlocksProduction). Called by mutation procs before state transitions
T029 | 1 | W1 - Foundation & LOT Core | StoredProc | SQL Engineer | Write Audit.Audit_LogOperation with LotEventLog routing | 3 | T015,T012 | NotStarted |  | B7: routes lot-scoped operation events to Lots.LotEventLog, others to Audit.ConfigLog. Emits no result set (runs inside mutation txns). Description convention SUBJECT MidDot CATEGORY MidDot ACTION
T030 | 1 | W1 - Foundation & LOT Core | NamedQuery | SQL / Integration | Create Named Queries wrapping all Phase-1 procs | 4 | T021,T022,T023,T024,T025,T026,T027,T028 | NotStarted |  | One NQ folder+resource.json per proc. Mutation procs (Shift_Start/End, Lot_Create/UpdateStatus/MoveTo, IdentifierSequence_Next) need attributes.type=Query (status-row pattern); reads default. Run scan.ps1
T031 | 1 | W1 - Foundation & LOT Core | GatewayScript | Gateway / Integration | Write Terminal_ResolveFromSession gateway script | 4 | T021 | NotStarted |  | Resolves terminal identity from Perspective session (client IP) via Terminal_GetByIpAddress; falls back to fallback Terminal row. Sets session.custom terminal context (B11)
T032 | 1 | W1 - Foundation & LOT Core | GatewayScript | Gateway / Integration | Write PresenceIdleWatcher Perspective-side script | 5 | T031 | NotStarted |  | Tracks last-interaction timestamp; drives 30-min idle re-confirm modal. Perspective session script. Pairs with Idle Re-Confirm Modal view
T033 | 1 | W1 - Foundation & LOT Core | GatewayScript | Gateway / Integration | Write ShiftBoundaryTicker 60s timer script | 5 | T023 | NotStarted |  | Gateway timer (60s); detects shift boundary crossings, calls Shift_End/Shift_Start. XDEP: shift schedule seed (Arc 1)
T034 | 1 | W1 - Foundation & LOT Core | GatewayScript | Gateway / Integration | Write PartitionMaintenance 24h timer script | 6 | T016 | NotStarted |  | B2 sliding-window: 24h gateway timer; splits/merges/switches partitions on event tables to maintain retention window. OI-35 retention strategy
T035 | 1 | W1 - Foundation & LOT Core | Frontend | Perspective Engineer | Build Initials Entry view | 4 | T030 | NotStarted |  | Top-level Perspective view; numeric/initials keypad -> AppUser_GetByInitials. Operator attribution entry
T036 | 1 | W1 - Foundation & LOT Core | Frontend | Perspective Engineer | Build Terminal Selector view | 4 | T030,T031 | NotStarted |  | Top-level view; lists terminals (Terminal_List) for manual override when IP resolve fails/ambiguous
T037 | 1 | W1 - Foundation & LOT Core | Frontend | Perspective Engineer | Build Cell Context Selector shared component | 4 | T030,T018 | NotStarted |  | Reusable embedded component; cascading cell/coupled-downstream selection, reads v_EffectiveItemLocation. Shared across plant-floor screens (B12)
T038 | 1 | W1 - Foundation & LOT Core | Frontend | Perspective Engineer | Build Home Router view | 6 | T031,T035,T036,T037 | NotStarted |  | Top-level entry router; resolves terminal -> DefaultScreen, gates on initials entry, routes to cell context (B11). Central plant-floor landing
T039 | 1 | W1 - Foundation & LOT Core | Frontend | Perspective Engineer | Build 30-Min Idle Re-Confirm Modal | 3 | T032 | NotStarted |  | Embedded modal; fires on PresenceIdleWatcher idle threshold; re-confirm initials to continue session
T040 | 1 | W1 - Foundation & LOT Core | Frontend | Perspective Engineer | Build Per-Mutation Initials Field component | 4 | T030 | NotStarted |  | Reusable embedded component; inline initials capture per protected mutation; validates via AppUser_GetByInitials. Page-scoped message to parent (B12)
T041 | 1 | W1 - Foundation & LOT Core | Frontend | Perspective Engineer | Build Elevation Modal (per-action AD) component | 5 | T030 | NotStarted |  | Reusable embedded modal; AD username/password elevation for protected actions -> AppUser_AuthenticateAd + AppUser_GetRoles. Per-action elevation (FDS-04-007)
T042 | 1 | W1 - Foundation & LOT Core | Testing | QA / SQL | Write Phase-1 suite test: terminal resolve | 2 | T021,T031 | NotStarted |  | Foundation suite (renumbered). Terminal_GetByIpAddress + Terminal_List + fallback. INSERT-EXEC temp-table assert pattern
T043 | 1 | W1 - Foundation & LOT Core | Testing | QA / SQL | Write Phase-1 suite test: appuser/initials + AD auth | 3 | T022 | NotStarted |  | AppUser_GetByInitials, AppUser_AuthenticateAd, AppUser_GetRoles assertions
T044 | 1 | W1 - Foundation & LOT Core | Testing | QA / SQL | Write Phase-1 suite test: shift lifecycle | 3 | T023 | NotStarted |  | Shift_Start/End/GetActive/GetOpen; boundary + double-open guard assertions
T045 | 1 | W1 - Foundation & LOT Core | Testing | QA / SQL | Write Phase-1 suite test: identifier sequence | 2 | T024 | NotStarted |  | IdentifierSequence_Next row-lock increment + format template; concurrency/no-gap assertions
T046 | 1 | W1 - Foundation & LOT Core | Testing | QA / SQL | Write Phase-1 suite test: lot create/move/status | 4 | T025,T026,T027,T028 | NotStarted |  | Lot_Create/Get/List/UpdateStatus/MoveTo/AssertNotBlocked; history-table writes + materialized totals (B5) assertions
T047 | 1 | W1 - Foundation & LOT Core | Testing | QA / SQL | Write Phase-1 suite test: genealogy closure table | 3 | T014,T025 | NotStarted |  | B4 LotGenealogyClosure ancestor/descendant/depth population on multi-parent lot create assertions
T048 | 1 | W1 - Foundation & LOT Core | Testing | QA / SQL | Write Phase-1 suite test: audit operation log + LotEventLog routing | 3 | T029,T025,T027 | NotStarted |  | Audit_LogOperation B7 routing (lot events -> LotEventLog, others -> ConfigLog); Description convention + JSON resolved-name FK assertions. Phase-1 gate. Suite target ~80-105 assertions
T049 | 2 | W1 - Foundation & LOT Core | Migration | SQL Engineer | CREATE Lots.LotGenealogy + LotAttributeChange + LotLabel tables (0020) | 4 | T048 | NotStarted |  | B-2: these do NOT exist; Arc 1 made only Lots code tables, Phase 1 made Lot+StatusHistory+Movement. File 0021_arc2_phase2_lot_lifecycle.sql. LotGenealogy(ParentLotId,ChildLotId,RelationshipTypeId,PieceCount); LotAttributeChange(LotId,AttributeName,OldValue,NewValue,ChangedByUserId,TerminalLocationId,ChangedAt); LotLabel append-only. XDEP: Phase 1
T050 | 2 | W1 - Foundation & LOT Core | Migration | SQL Engineer | CREATE Lots.PauseEvent table (FDS-05-038) with constraints + filtered indexes | 3 | T049 | NotStarted |  | Same migration 0021. Append-only place+close lifecycle. CK_PauseEvent_ResumePaired; filtered UQ (LotId,LocationId) WHERE ResumedAt IS NULL; IX_PauseEvent_OpenByLocation
T051 | 2 | W1 - Foundation & LOT Core | Migration | SQL Engineer | CREATE VIEW Lots.v_LotDerivedQuantities + genealogy indexes + LogEntityType row | 2 | T049 | NotStarted |  | v_LotDerivedQuantities(LotId,TotalInProcess,InventoryAvailable) diagnostic fallback under OI-35 B5 materialized-columns default. Genealogy indexes only if not partition-covered by Phase 1. +Audit.LogEntityType PauseEvent row
T052 | 2 | W1 - Foundation & LOT Core | Seed | SQL Engineer | Verify GenealogyRelationshipType/PrintReasonCode/LabelTypeCode code tables present | 1 | T049 | NotStarted |  | Confirm Arc-1 code-table seeds exist; add any missing. S-08 Tools.DieRankCompatibility owed (TRUE BLOCKER w/ supervisor-override per FDS-04-007); empty seed OK for build, merge tests need rows
T053 | 2 | W1 - Foundation & LOT Core | StoredProc | SQL Engineer | Lots.Lot_Update + Lot_UpdateAttribute (per-field LotAttributeChange + optimistic lock) | 3 | T049 | NotStarted |  | XDEP: Phase 1 (Lot_AssertNotBlocked B2). Lot_Update writes LotAttributeChange; B5 InventoryAvailable recalc. Lot_UpdateAttribute used by Lot_Split to reduce parent piece count
T054 | 2 | W1 - Foundation & LOT Core | StoredProc | SQL Engineer | Lots.Lot_Split (N-way split + genealogy + closure rows) | 4 | T049,T053 | NotStarted |  | XDEP: Phase 1 (Lot_Create/UpdateStatus, B2). SPLIT LotGenealogy + LotGenealogyClosure (B4), reduce parent, close if residual=0. Multi-row output. Consumed by Phase 5 + 7
T055 | 2 | W1 - Foundation & LOT Core | StoredProc | SQL Engineer | Lots.Lot_Merge (FDS-05-025..030 rules + die-rank gate + override) | 4 | T049,T052 | NotStarted |  | XDEP: Phase 1. Consumes S-08 DieRankCompatibility (TRUE BLOCKER); cross-die merges reject until populated, supervisor AD override per FDS-04-007. Same Item, all Good, post-sort, no HoldxGood. Output NULL Tool/Cavity
T056 | 2 | W1 - Foundation & LOT Core | StoredProc | SQL Engineer | Lots.LotGenealogy_RecordConsumption (consumption genealogy + closure) | 2 | T049 | NotStarted |  | XDEP: consumed by Phase 5 Machining IN + Phase 6 Assembly. Closure rows per B4. Output status-row
T057 | 2 | W1 - Foundation & LOT Core | StoredProc | SQL Engineer | Genealogy reads (GetGenealogyTree + GetParents + GetChildren + GetAttributeHistory) | 3 | T049 | NotStarted |  | XDEP: OI-35 B4 (closure-table vs recursive CTE MAXRECURSION 100). B8 depth bound 100 = business-rule violation. GetAttributeHistory unions LotAttributeChange+StatusHistory+Movement
T058 | 2 | W1 - Foundation & LOT Core | StoredProc | SQL Engineer | Lots.LotLabel_Print + LotLabel_Reprint | 2 | T049 | NotStarted |  | Append-only. Print returns ZplContent; Reprint forces PrintReasonCode. Gateway ZPL dispatch is later-phase (B6/B17); no new gateway script in Phase 2
T059 | 2 | W1 - Foundation & LOT Core | StoredProc | SQL Engineer | LOT pause lifecycle procs (Place/Resume/GetByLocation/GetCountsByLocation) | 3 | T050 | NotStarted |  | Place enforces open-event invariant B3 (filtered UNIQUE) + Lot_AssertNotBlocked; Resume rejects already-resumed; resumer MAY differ from pauser. No TTL/auto-resume
T060 | 2 | W1 - Foundation & LOT Core | NamedQuery | SQL / Integration | Named Queries wrapping all Phase-2 procs | 3 | T053,T054,T055,T056,T057,T058,T059 | NotStarted |  | Mutation procs (status-row SELECT) MUST set attributes.type=Query (UpdateQuery throws). Run scan.ps1 after
T061 | 2 | W1 - Foundation & LOT Core | Frontend | Perspective Engineer | LOT Detail top-level view (@LotId naturally-parametric B12) | 10 | T060 | NotStarted |  | XDEP: Phase 1 (Lot_Get). One LOT Detail across whole plant, no per-station variants. Flex Repeater for history/genealogy cards. Pre-declare bound custom props; atomic state writes; ConfirmUnsaved on dirty edits
T062 | 2 | W1 - Foundation & LOT Core | Frontend | Perspective Engineer | LOT Search top-level view (filter-driven) | 6 | T060 | NotStarted |  | XDEP: Phase 1 (Lot_List). Explicit Apply/Reset; TOP-cap + TotalCount window. ia.display.table onSelectionChange row-click -> LOT Detail
T063 | 2 | W1 - Foundation & LOT Core | Frontend | Perspective Engineer | Genealogy Viewer top-level view (@LotId) | 8 | T060 | NotStarted |  | Flex Repeater ancestor/descendant cards (B12). Verify mpp/ icon paths against mpp.svg before use
T064 | 2 | W1 - Foundation & LOT Core | Frontend | Perspective Engineer | Paused-LOT Indicator component + tap-through detail list | 5 | T060 | NotStarted |  | Badge count from GetCountsByLocation; list from GetByLocation. Reused on every workstation view (B12). Page-scoped messages embed->parent. Resume via LotPause_Resume
T065 | 2 | W1 - Foundation & LOT Core | Testing | QA / SQL | Test 010 Lot_Update (field audit + row-version + blocked + B5 recalc) | 3 | T053 | NotStarted |  | Suite renumbered 0020. INSERT-EXEC temp-table assert; dynamic location lookups (no seed-coupled hardcodes)
T066 | 2 | W1 - Foundation & LOT Core | Testing | QA / SQL | Test 020 Lot_Split (N-way + sum-exceeds reject + closure rows + parent close) | 3 | T054 | NotStarted |  | Assert LotGenealogy + LotGenealogyClosure rows; parent residual=0 -> Closed
T067 | 2 | W1 - Foundation & LOT Core | Testing | QA / SQL | Test 030 Lot_Merge (same/cross-die compat + override + NULL Tool/Cavity) | 4 | T055 | NotStarted |  | Seeds DieRankCompatibility rows locally for compat cases (S-08 escape). Covers FDS-04-007 override branch
T068 | 2 | W1 - Foundation & LOT Core | Testing | QA / SQL | Test 040 LotGenealogy_RecordConsumption (+ multi-source) | 2 | T056 | NotStarted
T069 | 2 | W1 - Foundation & LOT Core | Testing | QA / SQL | Test 050 Lot_GetGenealogyTree (Ancestors/Descendants/Both + depth bound + closure-vs-CTE) | 3 | T057 | NotStarted |  | XDEP: OI-35 B4 equivalence test only when closure elected
T070 | 2 | W1 - Foundation & LOT Core | Testing | QA / SQL | Test 060 LotPause lifecycle (place/resume + double-place reject + open-event invariant) | 3 | T059 | NotStarted |  | Assert ResumedAt IS NULL after Place, IS NOT NULL after Resume (B9)
T071 | 2 | W1 - Foundation & LOT Core | Testing | QA / SQL | Test 065 LotPause indicator (counts + ordered list) | 2 | T059 | NotStarted
T072 | 2 | W1 - Foundation & LOT Core | Testing | QA / SQL | Test 070 Label print/reprint (initial + reason + ZPL render) | 2 | T058 | NotStarted |  | Phase-2 gate. Suite 0020 target 90-120 assertions
T073 | 3 | W2 - Production Flow (Cast->Machining) | Migration | SQL Engineer | Create 0022_arc2_phase3_die_cast.sql migration shell (no new tables) | 1 | T072 | NotStarted |  | XDEP: Phase 1, Phase 2. CORRECTED number 0021 not 0016. SchemaVersion row + idempotent guards; section markers for seeds below
T074 | 3 | W2 - Production Flow (Cast->Machining) | Seed | SQL Engineer | Seed Parts.OperationTemplate DieCastShot (Draft->Published) | 2 | T073 | NotStarted |  | Versioned entity; three-state. ASCII-only Name/Description
T075 | 3 | W2 - Production Flow (Cast->Machining) | Seed | SQL Engineer | Seed DieCastShot data-collection fields (DieInfo/CavityInfo/Weight/Good/Bad/ShotCount) | 2 | T074 | NotStarted |  | OperationTemplate field/value-definition child rows; code-table backed types; ordering via up/down rank not drag
T076 | 3 | W2 - Production Flow (Cast->Machining) | Seed | SQL Engineer | Seed Audit.LogEventType rows DieCastCheckpointRecorded + RejectEventRecorded | 1 | T073 | NotStarted |  | ASCII-only; idempotent MERGE/IF NOT EXISTS
T077 | 3 | W2 - Production Flow (Cast->Machining) | StoredProc | SQL Engineer | Workorder.ProductionEvent_Record (checkpoint shape + cumulative counters + value rows) | 4 | T075 | NotStarted |  | LAG-delta cumulative counters; warm-up shots -> DowntimeEvent Setup; materialize TotalInProcess/InventoryAvailable per OI-35 B5; ScrapSource discriminator FDS-06-023a; emits DieCastCheckpointRecorded; @Status/@Message/@NewId locals, no OUTPUT
T078 | 3 | W2 - Production Flow (Cast->Machining) | StoredProc | SQL Engineer | Workorder.RejectEvent_Record (per defect code S-03) | 3 | T076 | NotStarted |  | Transactional; writes reject rows + RejectEventRecorded audit; updates ScrapCount/materialized inventory; status-row pattern
T079 | 3 | W2 - Production Flow (Cast->Machining) | StoredProc | SQL Engineer | Tools.ToolAssignment_ListActiveByCell (active mounted tool lookup) | 1 | T073 | NotStarted |  | Read proc; empty result = none; no OUTPUT
T080 | 3 | W2 - Production Flow (Cast->Machining) | StoredProc | SQL Engineer | Tools.ToolCavity_ListActiveByTool (active cavities for mounted tool) | 1 | T079 | NotStarted |  | Read proc; feeds cavity/item selection in LOT entry view
T081 | 3 | W2 - Production Flow (Cast->Machining) | NamedQuery | SQL / Integration | Wrap Phase-3 procs as Named Queries | 2 | T077,T078,T079,T080 | NotStarted |  | Mutation procs (Record) need attributes.type=Query; List procs default. Run scan.ps1
T082 | 3 | W2 - Production Flow (Cast->Machining) | GatewayScript | Gateway / Integration | DieCastCycleReader gateway script (per-press PLC CycleComplete edge, OPTIONAL) | 6 | T081 | NotStarted |  | Edge-detect CycleComplete OPC tag per press via TOPServer; dispatch ProductionEvent_Record checkpoint; async; log to Audit.InterfaceLog; feature-flagged
T083 | 3 | W2 - Production Flow (Cast->Machining) | Frontend | Perspective Engineer | Die Cast LOT Entry view (purpose-built top-level) | 10 | T081 | NotStarted |  | Scan LTT -> auto-populate mounted Tool -> cavity/item select -> eligibility+max-lot-size validate -> write ProductionEvent. No Initial LTT print at Die Cast. Routes to Phase 2 LOT Detail. Pre-declare bound custom props
T084 | 3 | W2 - Production Flow (Cast->Machining) | Frontend | Perspective Engineer | Reject Entry embedded component (per-defect-code capture) | 4 | T083 | NotStarted |  | Embed; page-scoped message to parent for reject submit; defect code picker from seeded codes; input-only params
T085 | 3 | W2 - Production Flow (Cast->Machining) | Frontend | Perspective Engineer | Checkpoint summary embedded component (cumulative counters readback) | 3 | T083 | NotStarted |  | Embed reads materialized totals; StateBadge-style guards for unselected state
T086 | 3 | W2 - Production Flow (Cast->Machining) | Testing | QA / SQL | Phase-3 test suite (checkpoint/LAG-delta + reject + tool/cavity + eligibility/max-lot) | 4 | T077,T078,T079,T080 | NotStarted |  | Phase-3 gate. ~50-70 assertions. INSERT-EXEC temp tables; assert cumulative deltas, warm-up->Setup downtime, ScrapSource discriminator, eligibility+max-lot rejection
T087 | 4 | W2 - Production Flow (Cast->Machining) | Migration | SQL Engineer | Migration 0023_arc2_phase4_movement_trim_receiving.sql (OperationTemplate + LogEventType seeds) | 2 | T048,T086 | NotStarted |  | XDEP: Phase 1, Phase 3. No new tables, NO RequiresSubLotSplit ALTER (relocated to Phase 5/0023). Seeds OperationTemplate {TrimIn,TrimOut,ReceivingScan} + LogEventType {LotMoved,TrimCheckpointRecorded,TrimOutRecorded,ReceivingScanRecorded}
T088 | 4 | W2 - Production Flow (Cast->Machining) | StoredProc | SQL Engineer | Parts.ItemLocation_CheckEligibility (fronts every scan-in) | 2 | T087 | NotStarted |  | Reads v_EffectiveItemLocation (direct U BOM-derived). Returns eligible/ineligible + reason. Read-only check, no audit write
T089 | 4 | W2 - Production Flow (Cast->Machining) | StoredProc | SQL Engineer | Parts.Item_GetMaxParts read proc | 1 | T087 | NotStarted |  | Returns MaxParts per item for capacity validation on scan-in
T090 | 4 | W2 - Production Flow (Cast->Machining) | StoredProc | SQL Engineer | Lots.Lot_GetCellLineQuantity (LinesideLimit cap read) | 1 | T087 | NotStarted |  | Returns current cell/line on-hand qty for LinesideLimit cap enforcement
T091 | 4 | W2 - Production Flow (Cast->Machining) | StoredProc | SQL Engineer | Lots.Lot_GetWipQueueByLocation read proc | 1 | T087 | NotStarted |  | FIFO WIP queue read for a location (Trim Station IN pick list)
T092 | 4 | W2 - Production Flow (Cast->Machining) | StoredProc | SQL Engineer | Workorder.TrimOut_Record (ProductionEvent + whole-LOT 1:1 LotMovement) | 3 | T087 | NotStarted |  | Whole-LOT 1:1 LotMovement to destination Machining line at Area resolution, NO split. Audit TrimOutRecorded. Status-row pattern
T093 | 4 | W2 - Production Flow (Cast->Machining) | NamedQuery | SQL / Integration | Named Queries wrapping all Phase-4 procs | 2 | T088,T089,T090,T091,T092 | NotStarted |  | Mutation procs (TrimOut_Record) get attributes.type=Query. Read NQs default. Run scan.ps1
T094 | 4 | W2 - Production Flow (Cast->Machining) | GatewayScript | Gateway / Integration | LttZplDispatcher gateway message handler | 5 | T087 | NotStarted |  | Message handler: renders LTT ZPL -> Zebra socket per B6. ASCII-only ZPL. Logs dispatch to Audit.InterfaceLog
T095 | 4 | W2 - Production Flow (Cast->Machining) | Frontend | Perspective Engineer | Movement Scan embedded component (cross-cutting reusable) | 5 | T093 | NotStarted |  | Reused by Trim/Receiving + later phases. Calls ItemLocation_CheckEligibility before accept; enforces MaxParts + LinesideLimit. Input-only itemId param; page-scoped replies
T096 | 4 | W2 - Production Flow (Cast->Machining) | Frontend | Perspective Engineer | Trim Station IN top-level view (FIFO pick / scan) | 8 | T093,T095 | NotStarted |  | FIFO pick from Lot_GetWipQueueByLocation or scan; LotMovement to Trim Shop Area. Embeds Movement Scan. Routes to Phase 2 LOT Detail
T097 | 4 | W2 - Production Flow (Cast->Machining) | Frontend | Perspective Engineer | Trim Station OUT top-level view (whole-LOT move + weight estimate) | 9 | T093,T095 | NotStarted |  | TrimOut_Record; weight-based piece-count estimation (FDS-06-005) accept/keep -> LotAttributeChange non-blocking. Embeds Movement Scan
T098 | 4 | W2 - Production Flow (Cast->Machining) | Frontend | Perspective Engineer | Receiving Dock top-level view (pass-through scan) | 6 | T093,T095 | NotStarted |  | Pass-through scan; LotMovement + ReceivingScanRecorded. Embeds Movement Scan
T099 | 4 | W2 - Production Flow (Cast->Machining) | Testing | QA / SQL | Phase-4 proc test suite | 4 | T088,T089,T090,T091,T092 | NotStarted |  | Phase-4 gate. ~55-75 assertions: eligibility (direct U BOM), max-parts + lineside caps, trim-out whole-move 1:1, wip queue, movement. Split tests NOT here (Phase 5)
T100 | 5 | W2 - Production Flow (Cast->Machining) | Migration | SQL Engineer | 0024_arc2_phase5_machining.sql - ALTER OperationTemplate ADD RequiresSubLotSplit | 2 | T099 | NotStarted |  | CORRECTED number 0023 (NOT 0018 - 0018 is shipped Arc-1 tooltype). Column relocated here from Phase 4. XDEP: Phase 1, Phase 2, Phase 3, Phase 4
T101 | 5 | W2 - Production Flow (Cast->Machining) | Seed | SQL Engineer | Seed OperationTemplate MachiningIn + MachiningOut | 1 | T100 | NotStarted |  | Doc-fix note (NOT a build task): DM still describes RequiresSubLotSplit under Trim OUT - relocate in data model at next bump
T102 | 5 | W2 - Production Flow (Cast->Machining) | Seed | SQL Engineer | Seed Audit.LogEventType (MachiningInPicked/OutCompleted/OutAutoMoved/OutSubLotSplit) | 1 | T100 | NotStarted
T103 | 5 | W2 - Production Flow (Cast->Machining) | StoredProc | SQL Engineer | Workorder.MachiningIn_PickAndConsume (FIFO pick + BOM-driven Trim->Machining rename) | 4 | T101 | NotStarted |  | ConsumptionEvent (Consumed=trim Produced=machined) + LotGenealogy Consumption edge + new machined-LOT create. Transactional. Audit MachiningInPicked. XDEP: Phase 2 RecordConsumption
T104 | 5 | W2 - Production Flow (Cast->Machining) | StoredProc | SQL Engineer | Workorder.MachiningOut_AutoComplete (PLC OperationComplete -> auto-move whole LOT) | 3 | T101 | NotStarted |  | ProductionEvent + auto-move whole LOT to CoupledDownstreamCellLocationId (non-sublotting lines). Audit OutCompleted + OutAutoMoved. No operator screen these lines
T105 | 5 | W2 - Production Flow (Cast->Machining) | StoredProc | SQL Engineer | Workorder.MachiningOut_RecordSplit (operator-initiated N-way even split) | 4 | T101 | NotStarted |  | Fresh LTT per child via IdentifierSequence_Next, LotGenealogy Split edges, moves, child labels, parent decrement/close. Uneven adjust per FDS-05-010. PENDING UJ-03 even-split default. XDEP: Phase 2 Lot_Split
T106 | 5 | W2 - Production Flow (Cast->Machining) | GatewayScript | Gateway / Integration | MachiningOpCompleteWatcher (per-Cell PLC OperationComplete edge) | 7 | T104 | NotStarted |  | TOPServer edge -> MachiningOut_AutoComplete (non-sublotting auto-complete)
T107 | 5 | W2 - Production Flow (Cast->Machining) | GatewayScript | Gateway / Integration | MachiningCycleReader (optional per-Cell PLC CycleComplete) | 6 |  | NotStarted |  | Optional per FRS. XDEP: TOPServer tag config (S-04)
T108 | 5 | W2 - Production Flow (Cast->Machining) | NamedQuery | SQL / Integration | Named Queries wrapping Phase-5 procs | 2 | T103,T104,T105 | NotStarted |  | Mutation NQs need attributes.type=Query (status-row). Run scan.ps1
T109 | 5 | W2 - Production Flow (Cast->Machining) | Frontend | Perspective Engineer | Cell Selector Repeater Entity (cross-cutting embedded) | 4 | T108 | NotStarted |  | Destination/cell picker reused by IN and OUT-Split screens (B12)
T110 | 5 | W2 - Production Flow (Cast->Machining) | Frontend | Perspective Engineer | BOM-Driven Rename Confirmation Modal (cross-cutting embedded) | 4 | T108 | NotStarted |  | Shows Trim->Machining 1-line BOM rename before consume-commit
T111 | 5 | W2 - Production Flow (Cast->Machining) | Frontend | Perspective Engineer | Machining IN view (purpose-built top-level) | 9 | T108,T109,T110 | NotStarted |  | FIFO queue list w/ override + scan, invokes PickAndConsume
T112 | 5 | W2 - Production Flow (Cast->Machining) | Frontend | Perspective Engineer | Machining OUT Split view (top-level, sublotting lines only) | 9 | T108,T109 | NotStarted |  | N-way even-split entry + destination-picker Flex Repeater rendering N pickers per child (B12), invokes RecordSplit
T113 | 5 | W2 - Production Flow (Cast->Machining) | Testing | QA / SQL | Phase-5 proc test suite | 4 | T103,T104,T105 | NotStarted |  | Phase-5 gate. ~80-110 assertions: machining-in pick+rename+consumption, auto-complete+auto-move, sub-LOT split (even+uneven), genealogy permanence, FIFO ordering
T114 | 6 | W3 - Assembly & Containers | Migration | SQL Engineer | Migration 0025_arc2_phase6_assembly.sql - CREATE Container family + ShippingLabel + seeds | 4 | T113 | NotStarted |  | XDEP: Phase 1-5; Phase 7 AimShipperIdPool schema must exist first (Container_Complete claims from pool). CREATE Lots.Container, ContainerTray, ContainerSerial (incl HardwareInterlockBypassed BIT DEFAULT 0 per C-9), SerializedPart, ShippingLabel (PrintedAt NULL, added per C-5). Seeds OperationTemplate assembly rows; LogEntityType Container/Tray/Serial/SerializedPart/ShippingLabel; LogEventType ContainerOpened/TrayClosed/ContainerCompleted/ContainerSerialAdded/MaterialSubstituteOverride/WorkOrderCompletionConfirmed
T115 | 6 | W3 - Assembly & Containers | StoredProc | SQL Engineer | Lots.Container_Open | 2 | T114 | NotStarted |  | Open container against assembly station + work order; audit ContainerOpened
T116 | 6 | W3 - Assembly & Containers | StoredProc | SQL Engineer | Lots.ContainerTray_Close (ByCount/ByWeight/ByVision) | 4 | T114 | NotStarted |  | Three closure methods dispatched by @ClosureMethod; per-tray Workorder.ConsumptionEvent emit; audit TrayClosed
T117 | 6 | W3 - Assembly & Containers | StoredProc | SQL Engineer | Lots.ContainerSerial_Add | 2 | T114 | NotStarted |  | Add serialized part scan to open container/tray; HardwareInterlockBypassed flag passthrough; audit ContainerSerialAdded
T118 | 6 | W3 - Assembly & Containers | StoredProc | SQL Engineer | Lots.SerializedPart_Mint (IdentifierSequence_Next MESI) | 2 | T114 | NotStarted |  | Mint MESI serial via IdentifierSequence_Next; insert SerializedPart. XDEP: Phase 1 IdentifierSequence_Next
T119 | 6 | W3 - Assembly & Containers | StoredProc | SQL Engineer | Lots.Container_Complete (atomic complete + AIM claim + ShippingLabel + async print + auto-close LOT) | 4 | T115,T116,T117,T132,T141 | NotStarted |  | Atomic txn: set Complete + AimShipperIdPool_Claim + INSERT ShippingLabel PrintedAt=NULL + async ShippingLabelDispatcher + auto-close finished-good LOT. XDEP: Phase 7 AimShipperIdPool_Claim. Audit ContainerCompleted
T120 | 6 | W3 - Assembly & Containers | StoredProc | SQL Engineer | Workorder.ConsumptionEvent_RecordWithBomCheck (UJ-09 substitute override) | 4 | T114 | NotStarted |  | BOM material verification at consumption; supervisor substitute override (UJ-09) with AD elevation; audit MaterialSubstituteOverride on override. XDEP: Phase 2 RecordConsumption pattern
T121 | 6 | W3 - Assembly & Containers | NamedQuery | SQL / Integration | Named Queries wrapping Phase-6 procs | 2 | T115,T116,T117,T118,T119,T120 | NotStarted |  | Mutation procs get attributes.type=Query for status-row SELECT. Run scan.ps1
T122 | 6 | W3 - Assembly & Containers | GatewayScript | Gateway / Integration | AssemblyMipHandler gateway script (serialized line MIP via TOPServer) | 12 | T121 | NotStarted |  | Full MIP handshake: PartSN/PartValid/DataReady/HardwareInterlockEnable/CompletionConfirmed/TrayFullFlag via TOPServer; alarms to AlarmMsg; ContainerFullFlag legacy-cutover; calls ContainerSerial_Add/SerializedPart_Mint/ContainerTray_Close. S-04 OPC tags
T123 | 6 | W3 - Assembly & Containers | GatewayScript | Gateway / Integration | NonSerializedLineHandler gateway script (PLC + OmniServer scale) | 10 | T121 | NotStarted |  | PLC + OmniServer scale for ByWeight; PartDisposition/VisionPartNumber; calls ContainerTray_Close ByWeight/ByVision
T124 | 6 | W3 - Assembly & Containers | GatewayScript | Gateway / Integration | ShippingLabelDispatcher gateway script (message handler + Zebra socket) | 8 | T121 | NotStarted |  | Dispatch from Container_Complete; Zebra ZPL over socket; 3x2s retry; on failure surface to Print Failure Banner. XDEP: reused by Phase 7
T125 | 6 | W3 - Assembly & Containers | Frontend | Perspective Engineer | Assembly Serialized view (top-level) | 10 | T121 | NotStarted |  | MIP status surface; serial scan list; tray/container state; completion confirm
T126 | 6 | W3 - Assembly & Containers | Frontend | Perspective Engineer | Assembly Non-Serialized view (top-level) | 8 | T121 | NotStarted |  | ByCount/ByWeight/ByVision closure UX; scale reading display; part disposition
T127 | 6 | W3 - Assembly & Containers | Frontend | Perspective Engineer | Confirmation Method Resolver (embedded component) | 4 | T121 | NotStarted |  | Cross-cutting; reads ConfirmationMethod LocationAttribute -> Vision/Barcode/Both UX branch (UJ-17/FDS-10-013)
T128 | 6 | W3 - Assembly & Containers | Frontend | Perspective Engineer | Print Failure Banner (embedded component) | 3 | T124 | NotStarted |  | Cross-cutting; reused in Phase 7; subscribes to ShippingLabelDispatcher failure message; retry action
T129 | 6 | W3 - Assembly & Containers | Frontend | Perspective Engineer | Material Substitute Override Modal (embedded component) | 4 | T121 | NotStarted |  | Cross-cutting; UJ-09 supervisor override; AD elevation prompt; calls ConsumptionEvent_RecordWithBomCheck override path
T130 | 6 | W3 - Assembly & Containers | Testing | QA / SQL | Test suite - container/tray/serial procs (open/3 close methods/add/mint) | 4 | T115,T116,T117,T118 | NotStarted |  | Container open; ByCount/ByWeight/ByVision tray close + per-tray ConsumptionEvent; serial add; MESI mint. INSERT-EXEC temp-table pattern
T131 | 6 | W3 - Assembly & Containers | Testing | QA / SQL | Test suite - Container_Complete + AIM claim + ShippingLabel + BOM check + MIP + auto-finish | 4 | T119,T120 | NotStarted |  | Phase-6 gate. Complete atomicity + AIM claim + ShippingLabel PrintedAt=NULL; BOM material check pass/fail + override; MIP proc-layer; auto-finish + WorkOrderCompletionConfirmed (FDS-06-028). ~100-135 assertions across both files
T132 | 7 | W4 - Fulfillment (Hold/Ship/AIM) | Migration | SQL Engineer | CREATE 0026_arc2_phase7 - HoldEvent + AimShipperIdPool + AimPoolConfig + ContainerSerialHistory | 4 | T072 | NotStarted |  | XDEP: Phase 1, Phase 2, Phase 6. CREATE Quality.HoldEvent (C-4, no longer Phase 1). AimShipperIdPool+AimPoolConfig must ship BEFORE Phase 6 Container_Complete claims - keep CREATE callable early. ContainerSerialHistory = UJ-05 update-in-place serial migration audit; structure for void-and-recreate swap. Open-event invariant via filtered unique index
T133 | 7 | W4 - Fulfillment (Hold/Ship/AIM) | Seed | SQL Engineer | Seed Quality.HoldTypeCode rows | 1 | T132 | NotStarted |  | CustomerComplaint, QualityIssue, EngineeringHold, ProductionHold, ContainerHold. ASCII-only. Code-table FK for HoldEvent.HoldTypeId
T134 | 7 | W4 - Fulfillment (Hold/Ship/AIM) | Seed | SQL Engineer | Seed Lots.AimPoolConfig single row (S-11 defaults) | 1 | T132 | NotStarted |  | TargetBuffer=50, Topup=30, Warn=20, Crit=10. Tuned later via AimPoolConfig admin view
T135 | 7 | W4 - Fulfillment (Hold/Ship/AIM) | Seed | SQL Engineer | Seed Audit.LogEntityType (4) + LogEventType (10) rows | 1 | T132 | NotStarted |  | LogEventType: HoldPlaced, HoldReleased, AimShipperIdClaimed, AimShipperIdToppedUp, AimPoolWarningAlarmFired, AimPoolCriticalAlarmFired, ContainerSerialMigrated, ShippingLabelVoided, ContainerShipped, PrintFailureSafetySweepRecovered
T136 | 7 | W4 - Fulfillment (Hold/Ship/AIM) | StoredProc | SQL Engineer | Quality.Hold_Place + Hold_Release | 4 | T132,T133,T135,T131 | NotStarted |  | Open-event invariant: reject Place when open HoldEvent exists for Lot/Container. Bulk hold FDS-08-006. Container hold FDS-07-015/016 dispatches AIM PlaceOnHold/ReleaseFromHold via AimHoldHandler. Status-row. Audit HoldPlaced/HoldReleased
T137 | 7 | W4 - Fulfillment (Hold/Ship/AIM) | StoredProc | SQL Engineer | Quality.Hold_GetOpenByLot + Hold_GetOpenByContainer | 2 | T132,T133 | NotStarted |  | No OUTPUT; empty set = no open hold. Resolved-name FK sub-objects
T138 | 7 | W4 - Fulfillment (Hold/Ship/AIM) | StoredProc | SQL Engineer | Lots.Container_Ship | 4 | T132,T135,T131 | NotStarted |  | Validate Complete + AIM-assigned + not-shipped + no open hold before ship. Audit ContainerShipped. Status-row
T139 | 7 | W4 - Fulfillment (Hold/Ship/AIM) | StoredProc | SQL Engineer | Lots.ShippingLabel_Void + ShippingLabel_Reprint | 3 | T132,T135,T131 | NotStarted |  | Reads/voids/reprints Lots.ShippingLabel (CREATEd in Phase 6 per C-5 - Phase 7 does NOT create it). Audit ShippingLabelVoided. Status-row
T140 | 7 | W4 - Fulfillment (Hold/Ship/AIM) | StoredProc | SQL Engineer | Lots.SortCage_MigrateSerial + ContainerSerialHistory writeback | 4 | T132,T135,T131 | NotStarted |  | UJ-05 update-in-place: write old->new serial pair to ContainerSerialHistory, void old shipping label, structure so void-and-recreate variant swaps without rebuild. Audit ContainerSerialMigrated. Status-row
T141 | 7 | W4 - Fulfillment (Hold/Ship/AIM) | StoredProc | SQL Engineer | Lots.AimShipperIdPool_Claim + AimShipperIdPool_Topup | 4 | T132,T134,T135 | NotStarted |  | Claim = FIFO with READPAST; hard-fail on empty pool per FDS-07-010a (OI-33) - no silent fallback. Topup inserts fetched IDs, audit AimShipperIdToppedUp. Claim audits AimShipperIdClaimed. Status-row. Consumed by Phase 6 Container_Complete
T142 | 7 | W4 - Fulfillment (Hold/Ship/AIM) | StoredProc | SQL Engineer | Lots.AimShipperIdPool_GetDepth + GetByContainer | 2 | T132,T134 | NotStarted |  | GetDepth -> available count for alarm monitor + wallboard. GetByContainer resolves claimed ID. No OUTPUT
T143 | 7 | W4 - Fulfillment (Hold/Ship/AIM) | StoredProc | SQL Engineer | Lots.AimPoolConfig_Get + AimPoolConfig_Update | 2 | T132,T134 | NotStarted |  | Get returns single config row. Update is status-row mutation; audit via AimPoolConfig entity type
T144 | 7 | W4 - Fulfillment (Hold/Ship/AIM) | NamedQuery | SQL / Integration | Named Queries wrapping all Phase-7 procs | 3 | T136,T137,T138,T139,T140,T141,T142,T143 | NotStarted |  | Mutation procs need attributes.type=Query (status-row JDBC). Run scan.ps1 after
T145 | 7 | W4 - Fulfillment (Hold/Ship/AIM) | GatewayScript | Gateway / Integration | AimPoolTopup gateway timer (30s AIM GetNextNumber) | 6 | T144 | NotStarted |  | 30s timer. Fetch AIM shipper IDs via HTTP/SOAP GetNextNumber when depth < TargetBuffer, call Topup. Log to Audit.InterfaceLog. Honors AimPoolConfig thresholds. B17 async
T146 | 7 | W4 - Fulfillment (Hold/Ship/AIM) | GatewayScript | Gateway / Integration | AimPoolAlarmMonitor gateway timer (60s warn/crit/exhausted) | 5 | T144 | NotStarted |  | 60s timer. GetDepth vs Warn/Crit; fire Warning/Critical/exhausted alarms. Audit alarm-fired events
T147 | 7 | W4 - Fulfillment (Hold/Ship/AIM) | GatewayScript | Gateway / Integration | AimHoldHandler message handler (AIM PlaceOnHold/ReleaseFromHold) | 6 | T144 | NotStarted |  | Dispatched by Hold_Place/Release for container holds (FDS-07-015/016). AIM PlaceOnHold/ReleaseFromHold; log Audit.InterfaceLog. FDS-01-014 async
T148 | 7 | W4 - Fulfillment (Hold/Ship/AIM) | GatewayScript | Gateway / Integration | AimUpdateHandler message handler (AIM UpdateAim re-sort) | 6 | T144 | NotStarted |  | Sort-cage re-sort serial migration (UJ-05). AIM UpdateAim to remap shipper assignment after serial replacement. Log Audit.InterfaceLog
T149 | 7 | W4 - Fulfillment (Hold/Ship/AIM) | GatewayScript | Gateway / Integration | PrintFailureSafetySweep gateway timer (5-min orphan recovery) | 6 | T144 | NotStarted |  | 5-min timer. Recover orphaned print failures; alarm when >5 stranded. Audit PrintFailureSafetySweepRecovered (FDS-07-006b)
T150 | 7 | W4 - Fulfillment (Hold/Ship/AIM) | GatewayScript | Gateway / Integration | PrintFailureBroadcaster gateway timer (5s per-terminal banner) | 5 | T144 | NotStarted |  | 5s timer. Broadcast per-terminal print-failure banner via session-filter (FDS-07-006b). Feeds Print Failure Banner. XDEP: Phase 6 print-failure source
T151 | 7 | W4 - Fulfillment (Hold/Ship/AIM) | Frontend | Perspective Engineer | Hold Management top-level view | 10 | T144 | NotStarted |  | Active-hold + container-hold lists, place/release, bulk hold (FDS-08-006), row-click nav to LOT Detail. onSelectionChange. XDEP: Phase 6 LOT Detail nav target (actually Phase 2)
T152 | 7 | W4 - Fulfillment (Hold/Ship/AIM) | Frontend | Perspective Engineer | Sort Cage Workflow top-level view | 10 | T144 | NotStarted |  | Unpack->inspect->re-pack; serial replacement via SortCage_MigrateSerial; print new LTT + shipping labels; void old; trigger AimUpdateHandler. Multi-step state machine in view.custom
T153 | 7 | W4 - Fulfillment (Hold/Ship/AIM) | Frontend | Perspective Engineer | Shipping Dock top-level view | 8 | T144 | NotStarted |  | Scan shipping label -> validate via Container_Ship preconditions -> confirm ship. Scan-driven
T154 | 7 | W4 - Fulfillment (Hold/Ship/AIM) | Frontend | Perspective Engineer | AIM Pool Configuration admin view (S-11 tuning) | 6 | T144 | NotStarted |  | Admin-only edit of AimPoolConfig single row via Config_Get/Update. editDraft/selected + dirty + ConfirmUnsaved. Pre-shape editDraft with every bound field
T155 | 7 | W4 - Fulfillment (Hold/Ship/AIM) | Frontend | Perspective Engineer | AIM Pool Wallboard Tile embedded component | 4 | T144 | NotStarted |  | Cross-cutting tile: pool depth via GetDepth, warn/crit color states vs config thresholds
T156 | 7 | W4 - Fulfillment (Hold/Ship/AIM) | Frontend | Perspective Engineer | Print Failure Banner (reused from Phase 6) | 3 | T150 | NotStarted |  | Wire Phase-6 Print Failure Banner to PrintFailureBroadcaster session-filtered messages
T157 | 7 | W4 - Fulfillment (Hold/Ship/AIM) | Testing | QA / SQL | Phase 7 SQL test suite | 4 | T136,T137,T138,T139,T140,T141,T142,T143 | NotStarted |  | Phase-7 gate. ~90-120 assertions. Hold place/release/bulk + open-event invariant, container ship validation, label void/reprint, sort-cage migration + history, AIM pool claim FIFO READPAST + hard-fail-empty (FDS-07-010a), topup, depth/alarms, config CRUD
T158 | 8 | W5 - OEE & Shift (parallel track) | Migration | SQL Engineer | 0027_arc2_phase8_downtime_shift.sql - CREATE Oee.DowntimeEvent + LogEventType seeds | 3 | T048 | NotStarted |  | CORRECTED number 0026 (not 0021). XDEP: Phase 1. Per C-4 Phase 8 OWNS the CREATE of Oee.DowntimeEvent (does not exist yet). One-open-per-machine invariant via filtered unique index WHERE EndedAt IS NULL. Nullable ReasonCodeId for late binding. Seed LogEventType: DowntimeStarted/DowntimeEnded/DowntimeReasonAssigned/EndOfShiftSubmitted/ShiftHandoverAcknowledged. Oee.Shift exists from Arc-1 0009 - NO Shift CREATE
T159 | 8 | W5 - OEE & Shift (parallel track) | StoredProc | SQL Engineer | Oee.DowntimeEvent_Start + DowntimeEvent_End | 2 | T158 | NotStarted |  | Start: nullable reason, enforces open-event invariant (refuse second open). End: closes open event, computes duration. Status-row procs -> NQ type=Query
T160 | 8 | W5 - OEE & Shift (parallel track) | StoredProc | SQL Engineer | Oee.DowntimeReasonCode_Assign (late-binding no-overwrite) | 1 | T158 | NotStarted |  | FDS-09-005 late-binding to existing (possibly closed) DowntimeEvent. Refuses overwrite of assigned reason. Audit DowntimeReasonAssigned
T161 | 8 | W5 - OEE & Shift (parallel track) | StoredProc | SQL Engineer | Oee.EndOfShiftEntry_Submit (single-submission) | 4 | T158 | NotStarted |  | FDS-09-013 single submit per shift (refuse second). Toggle-per-break; durations from shift schedule (Oee.Shift). Writes DowntimeEvent rows. Audit EndOfShiftSubmitted
T162 | 8 | W5 - OEE & Shift (parallel track) | StoredProc | SQL Engineer | Oee.Shift_GetEndOfShiftSummary (handover read) | 2 | T158 | NotStarted |  | FDS-09-015: open downtime, active pauses, in-process LOTs at shift end. No OUTPUT. Shift_End leaves open events open per UJ-10 Option D / OI-03
T163 | 8 | W5 - OEE & Shift (parallel track) | Seed | SQL Engineer | Invoke S-02 downtime reason code bulk-load (353-row CSV) | 2 | T158 | NotStarted |  | Bulk-load proc shipped Arc-1; invoke once Area mapping locks. Source reference/seed_data downtime_reason_codes. XDEP: Area->ReasonType mapping (FDS-09-005). ASCII byte-scan before apply
T164 | 8 | W5 - OEE & Shift (parallel track) | NamedQuery | SQL / Integration | Phase-8 Named Query wrappers | 2 | T159,T160,T161,T162 | NotStarted |  | Wraps DowntimeEvent_Start/End, ReasonCode_Assign, EndOfShiftEntry_Submit, Shift_GetEndOfShiftSummary + reason-code list filtered by Area+ReasonType. Mutation procs -> attributes.type=Query. Run scan.ps1
T165 | 8 | W5 - OEE & Shift (parallel track) | GatewayScript | Gateway / Integration | DowntimePlcWatcher (per-machine PLC stop/run edge) | 7 | T159 | NotStarted |  | TOPServer OPC stop/run edges. Stop edge -> DowntimeEvent_Start (NULL reason); run edge -> DowntimeEvent_End. Edge-detect/debounce; log Audit.InterfaceLog. S-04 OPC tags
T166 | 8 | W5 - OEE & Shift (parallel track) | GatewayScript | Gateway / Integration | EndOfShiftWindowTrigger (Perspective view-side timer) | 5 | T162 | NotStarted |  | View-side timer opens/prompts End-of-Shift entry within shift-end window from Oee.Shift schedule
T167 | 8 | W5 - OEE & Shift (parallel track) | Frontend | Perspective Engineer | Downtime Entry view (manual) | 8 | T164 | NotStarted |  | Machine auto-pop from station context. Reason dropdown filtered by Area + ReasonType (FDS-09-005). Start/End + late reason assign. Pre-declare bound custom props
T168 | 8 | W5 - OEE & Shift (parallel track) | Frontend | Perspective Engineer | End-of-Shift Time Entry view (toggle-per-break) | 8 | T164 | NotStarted |  | FDS-09-013 single-submission UI. One toggle per break; durations from schedule. Submit -> EndOfShiftEntry_Submit. Lock after submit. ConfirmUnsaved on close if dirty
T169 | 8 | W5 - OEE & Shift (parallel track) | Frontend | Perspective Engineer | Shift-end Summary view (read-only handover) | 6 | T164 | NotStarted |  | FDS-09-015: open downtime, active pauses, in-process LOTs from Shift_GetEndOfShiftSummary. Acknowledge -> Audit ShiftHandoverAcknowledged
T170 | 8 | W5 - OEE & Shift (parallel track) | Frontend | Perspective Engineer | Supervisor Dashboard view (5 tiles) | 10 | T164 | NotStarted |  | Tiles: DowntimeOpenSummary, PausedLotsSummary, ShiftAvailabilityTile, AimPoolWallboardTile, PrintFailureStrandedTile. Each bound to its read NQ. Pre-declare every bound custom prop
T171 | 8 | W5 - OEE & Shift (parallel track) | Testing | QA / SQL | Phase-8 SQL test suite | 4 | T159,T160,T161,T162 | NotStarted |  | Phase-8 gate. ~60-80 assertions: downtime start/end + open-event invariant, reason late-assign + no-overwrite, end-of-shift single submit (+ second-submit refusal), shift-end summary, reason filtering Area+ReasonType, shift availability derivation, Shift_End leaves open events open (UJ-10 Option D)
T172 | 9 | W6 - Quality Capture & Trace | Migration | SQL Engineer | CREATE Quality.QualitySample + QualityResult + QualityAttachment (migration 0028) | 3 | T048 | NotStarted |  | IN-SCOPE (confirmed 2026-06-08, G-1): inspection recording FDS-08-011/012/013. Runtime-captured tables specified in Data Model section 5. CREATE QualitySample (LotId, QualitySpecVersionId, InspectionResultCodeId, SampledByUserId, SampledAt), QualityResult (per-attribute MeasuredValue/NumericValue/IsPass), QualityAttachment (file metadata). XDEP: Phase 1 (Lot) + Arc-1 QualitySpec tables.
T173 | 9 | W6 - Quality Capture & Trace | StoredProc | SQL Engineer | Inspection recording procs (Sample_Record + GetByLot + Result writers + attachment metadata) | 4 | T172 | NotStarted |  | QualitySample_Record (header + per-attribute results + overall pass/fail + log), QualitySample_GetByLot, attachment metadata writer. Failed inspection = alert only, no auto-hold (FDS-08-012). Status-row pattern
T174 | 9 | W6 - Quality Capture & Trace | NamedQuery | SQL / Integration | Wrap inspection procs as Named Queries | 1 | T173 | NotStarted |  | Mutation procs -> attributes.type=Query
T175 | 9 | W6 - Quality Capture & Trace | Frontend | Perspective Engineer | Inspection Entry view | 8 | T174 | NotStarted |  | Sample against published spec; per-attribute result grid; overall pass/fail; file attach (CSV/XLSX/PDF/PNG/JPG to filesystem + metadata). Pre-declare bound custom props
T176 | 9 | W6 - Quality Capture & Trace | Frontend | Perspective Engineer | Inspection History read view | 4 | T174 | NotStarted |  | Read sample/result history per LOT; attachment download
T177 | 9 | W6 - Quality Capture & Trace | Testing | QA / SQL | Inspection recording test suite | 3 | T173 | NotStarted |  | Sample record, per-attribute results, pass/fail rollup, no-auto-hold. INSERT-EXEC temp-table
T178 | 9 | W6 - Quality Capture & Trace | StoredProc | SQL Engineer | Global Trace resolve + full-trace procs | 4 | T157 | NotStarted |  | IN-SCOPE (2026-06-08, G-3a Global Trace): FDS-12-012/013/014 Global Trace Tool is MVP; plan deferred to unscoped workstream. GlobalTrace_Resolve (LOT/Serial/Container/Shipper input -> entity, disambiguation) + GlobalTrace_GetFullTrace (header + genealogy tree + production + movement + holds + shipping). Reads existing event tables - NOT gated on UJ-19. XDEP: Phase 7 gate
T179 | 9 | W6 - Quality Capture & Trace | NamedQuery | SQL / Integration | Wrap Global Trace procs as Named Queries | 1 | T178 | NotStarted
T180 | 9 | W6 - Quality Capture & Trace | Frontend | Perspective Engineer | Global Trace Tool view (Track home tile) | 10 | T179 | NotStarted |  | Any-context read-only trace surface: input resolution + scan, header, genealogy tree, production, movement, holds, shipping, Print/Export. Primary Honda traceability deliverable (FDS-12-001/012/013/014)
T181 | 9 | W6 - Quality Capture & Trace | Testing | QA / SQL | Global Trace test suite | 3 | T178 | NotStarted |  | Resolve disambiguation + full-trace assembly across event tables
T182 | 9 | W6 - Quality Capture & Trace | Seed | SQL Engineer | CRT: seed audit event types (Lot.CrtActive shipped in Phase 1) | 1 |  | NotStarted |  | IN-SCOPE (2026-06-08, G-2). Lot.CrtActive BIT added to the Phase 1 Lot CREATE (Data Model v1.9q). This task seeds the CRT Audit.LogEventType rows (CrtActivated, CrtCleared, MissedCrtInspect) in the Phase 9 migration.
T183 | 9 | W6 - Quality Capture & Trace | StoredProc | SQL Engineer | CRT workflow procs + UI (200% inspect, missed-inspect re-run, release) | 8 | T182 | NotStarted |  | IN-SCOPE (2026-06-08, G-2). Lot_SetCrt/Lot_ClearCrt (supervisor-elevated) + Crt_GetRequiredInspections 200% gate + missed-inspect detection consumed by production procs + supervisor-AD-elevated clearance. Spans Phase 6 (assembly inspect) + Phase 7 (release). Builds on the QualitySample inspection stream (T172).
T184 | 9 | W6 - Quality Capture & Trace | Reporting | Reporting Engineer | Reporting workstream - PD-replacement operational reports (DEFERRED) | 16 |  | Deferred |  | DEFERRED to near/post-deployment per 2026-06-08 decision. Die Shot/Rejects/Downtime/Production reports + Shipping History via Ignition Reporting module over ProductionEvent/RejectEvent/DowntimeEvent/Shift. Gated on UJ-19 (MPP names the 4 PD reports + data sources). NOT the Global Trace Tool - that is in-scope (T178-T181).

## Workstreams
Suggested Workstreams (vertical feature tracks for assignment)
Workstream | Phases | Tasks | Hours | Dev-days | Description
W0 - Decisions & Architecture | 0 | 9 | 29 | 3.6 | Phase 0 customer-validation (A1-A9) + OI-35 architecture decisions. MUST finish before any build. Owner: Architect + PM + MPP.
W1 - Foundation & LOT Core | 1-2 | 63 | 220 | 27.5 | Operator session, terminal routing, LOT core + full lifecycle. CRITICAL PATH - everything depends on it. Senior SQL+Perspective pair, sequential.
W2 - Production Flow (Cast->Machining) | 3-5 | 41 | 153 | 19.1 | Die Cast -> Trim/Move -> Machining. Sequential chain. One vertical team across SQL+Gateway+Perspective.
W3 - Assembly & Containers | 6 | 18 | 91 | 11.4 | Serialized MIP + non-serialized assembly, tray-level container packing, shipping-label mint. Heavy Gateway/PLC. After W2.
W4 - Fulfillment (Hold/Ship/AIM) | 7 | 26 | 114 | 14.2 | Hold, sort cage, shipping dock, AIM pool. SCHEMA ships early (parallel with W3); operational procs need W3 container tables.
W5 - OEE & Shift (parallel track) | 8 | 14 | 64 | 8 | Downtime + shift/end-of-shift. PARALLEL from Phase 1 - a separate engineer alongside W1-W4.
W6 - Quality Capture & Trace | 9 | 13 | 66 | 8.2 | MVP gap-closure (ratified 2026-06-08): inspection recording (G-1) + Controlled Run Tag (G-2) + Global Trace Tool/Genealogy Report (G-3a). PD operational reports DEFERRED (T184, pending UJ-19).
TOTAL | 0-9 | 184 | 737 | 92.1

## By Phase
Per-Phase Summary (the Gate task is the phase exit criterion)
Phase | Title | Workstream | Tasks | Hours | Gate Task (exit)
0 | Customer Validation + Architecture (OI-35) | W0 - Decisions & Architecture | 9 | 29 | T009
1 | Shop Floor Foundation | W1 - Foundation & LOT Core | 39 | 135 | T048
2 | LOT Lifecycle Completion | W1 - Foundation & LOT Core | 24 | 85 | T072
3 | Die Cast Operator Station | W2 - Production Flow (Cast->Machining) | 14 | 44 | T086
4 | Movement + Trim + Receiving | W2 - Production Flow (Cast->Machining) | 13 | 49 | T099
5 | Machining | W2 - Production Flow (Cast->Machining) | 14 | 60 | T113
6 | Assembly + MIP + Container Pack | W3 - Assembly & Containers | 18 | 91 | T131
7 | Hold + Sort Cage + Shipping + AIM | W4 - Fulfillment (Hold/Ship/AIM) | 26 | 114 | T157
8 | Downtime + Shift Boundary | W5 - OEE & Shift (parallel track) | 14 | 64 | T171
9 | Quality Capture + CRT + Global Trace | W6 - Quality Capture & Trace | 13 | 66 | T184

## By Role-Layer
Staffing View - effort by role / layer
Suggested Role | Category (layer) | Tasks | Hours | Dev-days
Perspective Engineer | Frontend | 40 | 254 | 31.8
SQL Engineer | StoredProc | 49 | 145 | 18.1
Gateway / Integration | GatewayScript | 19 | 120 | 15
QA / SQL | Testing | 24 | 76 | 9.5
SQL Engineer | Migration | 19 | 57 | 7.1
Architect / PM | Decision | 8 | 25 | 3.1
SQL / Integration | NamedQuery | 10 | 22 | 2.8
SQL Engineer | Seed | 13 | 18 | 2.2
Reporting Engineer | Reporting | 1 | 16 | 2
Architect / PM | Documentation | 1 | 4 | 0.5

## ReadMe
MPP MES - Plant Floor (Arc 2) Task List
Companion to MPP_MES_PHASED_PLAN_PLANT_FLOOR.md (v1.3) and MPP_MES_PLANT_FLOOR_PLAN_VALIDATION.md. 184 tasks, ~737 h (~92 dev-days).
Grouping columns: Workstream (vertical feature track, W0-W6) and SuggestedRole (SQL/Gateway/Perspective/QA/Architect). Workstream x Role = a staffing grid.
Suggested swimlanes
Lane 1 (critical path, sequential): W0 -> W1 -> W2 -> W3 -> W4 -> W6.
Lane 2 (parallel from Phase 1): W5 OEE & Shift.
Lane 3 (schema-first overlap): W4 AIM-pool schema ships during W3.
Within a phase: SQL Engineer lands the proc layer first, then Gateway + Perspective work in parallel off it, QA writes the suite. The Gate task is the exit criterion.
Status legend
NotStarted = ready once dependencies clear. Deferred (grey) = post-MVP: T184 PD operational reports (gated on UJ-19).
No Blocked tasks remain - the G-1/G-2/G-3a scope was ratified 2026-06-08 (quality capture, Controlled Run Tag, Global Trace all in-scope as Phase 9).
Migration / test-suite numbering (re-baselined 2026-06-08)
Arc 2 migrations 0020-0027 (Phases 1-8), Phase 9 = 0028. Re-baselined +1 after 0019_location_coupled_downstream_cell landed on disk.
Numbers are next-free-at-build-time - re-baseline against the actual high-water mark when the Arc 2 build commences (it is OI-35-gated).
Test suites 0020-0027 (Phase 9 suite 0028). Arc 1 test suites end at 0019.