# MPP MES — Phased Delivery Plan: Arc 2 (Plant Floor MES)

Document ID: MPP-PLAN-ARC2-v1.0 Project: Madison Precision Products MES Replacement Contractor: Blue Ridge Automation Version: 1.1 (2026-06-03) Status: Working draft — full rebuild against current source-of-truth docs (FDS v0.11m, Data Model v1.9l, User Journeys v0.9, Open Issues Register v2.16, Seeding Registry v1.0). Supersedes the v0.1 → v0.3 line; the prior draft chain is retained in git history.

Reader note (v1.0): This is a clean rebuild. Read top-to-bottom. Cross-Cutting Concerns (B1–B17) are normative for every phase. Phase 0 has two parallel tracks — MPP-owned customer validation and Blue Ridge–owned architecture decisions (OI-35) — both must complete before Phase 1 SQL build commences. Per-phase narratives reference current source-of-truth docs by version; updates to those docs propagate here at the next plan revision.

In-progress note (v1.0a, 2026-04-29): This file currently contains Phases 0–4 of the rebuild. Phases 5–8 are placeholders awaiting review of the first half. The closing sections (Out of Scope, Open Items Affecting This Plan, Related Documents) will land with Phases 5–8.

## Revision History

| Version | Date | Author | Change Summary |
| --- | --- | --- | --- |
| 1.1 | 2026-06-03 | Blue Ridge Automation | Sub-LOT split relocated from Trim OUT to Machining OUT (per MPP, confirmed 2026-06 — settled, not an open item). Reverses the v1.0 driver-(a) claim that the split sits at Trim OUT. Trim is now a 1:1 whole-LOT move tracked at Area resolution; the Parts.OperationTemplate.RequiresSubLotSplit flag plus the split UX / *_Record split branch / split tests move from Phase 4 (Trim, migration 0017) to Phase 5 (Machining OUT, migration 0018). Phase 4 Trim OUT becomes move-whole-only (TrimOut_Record no longer splits); Phase 5 Machining OUT gains an operator-initiated split path on sublotting lines (physical signature: a dedicated Machining OUT terminal) alongside the existing PLC auto-move on coupled lines. UJ-03 reframed (was closed backwards as “Machining no longer splits”). The Phase 4→5 ordering is unchanged but its nature shifts: a whole-LOT handoff into the Machining FIFO queue, not pre-split sub-LOTs. Mirrors FDS v1.3. No schema change — Lot.ParentLotId / LotGenealogy already model machining-origin sub-LOTs; the RequiresSubLotSplit column simply lands in 0018 instead of 0017. |
| 1.0 | 2026-04-29 | Blue Ridge Automation | Full rebuild against current source-of-truth docs. Replaces the v0.1 → v0.3 line. Drivers: (a) the v0.11k/l/m FDS continuity passes shifted three workflow boundaries — sub-LOT split moved from Machining IN to Trim OUT (FDS-05-009), part-identity rename moved from Casting→Trim to Trim→Machining (FDS-05-033), Machining OUT became event-driven PLC-auto-complete + auto-move to coupled Cell (FDS-06-008); (b) container closure granularity moved from container-level to tray-level with three peer methods ByCount / ByWeight / ByVision (FDS-06-014); (c) end-of-shift time entry reframed as a single FDS-09-013 submission with shift-schedule durations (no minute adjustments); (d) OIR v2.16 added OI-35 (long-horizon scaling + retention + archiving — gates Arc 2 Phase 1 SQL build); (e) OIR closures v2.10 → v2.16 retired ~14 prior gating items. Phase shape preserved (9 phases, 0–8); structural elements lifted verbatim (Cross-Cutting Concerns B1–B17, Architecture Pattern, Phase template, SP convention). Per-phase narratives rewritten from current source where FDS reframes hit; lifted with light touch-up where current. NEW section Seeding Registry — Phase Coupling maps S-01..S-11 to phases. Phase 0 expanded with the Architecture Decision track (OI-35 — 8 decisions). Phase 1 entry gated on both Phase 0 tracks; migration baked-in with the architectural decisions on day one. |

## Purpose

This document is the phased delivery plan for Arc 2 (Plant Floor MES) — the operator-facing portion of the MPP MES replacement. It is the sibling of MPP_MES_PHASED_PLAN_CONFIG_TOOL.docx (Arc 1), which is complete.

Arc 1 built the Configuration Tool: the engineering-facing surface where plant, items, routes, BOMs, quality specs, and reference vocabularies (shifts, downtime codes, defect codes) are authored. Arc 1 delivered across eight phases, with 13 versioned migrations (0001–0013), ~216 repeatable stored procedures, and 858/858 passing tests as of 2026-04-28.

Arc 2 builds the Plant Floor MES: the operator-facing surface that runs against Arc 1’s configured master data. Its audiences are shop-floor operators, supervisors, quality staff, and shipping staff, interacting through Ignition Perspective touch terminals, barcode scanners, and PLC-integrated production machinery. Arc 2 captures LOT lifecycle from die-cast origination through containerized shipment to Honda, with traceable genealogy at every step.

This plan has one explicit precondition: Phase 0 must complete before Phase 1 implementation begins. Phase 0 has two parallel tracks — an MPP-owned Customer Validation Gate that resolves design-time decisions whose wrong answer would force a phase rebuild, and a Blue Ridge–owned Architecture Decision Workshop (OI-35) that resolves long-horizon scaling decisions that must bake into the Phase 1 migration on day one.

## Architecture Pattern

Arc 1 used Ignition Named Queries calling stored procedures, with Perspective views as thin CRUD forms over the proc layer. Arc 2 builds on that architecture but adds two more layers, both first-class in this plan:

Ignition Gateway Scripts. Many plant-floor events originate outside Perspective sessions: PLC tags change, OmniServer scales publish values, timers tick at shift boundaries, and external systems (AIM, Zebra printers) expect direct calls. These live in Ignition Gateway scripts — long-running background scripts that watch OPC tags, poll queues, and issue HTTP/SOAP calls. Gateway scripts call stored procs for DB work; they never execute DML directly.

PLC/OPC Touchpoints. Plant-floor workflows tangle with assembly PLC handshakes (MIP), scales (OmniServer), and vision systems (Cognex). This plan describes PLC touchpoints functionally — what tag is read, what is written, what the handshake semantics are — but defers bit-level OPC addresses and register maps to reference/5GO_AP4_Automation_Touchpoint_Agreement.pdf and FRS Appendix C.

The three layers compose as:

Perspective View (touch UI)
       │         │
       │ (Named Query)           (Named Query)
       ▼         ▼                      ▼
  Stored Proc (SQL)   ◀─── calls ───  Gateway Script (Python)
                                          │        │
                                          ▼        ▼
                                     OPC/PLC   AIM / Zebra / etc.

Stored procs remain the authoritative write path — no Gateway script or Perspective binding performs DML directly. Every external I/O (AIM HTTP, Zebra socket write, OPC tag write-back) is bracketed with Audit.Audit_LogInterface calls so the external conversation is reconstructible forever.

## Cross-Cutting Concerns

Arc 1’s conventions carry forward unchanged and apply to every Arc 2 proc. They are not repeated here; see MPP_MES_PHASED_PLAN_CONFIG_TOOL.docx § Cross-Cutting Concerns. In summary: audit streams (ConfigLog, OperationLog, InterfaceLog, FailureLog), code-table-backed status everywhere, soft-delete via DeprecatedAt (never hard DELETE except where explicitly documented — BomLine, RouteStep), optimistic locking via @RowVersion on Update, SortOrder + _MoveUp/_MoveDown instead of drag-drop, BIGINT/NVARCHAR everywhere, single result set per proc (no OUTPUT parameters), RAISERROR in nested CATCH blocks (not THROW), user attribution via @AppUserId BIGINT.

Arc 2 adds the following seventeen conventions. These are normative for every phase of this plan.

### B1 — Operator session context binding

Every Arc 2 mutation proc accepts both @AppUserId BIGINT and @TerminalLocationId BIGINT as required parameters. Procs validate both exist and are active (AppUser not deprecated, Terminal Location not deprecated, Location of type Terminal). On any rejection, Audit.FailureLog captures both values along with the attempted parameters.

Session lifecycle (inactivity timeout, re-auth for high-security actions, logout) is enforced at the Ignition Perspective layer, not in procs. Procs treat every call as equally authoritative; Perspective is responsible for ensuring the caller is authenticated and the session has not expired.

### B2 — BlocksProduction interlock discipline

Any proc that advances a LOT through the process — Lot_MoveTo, ProductionEvent_Record, ConsumptionEvent_Record, Lot_Split, Lot_Merge, ContainerSerial_Add, Container_Create — first calls the shared guard Lots.Lot_AssertNotBlocked(@LotId). The guard reads Lot.LotStatusId → LotStatusCode.BlocksProduction. Any status with BlocksProduction=1 (Hold, Scrap, Closed) trips the guard. A tripped guard is a business rule violation, not an exception: the caller receives Status=0, Message='LOT MESL1710935 is in status Hold and cannot progress', the attempt is logged to FailureLog, and no partial writes occur.

The guard is delivered in Phase 1 (as part of the LOT core skeleton) and reused across all downstream phases.

### B3 — Open-event invariant

Oee.DowntimeEvent and Quality.HoldEvent both carry nullable EndedAt / ReleasedAt columns. The invariant: at most one open event per resource at any time. For DowntimeEvent, the resource is the machine Location; for HoldEvent, the resource is the Lot (or the optional NonConformance); for Lots.PauseEvent, the resource is the (LotId, LocationId) pair. _Start / _Place / _Pause procs enforce the invariant with an explicit pre-check:

IF EXISTS (SELECT 1 FROM Oee.DowntimeEvent
           WHERE LocationId = @LocationId AND EndedAt IS NULL)
BEGIN
    SET @Status = 0;
    SET @Message = CONCAT('Machine ', @LocationName, ' already has an open downtime event');
    -- log failure, return
END

Attempting a second open event is a business rule violation, not an exception. _End / _Release / _Resume procs reject if no open event exists.

### B4 — Gateway script layer contract

Gateway scripts call stored procs the same way Perspective views do — through parameterized Named Queries. Gateway scripts MUST NOT execute raw DML via system.db.runUpdateQuery or inline SQL. External I/O (AIM HTTP/SOAP, Zebra printer socket writes, OPC read/write via TOPServer or OmniServer) happens only in Gateway scripts; stored procs never reach outside the database.

Trigger pattern (FDS-01-014 / UJ-18 — Gateway-script-async): all external integrations are dispatched via system.util.sendMessage (fire-and-forget) or system.util.sendRequestAsync (when the caller needs error surfacing — print path, AIM Hold/Update). The Perspective view (or the MES proc, when proc-driven) fires the message; a Gateway-scoped message handler performs the external call. Sync direct-call from inside an MES proc is retired for external systems — sync remains the model for inter-MES DB calls only. The async dispatch decouples MES correctness from external availability and makes failures observable, retryable, and logged without operator-blocking. Note: system.util.sendMessageAsync is not a real Ignition API — pick sendMessage vs sendRequestAsync per caller need.

Audit trail. Every external call is bracketed by Audit.Audit_LogInterface writes — one when the request fires (Direction=‘Outbound’, RequestPayload populated, ResponsePayload NULL), one when the response or error returns (update the same row). Critical failures additionally log to Audit.FailureLog. The OI-01 “no outbox” decision still stands — there is no separate outbox table; the message-handler pattern delivers async semantics without a DB queue.

Special case — pre-fetched buffers. When zero operator-perceived latency is required (Container_Complete → AIM Shipper ID assignment per UJ-04), a pre-fetched local buffer (Lots.AimShipperIdPool, FDS-07-010) replaces the dispatch model: the MES proc consumes locally; the buffer’s topup loop runs as a Gateway-script-async. Empty pool = hard fail (FDS-07-010a — pending OI-33 customer validation).

Special case — print failure surfacing. Print attempts retry inline within the message handler (3 × 2s gap for shipping labels per FDS-07-006a). On exhaustion, DB state (PrintFailedAt, BannerAcknowledgedAt) drives a per-terminal banner via Gateway-broadcast-with-session-filter (FDS-07-006b) — one DB query per 5s regardless of terminal count; session-side filter is a cheap branch. A low-frequency safety-sweep timer (~5 min) recovers orphans (Gateway restart between proc commit and message dispatch) and alarms on stranded-prints count > 5.

### B5 — PLC descriptive boundary

Phase narratives describe what Gateway scripts read from and write to PLC tags in prose: tag names (e.g., PartSN, PartValid, DataReady, HardwareInterlockEnable, CycleComplete, OperationComplete, CompletionConfirmed, TrayFullFlag), semantics (edge-triggered vs. level-triggered), and handshake steps. Bit-level OPC addresses, data types, register numbers, and PLC ladder logic stay out of this plan. They live in reference/5GO_AP4_Automation_Touchpoint_Agreement.pdf and FRS Appendix C. Gateway script implementation references those documents; the plan references them by path.

### B6 — Print job contract

ZPL generation for labels (LTT, shipping label, master label) is assembled in Gateway scripts from a template file plus data returned by the originating stored proc. The stored proc (LotLabel_Print, ShippingLabel_Print, etc.) writes the audit row with the full rendered ZplContent and returns its Id; the Gateway script reads the Id, dispatches the ZPL content to the physical Zebra printer (via socket), and records the print acknowledgement back on the same row (not via a second insert). Void labels use IsVoid=1 + VoidedAt + VoidedByUserId; rows are never deleted.

### B7 — Late-binding reason codes

Oee.DowntimeEvent.DowntimeReasonCodeId is nullable. When a PLC detects a machine stop before an operator classifies it, DowntimeEvent_Start inserts the row with NULL reason. DowntimeEvent_End succeeds with a NULL reason. Unclassified downtime is flagged on the shift-supervisor dashboard and on shift-end reporting — it is not blocked at proc level. A separate DowntimeReasonCode_Assign proc fills the reason later; it refuses to overwrite an already-assigned reason (supervisors must correct by other means).

### B8 — Genealogy traversal

Lots.Lot_GetGenealogyTree(@LotId, @Direction) uses a recursive CTE with OPTION (MAXRECURSION 100). The @Direction parameter takes 'Ancestors' (walk ParentLot → ParentLot → …) or 'Descendants' (walk children via LotGenealogy). Tree depth beyond 100 hops is a business rule violation with the message genealogy tree exceeds supported depth of 100. Real plant genealogy never approaches this bound; the cap is a defensive recursion guard. Note (OI-35 / Phase 0 architecture): if the architecture review elects to add a materialized closure table, this CTE traversal becomes a fallback and the closure table is the canonical query path — see Phase 1 Data Model Changes for the conditional schema.

### B9 — Test pattern extension for open-state events

Arc 1’s test pattern covered mutations with a temp-table capture of the result shape (Status / Message / NewId). Arc 2 extends this for open-state events: after _Start / _Place / _Pause, tests assert EndedAt IS NULL (or ReleasedAt IS NULL / ResumedAt IS NULL) directly against the underlying table:

DECLARE @OpenCount INT;
SELECT @OpenCount = COUNT(*)
FROM Oee.DowntimeEvent
WHERE LocationId = @LocationId AND EndedAt IS NULL;
IF @OpenCount <> 1
    RAISERROR('Expected exactly 1 open DowntimeEvent, got %d', 16, 1, @OpenCount);

After _End / _Release / _Resume, tests assert the same row’s terminal column IS NOT NULL.

### B10 — Serial number migration audit

UJ-05 default direction (committed 2026-04-27): update-in-place + new Lots.ContainerSerialHistory table capturing each migration event. Awaits MPP Quality + Honda compliance affirmation before final lock; if MPP rejects update-in-place, the convention reverts to void-and-recreate with no history table. Schema delivers in Phase 7 alongside the rest of the Sort Cage workflow. Until UJ-05 closes definitively, Phase 7 builds against the default direction with the procs structured so a void-and-recreate flip can swap in without a migration rebuild.

### B11 — Zone-based default screen routing

On Perspective session startup, the client IP resolves to a Terminal-type Location row by querying its existing IpAddress LocationAttribute. The Terminal’s zone (parent Area in the Location hierarchy) plus a DefaultScreen LocationAttributeDefinition on the Terminal LocationTypeDefinition drives the initial Perspective view shown to any operator who logs in at that station.

A Trim Shop terminal opens to the Trim Station Screen; a Shipping Dock terminal opens to the Shipping Screen; a Die Cast terminal opens to the Die Cast LOT Entry Screen. Operator presence (initials) is orthogonal — the default-screen lookup happens on session start, before any initials entry or per-action elevation.

The DefaultScreen attribute is seeded as a new LocationAttributeDefinition row on the Terminal LocationTypeDefinition (via migration or via the existing Arc 1 Config Tool). Phase 1 delivers Location.Terminal_GetByIpAddress and the Terminal_ResolveFromSession Gateway script that stashes Zone + DefaultScreen in session props for the Home router view to consume.

### B12 — Purpose-built top-level views, polymorphic embedded components

Top-level views are purpose-built per workflow. No generic dashboard-configuration engine. One view per terminal function (Die Cast LOT Entry, Trim Station, Machining IN, Sort Cage Workflow, Shipping Dock, Hold Management, etc.); B11 routing picks by Terminal Location. LocationAttribute is for business policies only, never UI configuration. Flexware’s *DashboardConfiguration family (LotTrackingDashboardConfiguration, LotCreateDashboardConfiguration, WorkOrderDashboardConfiguration, FinalAssemblyDashboardConfiguration, CreateAllocationDashboardConfiguration, SortDashboardConfiguration, MaterialLabelPrintDashboardConfiguration, WorkstationDashboardConfiguration) is NOT reproduced. If two top-level views need different populate behavior, they are different views — not a configurable flag.

Polymorphism lives at the embedded-component level — Flex Repeater + Embedded View is the canonical pattern. Anywhere a view needs to handle N similar items (1 ≤ N ≤ many), the result set is bound to a Flex Repeater whose embedded view is the polymorphic unit. Examples: a destination picker repeater that renders N pickers when a machined LOT splits into N sub-LOTs at Machining OUT — same UI, same submit handler, count driven by the result set. Other natural Flex Repeater + Embedded View patterns: LOT history rows on the LOT Detail view, ancestor/descendant cards on the Genealogy Viewer, hold-row cards on Hold Management, container cards on the Sort Cage workflow, paused-LOT detail rows on the Paused-LOT indicator’s tap-through list.

Naturally-parametric top-level views. Some top-level views are inherently polymorphic by data-binding rather than by Flex Repeater composition: LOT Detail (one view, takes @LotId, conditionally renders Tool/Cavity rows when populated), LOT Search (one view, filter-driven), Genealogy Viewer (one view, takes @LotId). These do not get per-station variants. There is no “Die Cast LOT Detail” or “Trim LOT Detail” or “Machining LOT Detail” — there is one LOT Detail that adapts to whatever the LOT carries.

Cross-cutting embedded components (used across phases without modification): Per-Mutation Initials Field, Elevation Modal (per-action AD), Paused-LOT Indicator + tap-through detail list, Movement Scan, Cell Context Selector (Shared terminals), Confirmation Method Resolver (reads ConfirmationMethod LocationAttribute → renders Vision / Barcode / Both UX). These are inventoried per phase but their implementations live once and are reused.

### B13 — Tool/Cavity system of record

Tool and Cavity live on Lots.Lot (ToolId, ToolCavityId FKs, Data Model v1.9). They are never duplicated on Workorder.ProductionEvent, Workorder.ConsumptionEvent, or any derived LOT created via consumption / sub-LOT split. Honda-trace queries walk Lots.LotGenealogy (or the OI-35 closure table, if Phase 0 architecture review elects it) to the origin LOT and read Tool/Cavity from there. Downstream (Trim, Machining, Assembly) LOTs carry ToolId = NULL and ToolCavityId = NULL.

### B14 — Checkpoint-shape events

Workorder.ProductionEvent is a checkpoint table — each row carries cumulative ShotCount / ScrapCount as-of-the-checkpoint. Deltas are derived by readers via LAG() over (LotId, EventAt). No per-event GoodCount / NoGoodCount. No StartedAt / EndedAt. No LocationId / ItemId / DieIdentifier / CavityNumber (all derivable from Lot.ToolId / Lot.ToolCavityId + LotMovement + Lot.ItemId). A missed checkpoint doesn’t compound errors — the next event carries truth.

### B15 — Identifier minting via IdentifierSequence_Next

All MPP-internal identifier minting (LOT LTT barcodes, SerializedItem IDs, future non-AIM counters) goes through Lots.IdentifierSequence_Next @Code. No ad-hoc identifier generation anywhere. The Lots.IdentifierSequence table seeds at cutover from Flexware live counter values (S-10 in the Seeding Registry; OI-31 for the format-carry-forward + reset-policy questions). AIM Shipper IDs are a separate concern (Honda-issued via AIM.GetNextNumber, pooled locally per UJ-04).

Note (OI-35 / Phase 0 architecture): the implementation is row-locked-update by default; if Phase 0 architecture review elects SQL Server SEQUENCE object instead, the proc wraps the sequence with a format-string function and the underlying mechanism changes — Phase 1 honors the decided approach.

### B16 — Lazy LOT creation

LOT creation is operator-driven, not auto-triggered at any prescribed moment. Lots.Lot_Create fires whenever the operator decides — basket-full, before starting the next LOT, etc. The MES does not auto-create N LOTs at run start. Phase 3 UI and procs must not require a Lot row to exist for an in-progress cavity; physical-but-unlogged baskets are normal. Tool + Cavity assignment happens at Lot_Create time (FDS-05-034 / FDS-05-036).

### B17 — Gateway-script-async external integrations (FDS-01-014, UJ-18)

All MES outbound calls to external systems (AIM, Zebra printers, Honda EDI, future Macola pushes) use the Gateway-script-async pattern. Perspective views fire system.util.sendMessage or system.util.sendRequestAsync to a Gateway-scoped message handler with the relevant entity ID(s) as payload; the handler performs the external call. Failures retry inline within the handler (e.g., 3 attempts × 2s gap for shipping labels per FDS-07-006a) and ultimately write Audit.FailureLog if exhausted. Operator-facing failure surfaces (per-terminal banners, wallboard alarms) bind to DB state — not in-flight handler state — so Gateway restarts don’t lose visibility. Sync direct-call from inside MES procs is retired for external systems; sync remains for inter-MES DB calls. Pre-fetched buffers (Lots.AimShipperIdPool per UJ-04) are the special case where zero operator-perceived latency is required.

## Stored Procedure Template and Conventions

Arc 2 procs follow the same template, error hierarchy, audit placement rules, and code-review checklist defined in MPP_MES_PHASED_PLAN_CONFIG_TOOL.docx § Stored Procedure Template and Conventions. The template is reproduced in full there; it is not duplicated here. Cited fresh reminders:

- Three-tier error hierarchy (parameter validation → business rule → unexpected exception)

- SET NOCOUNT ON; SET XACT_ABORT ON; at top of every mutation proc

- Parameter validation and business-rule checks before BEGIN TRANSACTION; only the mutation wrapped in transaction

- Success audit call (Audit.Audit_LogOperation for Arc 2 plant-floor procs) inside the transaction, before COMMIT

- Failure audit call (Audit.Audit_LogFailure) outside transactions, in a nested TRY/CATCH around the failure-log insert so a failed audit-write cannot interfere with the primary rollback

- Final SELECT @Status AS Status, @Message AS Message[, @NewId AS NewId]; on every exit path (no OUTPUT parameters — FDS-11-011)

- RAISERROR not THROW in nested CATCH blocks

- All DB references schema-qualified (Lots.Lot, Audit.Audit_LogOperation)

One Arc 2 divergence: the primary audit sink for mutation procs is Audit.OperationLog (via Audit.Audit_LogOperation), not Audit.ConfigLog (via Audit.Audit_LogConfigChange). This is the core distinction between the two arcs. Config Tool mutations describe engineering-authored rules; Plant Floor mutations describe operator-observed events. The two audit streams are read by different supervisory queries.

Note (OI-35 / Phase 0 architecture): if the architecture review elects to split OperationLog into a 7-year retention general audit and a separate 20-year Lots.LotEventLog for traceability events, Arc 2 procs use Lots.LotEventLog for LOT-event mutations and Audit.OperationLog for everything else. The proc layer abstracts the destination; callers don’t change.

## Seeding Registry — Phase Coupling

The Seeding Registry (MPP_MES_SEEDING_REGISTRY.docx v1.0) tracks 11 external-data items (S-01 through S-11) sourced from MPP IT, MPP Quality, MPP Engineering, Honda, and vendors. These are deployment-time data dependencies, not build blockers — the schema CREATEs in the appropriate phase regardless of seed-data delivery status. Only S-08 (DieRankCompatibility) is a true blocker, and it carries a supervisor-override workaround so Phase 2 can ship without it. The table below maps each S-item to the phase that consumes it.

| ID | Item | Owner | Phase | Status (2026-04-29) | Notes |
| --- | --- | --- | --- | --- | --- |
| S-01 | Plant equipment master (Machines, ~209 rows) | MPP Engineering | Phase 1 (Location seed) | 🟡 Received — needs DC/MS/TS→Area mapping | CSV at reference/seed_data/machines.csv; loaded into Location.Location rows via Phase 1 dev-seed once mapping locks. |
| S-02 | Downtime reason codes (~353 rows) | MPP Engineering | Phase 8 (Oee.DowntimeReasonCode bulk load) | 🟡 Received — needs DC/MS/TS→Area mapping | Bulk-load proc Oee.DowntimeReasonCode_BulkLoadFromSeed shipped Phase 8 of Arc 1; awaits MPP-confirmed Area mapping to invoke against the 353-row CSV. |
| S-03 | Defect codes (~153 rows) | MPP Quality | Phase 6 (Quality.DefectCode), Phase 8 (per-Area filtering) | 🟡 Received — needs Area mapping | CSV at reference/seed_data/defect_codes.csv. |
| S-04 | OPC tag catalog (~161 rows) | MPP Engineering | Phase 6 + Phase 7 (PLC integration design) | 🟡 Received — endpoint validation pending | CSV at reference/seed_data/opc_tags.csv; informs Gateway script tag bindings. |
| S-05 | Parts master list | MPP IT | Phase 1 (Parts.Item bulk load) | ⬜ Owed | Format TBD; bulk-load proc skeleton lands in Phase 1 once MPP confirms export shape. |
| S-06 | Flexware BOM export (formerly OI-13) | MPP IT | Phase 4 + Phase 6 (Parts.Bom + BomLine seed) | ⬜ Owed | One-shot pull at cutover; refreshed at deployment. |
| S-07 | Die rank list | MPP Quality | Phase 1 (Tools.DieRank code table) | ⬜ Owed | Empty seed ships in Phase G; populated from MPP Quality input before Phase 2 merge tests run. |
| S-08 | Die rank compatibility matrix | MPP Quality | Phase 2 (Tools.DieRankCompatibility — gates Lot_Merge cross-die rules) | ⬜ Owed — TRUE BLOCKER (with override) | Empty seed; merge proc rejects cross-die merges until populated, supervisor override unblocks edge cases per FDS-04-007 (so the build is not gated, just the operational path). |
| S-09 | Label-type seed validation | MPP Shipping | Phase 6 (LotLabel) + Phase 7 (ShippingLabel) | ⬜ Owed | Phase 0 walkthrough confirms the Flexware 3-template inventory (CONTAINER / LOT / CONTAINER_HOLD) plus any additions (Sort Cage, Hold, Void). |
| S-10 | Identifier sequence baselines | MPP IT | Phase 1 (Lots.IdentifierSequence cutover seed) | ⬜ Owed (cutover-only) | Two counters: Lot (MESL{0:D7}, ~1,710,932 baseline) and SerializedItem (MESI{0:D7}, ~2,492 baseline). Sampled values drift; final values pulled at cutover day. Couples to OI-31 (format carry-forward + rollover policy questions, gated in Phase 0). |
| S-11 | AIM pool config tuning | MPP post-deploy | Phase 7 (Lots.AimPoolConfig) | 🟡 Defaults seeded | TargetBufferDepth=50, TopupThreshold=30, AlarmWarningDepth=20, AlarmCriticalDepth=10. Configuration Tool surfaces these for tuning post-deploy. |

Status legend: ⬜ Owed | 🟡 Received (needs prep / mapping) | ✅ Loaded (Dev) | 🔵 Verified (Cutover).

Per-phase narratives reference these S-items where relevant; this table is the canonical index. Updates flow into the Seeding Registry first, then into this table at the next plan revision.

## Phase Map and Dependencies

Phase 0 (Customer Validation Gate + Architecture Decision Workshop — parallel tracks)
    │
    ▼
Phase 1 (Foundation) ──────────────────────────────────▶ Phase 8 (Downtime + Shift)  [parallel]
    │
    ▼
Phase 2 (LOT lifecycle)
    │
    ▼
Phase 3 (Die Cast) ───────────────────────────┐
    │                                          │
    ├──────────────▶ Phase 4 (Move + Trim + Rx — whole-LOT move out)
    │                          │               │
    │                          ▼               │
    │                    Phase 5 (Machining: FIFO Pick + Rename + Sub-LOT Split / PLC Auto-Complete at OUT)
    │                          │               │
    │                          ▼               │
    │                    Phase 6 (Assembly + MIP + Container Pack — tray-level closure)
    │                          │               │
    │                          ▼               │
    └──────────────▶    Phase 7 (Hold + Sort Cage + Shipping + AIM)

Direct dependency table:

| Phase | Directly depends on | Unblocks |
| --- | --- | --- |
| 0 | — | 1 |
| 1 | 0 (both tracks) | 2, 8 |
| 2 | 1 | 3 |
| 3 | 1, 2 | 4, 7 |
| 4 | 1, 2, 3 | 5 |
| 5 | 1, 2, 3, 4 | 6 |
| 6 | 1, 2, 3, 4, 5 | 7 |
| 7 | 1, 2, 3, 6 | — |
| 8 | 1 | — (parallel track) |

Phase 8 runs in parallel to Phases 2–7 as soon as Phase 1 lands. Phase 4 and Phase 5 can no longer parallelize — Phase 5 consumes the whole LOTs that Phase 4’s Trim OUT deposits into the Machining FIFO queue (the sub-LOT split itself is now internal to Phase 5, at Machining OUT). A small team can still parallelize by running 8 alongside 2 + 3.

Note on Phase 0 parallel tracks. The Customer Validation Gate (MPP-owned) and the Architecture Decision Workshop (Blue Ridge–owned) are independent — they MAY run on different days with different stakeholders. Both must complete before Phase 1 commences. Customer validation outputs feed Phase 1’s seed data and column lists; architecture decisions feed Phase 1’s migration shape (partition functions, closure tables, etc.).

# Phase 0 — Customer Validation Gate + Architecture Decision Workshop

Goal: Resolve two classes of decisions whose wrong answer would force a phase rebuild in Arc 2: (a) MPP-owned design choices about workflow, retention, label scope, and rollout shape; (b) Blue Ridge–owned architectural decisions about long-horizon scaling, retention, and archiving (OI-35) that must bake into the Phase 1 migration on day one.

Dependencies: None. Phase 0 blocks Phase 1 implementation but can run in parallel with Arc 1 post-delivery work.

Status: Unblocked. Both tracks require stakeholder availability — MPP for the customer validation track, Blue Ridge architecture + MPP IT for the OI-35 track (MPP IT participates only in the retention-policy negotiation; the rest is Blue Ridge–internal).

## Two Parallel Tracks

### Track A — Customer Validation Gate (MPP-owned)

This is the workshop with MPP stakeholders (operations, quality, IT, production-control) where each gating item is walked, discussed, and decided. Items below are must resolve before Phase 1 — wrong answer rebuilds a phase.

| # | Item | Question | Why it gates | OIR ref |
| --- | --- | --- | --- | --- |
| A1 | OI-31 Identifier sequence cutover | Final cutover seed values + format carry-forward (keep MESL/MESI, or mint new?). Reset policy. Rollover policy at 9,999,999. Plus Ben’s rollout-shape decision (single-line vs full-cutover vs shadow — memo at Meeting_Notes/2026-04-24_OI-31_Single-Line_Deployment_Impact.md). Couples to S-10 in the Seeding Registry. | Phase 1 migration seeds LastValue; wrong seed = LTT collisions with live Flexware LOTs at cutover. | OI-31 |
| A2 | FDS-06-030 WorkOrder BIT-flag enumeration | Which Flexware WorkOrder flags are live (IsCameraProcessingEnabled, IsScaleProcessingEnabled, GroupTargetWeight + tolerance + UOM, RecipeNumber, TrayQuantity, ReturnableDunnageCode, Customer)? | Phase 1 Workorder.WorkOrder CREATE column list. Dead flags don’t ship. | FDS-06-030 |
| A3 | Historical data migration | Cutover approach — which entities migrate (LOTs, SerializedItems, ProductionOrders, Containers, Genealogy). Discrepancy review for unmatched rows (e.g., Flexware LotAttribute.DIE NAME with no matching Tools.Tool.Code). | Phase 1 migration-script + pre-flight validation design. | — |
| A4 | ShotCount semantics | Workorder.ProductionEvent.ShotCount = cumulative counter (current default) OR derived from aggregated LOT quantities? | Phase 3 operator-screen design + reporting path. Default until decided: keep cumulative column, mark provisional. | — |
| A5 | Workstation DefaultScreen + ConfirmationMethod seeding | Per-Cell list of terminal-function Perspective views + per-Cell ConfirmationMethod value (Vision / Barcode / Both). | Phase 1 seed data for B11 routing + UJ-17 / FDS-10-013. | — |
| A6 | Honda AIM Hold/Update contract detail | PlaceOnHold / ReleaseFromHold / UpdateAim signatures + error recovery expectations. UJ-04 GetNextNumber pool flow already locked; this covers the remaining AIM operations. | Phase 7 shipping Gateway scripts (Hold + Sort Cage re-pack paths). | UJ-04 (closed); remaining AIM ops |
| A7 | Label template scope | Flexware has 3 templates (CONTAINER / LOT / CONTAINER_HOLD). Confirm matches + any new (Sort Cage, Hold, Void). Print pattern itself is locked (UJ-18 Gateway-script-async); only template inventory is open. | Phase 6 / 7 label print procs + ZPL templates. Couples to S-09 in the Seeding Registry. | — |
| A8 | OI-32 Material Allocation operator screen | Premise challenged by Jacques in OIR v2.10 review; Blue Ridge clarification queued for confirmation. Awaits a separate Materials-Allocation walkthrough with MPP. | Phase 6 Assembly material flow. | OI-32 |
| A9 | OI-33 AIM pool empty-pool hard-fail customer validation | Customer affirmation that hard-fail is the desired posture when the pool is exhausted (production stops on affected lines until pool refills; no soft-fallback or placeholder-then-reconcile). Per FDS-07-010a — current design is hard-fail. | Phase 7 Container_Complete semantics + operational expectations. | OI-33 |

### Track B — Architecture Decision Workshop (Blue Ridge–owned, with MPP IT for retention)

This is the architecture review captured by OI-35 in the OIR (HIGH severity, “MUST DECIDE BEFORE ARC 2 PHASE 1 SQL BUILD”). Items 1, 3, 6, 8 are softer (post-CREATE configurable) but cleaner to lock in upfront; items 2, 4, 5, 7 must be in the CREATE migration because retrofitting them against populated 100M+ row tables is operationally expensive. Full context: Meeting_Notes/2026-04-28_DataModel_Indexing_Scaling_Review.md.

| # | Decision | Owner | Hard-gate reason |
| --- | --- | --- | --- |
| B1 | Per-table retention class. Negotiate which tables genuinely need 20 years vs which can carry 7-year retention. Push-back candidates: Audit.OperationLog, Audit.FailureLog, Audit.InterfaceLog, Oee.DowntimeEvent, Audit.ConfigLog. Honda traceability data (Lots.* events, ContainerSerial, ShippingLabel, LotGenealogy) almost certainly stays at 20 years. | Blue Ridge + MPP IT | Drives FDS-11 retention-policy amendment + which tables need partitioning. |
| B2 | Partitioning scheme. Native SQL Server 2022 range partitioning, monthly partitions, sliding-window automation. Applies to ~14 deferred high-volume event tables. Partition column is CreatedAt / EventAt / LoggedAt per table. | Blue Ridge | Partition function + scheme go in the CREATE migration. Partitioning a populated 100M-row table later requires rebuild + log-volume blow-up. |
| B3 | Columnstore on aged partitions. Convert partitions older than ~90 days from rowstore to clustered columnstore. Expected 8–15× compression on event-shape data. | Blue Ridge | Partition-aging job + maintenance plan. Configurable post-CREATE. |
| B4 | Lots.LotGenealogy materialized closure table. Pre-compute every ancestor-descendant pair at LOT creation time (AncestorLotId, DescendantLotId, Depth). Honda audit becomes O(1) lookup vs O(depth) recursion. | Blue Ridge | Closure table CREATEs alongside LotGenealogy. Backfilling 50M+ ancestor pairs from a recursive walk after 5 years of operation is expensive. |
| B5 | Materialize TotalInProcess / InventoryAvailable columns onto Lots.Lot. OI-23 chose the view-based path (Lots.v_LotDerivedQuantities); at scale the view aggregates over 200M+ event rows per query. If materialize, do it in the same Lot_Create / event-write procs that already touch the Lot row. | Blue Ridge | If materialized, columns and update paths land in CREATE migration. View stays as fallback for diagnostics. |
| B6 | Lots.IdentifierSequence_Next locking model. Single-row hot table; ~150K LOTs/year creates row-lock contention. Two paths: (a) explicit WITH (ROWLOCK, UPDLOCK) with serializable transaction (current implicit pattern); (b) replace with SQL Server SEQUENCE object + format-string wrapper. | Blue Ridge | Affects IdentifierSequence_Next proc shape + table presence. Configurable but cleaner upfront. |
| B7 | Split Audit.OperationLog. Today every mutating proc writes here. Keep OperationLog for 7-year general audit; add a separate Lots.LotEventLog for traceability subset (LOT events, container close events, ShippingLabel mints) at 20-year retention. | Blue Ridge + MPP IT | If split, the new table CREATEs in the Phase 1 migration and the Audit_LogOperation shared proc routes by entity type. Retroactive split requires data migration. |
| B8 | Filtered indexes on hot subsets. Systematic per-table pass: every “active subset” query (WHERE LotStatusCodeId IN (active codes), WHERE ResumedAt IS NULL, WHERE ConsumedAt IS NULL, WHERE PrintFailedAt IS NOT NULL AND BannerAcknowledgedAt IS NULL) gets a filtered index 0.1–1% the size of the full table. | Blue Ridge | Index list for each Phase 1 CREATE; configurable post-CREATE but cleaner upfront. |

## Data Model Changes

None directly — Phase 0 produces decisions, not DDL. Any DDL deltas flowing from Phase 0 decisions are captured in the Phase 1 migration.

## Open Items Affecting This Phase

This phase is the open items phase. The two tracks above enumerate the must-resolve items. Lower-priority items handled opportunistically:

| Item | Status | Fallback if unresolved at Phase 0 |
| --- | --- | --- |
| UJ-19 Productivity DB replacement & 4 PD reports | ⬜ Open | MPP names the four PD reports + their data sources for MES reporting subsystem replication. Couples to OI-30 Reports tile. |
| UJ-05 Sort Cage serial migration | ⬜ Open | Update-in-place + Lots.ContainerSerialHistory is the schema-supportable default. Awaits MPP Quality + Honda compliance affirmation. |
| UJ-03 Sublot split trigger | 🔶 In Review | Auto-prompt 50/50 even split (Option A) is current default per FDS-05-009; Ben confirms whether all parts split or only some. |
| OI-24..30 discovery items | ⬜ Open | Automation tile, Notifications, Supply part flag, cast-override cell flag, Workstation Category, Reports enumeration — handled in their respective phase walkthroughs if MPP brings input. |
| OI-34 Production schedule leverage | ⬜ Open | Current minimal use (shift-window timing only) is sufficient; expanded use (target quotas per shift, drift detection, etc.) drops into post-Phase-9 enrichment. |

Already closed items that previously appeared on the Phase 0 list:

- OI-01 Event outbox; OI-02 weight-based closure; OI-03 shift runtime; OI-04 vision-conflict; OI-05 merge rules; OI-06 / UJ-01 operator identity; OI-07 WorkOrderType; OI-08 terminal mode; OI-09 / UJ-15 cavity-parallel LOTs; OI-10 tool life (superseded); OI-11 Casting→Trim (superseded by Trim→Machining); OI-12 MaxParts; OI-13 BOM export (now S-06); OI-14, -15, -16, -17, -18, -19, -20, -21, -22, -23, -32b; UJ-02, -04, -06, -07, -08, -09, -10, -11, -12, -13, -14, -15, -16, -17, -18.

See MPP_MES_Open_Issues_Register.docx v2.16 for full status and decision history.

## State & Workflow

Phase 0 has two parallel tracks. The MPP-owned track is a facilitated workshop, not a technical build. The Blue Ridge–owned track is an architecture review session.

### Track A — Customer Validation Gate workflow

- Pre-work. Blue Ridge drafts a facilitator deck summarizing each gating item: the question, candidate answers, design implication of each, Blue Ridge’s recommended default. Distributed to MPP 3 business days before workshop.

- Workshop. 2–3 hour session with MPP stakeholders. Each gating item is walked, discussed, and decided. Opportunistic items covered if time permits.

- Decision log capture. Decisions appended to MPP_MES_Open_Issues_Register.docx with signed-off dates. Each decision references its OI/UJ number.

- Schema delta capture. Any DDL additions (new columns, new attribute-definition rows, new code-table entries) documented and folded into the Phase 1 migration file.

### Track B — Architecture Decision Workshop workflow

- Pre-work. Blue Ridge architecture lead drafts a decision deck covering items B1–B8. For B1 (retention policy), the deck includes a per-table proposed retention class for MPP IT review.

- Internal session (B2, B3, B4, B5, B6, B7, B8). Blue Ridge architecture review covers items 2–8 — these are technical decisions that don’t require MPP input. ~2 hours.

- MPP IT session (B1). Single-meeting deliverable on per-table retention policy. ~1 hour. Output: signed-off retention class per table.

- Architecture-decision log. All 8 decisions captured in a new section of the Data Model spec (§ “Scaling Decisions”) at the next data model bump (likely v1.10). Drives Phase 1 migration content.

- FDS-11 amendment. FDS § 11 (Audit) gains a per-table retention paragraph at the next FDS bump.

## API Layer (Named Queries → Stored Procedures)

None — no code deliverables in Phase 0.

## Gateway Scripts

None.

## Perspective Views

None.

## Test Coverage

No test suite additions.

## Phase 0 complete when

- Track A: Workshop held with MPP representatives. Decision log for items A1–A9 appended to Open Issues Register with signed-off dates.

- Track B: Architecture decisions B1–B8 finalized. Data Model § “Scaling Decisions” added (data model bump). FDS-11 retention paragraph drafted (FDS bump).

- B10 convention (serial migration audit) rewritten with the chosen UJ-05 pattern (default direction: update-in-place + Lots.ContainerSerialHistory; awaits MPP Quality + Honda affirmation).

- Any DDL deltas (Track A column lists, Track B partitioning + closure table + materialization columns + filtered indexes) captured in the Arc 2 Phase 1 migration draft. Migration numbering: versioned migrations 0001–0013 are landed (Arc 1 complete + 0013 OI-07/OI-12 corrections). Arc 2 Phase 1 lands at 0014_arc2_phase1_shop_floor_foundation.sql.

- Opportunistic items resolved or explicitly deferred with a documented fallback (UJ-19 PD reports, UJ-05 Sort Cage serial migration, UJ-03 sublot trigger, OI-24..30 discovery items, OI-34 production schedule leverage).

# Phase 1 — Shop Floor Foundation

Goal: Deliver the cross-cutting infrastructure that every downstream Arc 2 phase depends on — operator session, terminal binding, IP-based zone routing, shift runtime, LOT core skeleton, identifier sequence, and the shared operation-log audit contract — with the OI-35 architectural decisions baked into the migration on day one.

Dependencies: Phase 0 complete (both tracks). Arc 1 SQL complete (all tables referenced exist, Audit procs operational).

Status: Blocked on Phase 0.

## Data Model Changes

Migration sql/migrations/versioned/0014_arc2_phase1_shop_floor_foundation.sql (next unclaimed number — Arc 1 consumed 0001–0013).

The Phase 1 migration carries two distinct concerns simultaneously: the new tables required by the operator-facing surface, and the OI-35 architectural decisions resolved in Phase 0. This is intentional — partitioning, closure tables, materialization, and filtered indexes are all cheaper to land at CREATE time than retrofit. The actual contents of the migration depend on Phase 0 outputs; the descriptions below assume the Phase 0 default decisions (with each variant called out).

New tables (Arc 2 — introduced here, per Data Model v1.9l):

- Workorder.WorkOrder — CREATE with the v1.9l column contract: Id, WoNumber, WorkOrderTypeId (FK → Workorder.WorkOrderType; defaults to the single-seeded Production row per OI-07), ItemId, RouteTemplateId, WorkOrderStatusId, ToolId (FK → Tools.Tool, NULL — schema hook for FUTURE Maintenance WOs, unpopulated in MVP), CreatedAt, CompletedAt. Plus the FDS-06-030 Phase-0-confirmed BIT-flag columns (live flags only, per A2 decision).

- Workorder.WorkOrderOperation — CREATE per Data Model §4. AppUserId BIGINT NULL FK → AppUser.Id.

- Workorder.ProductionEvent — CREATE per Data Model v1.9l checkpoint shape: Id, LotId, OperationTemplateId, WorkOrderOperationId (NULL), EventAt, ShotCount (NULL, cumulative), ScrapCount (NULL, cumulative), ScrapSourceId (NULL FK → Workorder.ScrapSource), WeightValue, WeightUomId, AppUserId BIGINT NOT NULL FK → AppUser.Id, TerminalLocationId, Remarks. Required index (LotId, EventAt DESC). No LocationId, no ItemId, no DieIdentifier, no CavityNumber, no GoodCount / NoGoodCount, no StartedAt / EndedAt.

- Workorder.ProductionEventValue — CREATE per Data Model §4 (child of ProductionEvent, extensible DataCollectionField capture).

- Workorder.ConsumptionEvent — CREATE per Data Model §4. AppUserId BIGINT NOT NULL FK → AppUser.Id.

- Workorder.RejectEvent — CREATE per Data Model §4. AppUserId BIGINT NOT NULL FK → AppUser.Id.

- Lots.IdentifierSequence — CREATE per Data Model §3 (OI-31). Seed Lot (MESL{0:D7}) + SerializedItem (MESI{0:D7}) rows with LastValue set from the cutover-day Flexware snapshot (S-10, Phase 0 Track A delivers the values). Implementation depends on Phase 0 Track B / B6: if SEQUENCE object elected, IdentifierSequence_Next wraps a SEQUENCE per code; if row-locked-update elected, the proc uses UPDATE ... WITH (ROWLOCK, UPDLOCK).

OI-35 architectural additions (per Phase 0 Track B outputs):

- Partition functions + schemes for the high-volume event tables: Workorder.ProductionEvent, Workorder.ConsumptionEvent, Workorder.RejectEvent, Lots.LotMovement, Lots.LotStatusHistory, Lots.LotAttributeChange, Lots.LotGenealogy, Lots.ContainerSerial, Audit.OperationLog, Audit.InterfaceLog, Audit.FailureLog, Oee.DowntimeEvent, Quality.HoldEvent. Range partitioned on CreatedAt / EventAt / LoggedAt per table. Monthly boundaries; sliding-window maintenance lands in a Phase 1 Gateway timer.

- Materialized closure table for Lots.LotGenealogy (if Phase 0 elected B4): Lots.LotGenealogyClosure (AncestorLotId BIGINT, DescendantLotId BIGINT, Depth INT, CONSTRAINT PK_LotGenealogyClosure PRIMARY KEY (AncestorLotId, DescendantLotId)). Indexed on both directions. Lot_Create and Lot_Split / Lot_Merge write closure rows transactionally alongside the genealogy edge.

- Materialized derived-quantity columns on Lots.Lot (if Phase 0 elected B5): TotalInProcess INT NOT NULL DEFAULT 0, InventoryAvailable INT NOT NULL DEFAULT 0. Updated by ProductionEvent_Record / ConsumptionEvent_Record inside the same transaction. The Lots.v_LotDerivedQuantities view stays as a diagnostic fallback.

- Split Audit.OperationLog (if Phase 0 elected B7): new Lots.LotEventLog table created with the same row shape as OperationLog plus LotId BIGINT NOT NULL FK → Lots.Lot.Id. The shared Audit_LogOperation proc routes by entity type — LOT events to LotEventLog, everything else to OperationLog. Retention class differs (20-year vs 7-year).

- Filtered indexes on hot subsets (per B8): see per-table indexes in the corresponding phase migrations.

ALTERs (Arc 2 Phase 1):

- Lots.Lot ADD ToolId BIGINT NULL FK → Tools.Tool(Id) and ToolCavityId BIGINT NULL FK → Tools.ToolCavity(Id). Required at Lot_Create for die-cast-origin LOTs; NULL elsewhere; NULL after Lot_Merge.

LocationAttributeDefinition seeds on the Terminal LocationTypeDefinition:

- DefaultScreen (NVARCHAR — Perspective route path, e.g., '/shop-floor/die-cast-entry').

- RequiresCompletionConfirm (BIT — per OI-16) — when set on a Dedicated Terminal, the auto-finish completion flow shows a large “Confirm Completion” button instead of a passive popup. NULL = 0 = passive popup.

- No TerminalMode seed — terminal mode is derived from the Terminal Location’s parent ISA-95 tier per OI-08 (Cell-parent → Dedicated; WorkCenter- or Area-parent → Shared).

LocationAttributeDefinition seeds on Cell-tier LocationTypeDefinitions:

- ConfirmationMethod (NVARCHAR — 'Vision' / 'Barcode' / 'Both') on relevant Cell types (e.g., AssemblyStation, SerializedAssemblyLine) — per FDS-10-013 / UJ-17. Read by the production proc and operator UI; drives the FDS-06-010 / FDS-10-003 part-identity check. The exact list of receiving Cell types comes from Phase 0 A5.

- CoupledDownstreamCellLocationId (Integer / Location.Location.Id reference) on CNCMachine — per FDS-06-008. When non-NULL on a Machining Cell, Machining OUT auto-moves the LOT to the referenced Cell. NULL = legacy uncoupled path.

What is NOT seeded (per Phase C security rewrite):

- No IdleTimeoutSeconds attribute — there is no shift-start login to time out. Operator presence is persistent on Dedicated terminals; Shared terminals prompt on first action or machine change. The 30-minute idle re-confirmation overlay on Dedicated terminals is Perspective-layer behaviour, not a DB attribute.

- No RequiresReauthForSensitive attribute — elevation is per-action AD prompt (FDS-04-007) for every elevated action, everywhere. No per-terminal opt-out.

Other migration tasks:

- Add Location.Location.IpAddress-attribute-index if missing (read-heavy lookup in Terminal_GetByIpAddress).

- Seed a fallback Terminal Location row representing the global default (used when an unregistered IP connects).

Tables used (existing from Arc 1 / Phase G):

| Table | Role |
| --- | --- |
| Location.Location | Terminal location lookup by IP |
| Location.LocationAttribute | IpAddress, DefaultScreen, ConfirmationMethod, CoupledDownstreamCellLocationId values per Location |
| Location.LocationAttributeDefinition | Definitions of Terminal + Cell-tier attributes |
| Location.AppUser | Initials-based operator presence resolver; interactive users carry AD account |
| Tools.Tool, Tools.ToolCavity, Tools.ToolAssignment | System of record for Tool identity; Lot.ToolId / Lot.ToolCavityId FK to these |
| Oee.ShiftSchedule | Active-shift resolver input |
| Oee.Shift | Runtime shift instances (append-only) |
| Lots.Lot | LOT header — minimal CRUD in this phase (Phase 2 expands) |
| Lots.LotStatusHistory | Append on status change |
| Lots.LotMovement | Append on move |
| Lots.LotStatusCode | BlocksProduction flag source |
| Audit.OperationLog | Destination for general audit (or LotEventLog for LOT events if B7 elected) |
| Audit.FailureLog | Destination for rejected calls |

## Open Items Affecting This Phase

| Item | Assumption used |
| --- | --- |
| OI-31 identifier sequences | Pending Phase 0 Track A — cutover-day LastValue for Lot + SerializedItem; format carry-forward confirmed; locking model from Phase 0 Track B / B6. |
| OI-35 architectural decisions | Pending Phase 0 Track B — drives the migration shape. Default decisions assumed for the migration draft; final migration written after Phase 0. |
| FDS-06-030 WorkOrder BIT flags | Pending Phase 0 Track A — live flag column list on Workorder.WorkOrder CREATE. |
| Historical data migration | Pending Phase 0 Track A — entity list, pre-flight validation, discrepancy review process. |
| OI-06 / UJ-01 operator identity | ✅ Closed (Phase C). Initials-based presence + per-action AD elevation. Phase 1 delivers AppUser_GetByInitials. |
| UJ-10 shift boundary | ✅ Closed (Option D). Events span boundaries naturally per OI-03 — Shift_End does NOT auto-close open DowntimeEvent rows; the open-event invariant per B3 carries through the boundary. |
| UJ-17 vision vs barcode | ✅ Closed (Option A). ConfirmationMethod LocationAttribute on Cell-tier types per FDS-10-013. |
| OI-16 / RequiresCompletionConfirm | ✅ Closed. Per-Terminal BIT LocationAttribute. |
| OI-08 terminal mode | ✅ Closed. Mode derived from parent Location tier — Engineering attaches Terminals at the right place in the hierarchy. No seeded attribute. |
| UJ-18 Gateway-script-async | ✅ Closed. B4 + B17 codify the pattern. AIM pool topup is the canonical example; Phase 1 doesn’t directly use it (no external integrations until Phase 6/7), but Gateway-script-async is the foundation pattern for everything downstream. |

## State & Workflow

### Session establishment (terminal startup)

An Ignition Perspective session starts when a Perspective client connects to the Gateway. The Gateway invokes the Terminal_ResolveFromSession script with the client’s IP.

- Gateway calls Location.Terminal_GetByIpAddress(@IpAddress = '10.12.7.34').

- Proc queries Location.LocationAttribute for AttributeName = 'IpAddress' AND Value = @IpAddress, joins to the parent Location row (which must be LocationType = 'Terminal'), and returns:

  - TerminalLocationId (the Terminal Location’s Id)

  - TerminalName (Location.Name — e.g., 'DC-TERM-05')

  - ZoneLocationId + ZoneName (the Terminal’s parent Area — e.g., 'Die Cast')

  - DefaultScreen (from LocationAttribute, e.g., '/shop-floor/die-cast-entry')

  - TerminalMode — derived from the Terminal Location’s parent tier: Dedicated if parent is a Cell, Shared if parent is a WorkCenter or Area. No stored attribute.

- If no Terminal matches the IP, proc returns the fallback Terminal’s attributes. The Gateway script flags the session as “unregistered terminal” and routes to a generic Terminal Selector screen.

- Gateway stashes these values in Perspective session props: session.custom.terminal.*.

- Perspective’s Home router view reads session.custom.terminal.defaultScreen and navigates to that path.

No DB mutation during session establishment. No audit log — this is a read-only lookup.

### Operator presence (initials-based — per Phase C / FDS §4)

There is no login, no clock number, no PIN. Operators are identified on a terminal by their initials, which establish a persistent operator presence context that pre-populates a defeasible Initials field on every mutation screen.

Dedicated terminals (parented to a Cell — typically the lower-volume single-machine workstations):

- The operator scans or types their initials (e.g., XX) on the shift-start handoff screen or on first touch after the machine sits idle.

- Perspective calls Location.AppUser_GetByInitials @Initials='XX'.

- Proc returns the AppUser row (Id, Initials, DisplayName, UserClass). Empty result set = initials unknown — Perspective shows an inline error (“Initials XX not recognised — ask Admin to add this operator in the Configuration Tool”) and does not proceed.

- On success, Perspective stashes session.custom.user.* with {appUserId, initials, displayName, userClass}. Presence persists through the shift.

- 30-minute idle re-confirmation. A Perspective view-side timer resets on every interaction. At 30 minutes idle, the next touch shows a modal: “Operate as XX? Yes / No — change.” On Yes, presence continues. On No — change, Perspective clears the session’s initials and the operator scans/types fresh initials. The timer is a Perspective concern — no DB state.

Shared terminals (parented to a WorkCenter or Area — typically the higher-volume multi-machine areas like Die Cast or Assembly):

- Presence is prompted on first action and on every Cell-context change. The Initials field at the top of every mutation screen is never pre-populated.

- Operator enters initials inline on the screen being submitted. Each mutation carries its own @AppUserId resolved by AppUser_GetByInitials at submit time.

- No persistent session.custom.user.* on shared terminals — every action is standalone.

Cell-context selection (Shared terminals only — per FDS-02-009 / FDS-02-011): The terminal’s active Cell context is selectable by scan or dropdown. Selection is the first step of every interaction; it persists across the session until the operator changes it (again by scan or dropdown). Dedicated terminals have no Cell-context selector — context is fixed to the terminal’s parent Cell.

Pre-populated defeasible Initials field: Every mutation screen shows an Initials field pre-populated from session.custom.user.initials (Dedicated) or empty (Shared). Operator can override before submit — e.g., when a pair-working colleague enters data on behalf of the primary operator. The value at submit time is what stamps the event.

### Elevated actions (per FDS-04-007)

Elevated actions (place hold, release hold, scrap LOT, void shipping label, Tool mount / release, admin remove-item, override a BOM-driven destination, supervisor merge override, BOM-substitute material override) require a per-action Active Directory authentication. On invocation:

- Perspective shows the AD credential modal (AD username + password, integrated auth where available).

- Perspective calls Location.AppUser_AuthenticateAd @AdAccount='jdoe', @Password='...' (proc delegates to Ignition’s AD binding; returns the matching AppUser.Id + role list; NULL if invalid or role not permitted).

- On success, the elevated action proceeds with the authenticated user’s @AppUserId — this value stamps the mutation; the original operator-presence @AppUserId stays for non-elevated events. The elevation does NOT open a sticky session — next elevated action re-prompts.

- Every elevation attempt (success and failure) writes to Audit.OperationLog with LogEventType='ElevationGranted' or Audit.FailureLog with LogEventType='ElevationDenied'.

No “re-auth” flag on Terminal, no 5-minute-window session stickiness, no PIN fallback. Elevation is always per-action.

### Shift runtime

Shift boundaries are driven by a Gateway script tick (ShiftBoundaryTicker, runs every 60 seconds):

- Ticker calls Oee.Shift_GetActive(@LocationId, @NowUtc).

- Proc looks up Oee.ShiftSchedule rows active on today’s day-of-week (per DaysOfWeekBitmask) with EffectiveFrom <= @NowUtc and DeprecatedAt IS NULL. Returns the one matching the current time-of-day window.

- Ticker also calls Oee.Shift_GetOpen(@ShiftScheduleId) to see if there’s an open Shift row for this schedule.

- If the active schedule has no open Shift row, ticker calls Oee.Shift_Start(@ShiftScheduleId, @ActualStart = @NowUtc). Proc inserts the Shift row, logs OperationLog.

- If the previously-active schedule has an open Shift row but the active schedule is different (i.e., boundary crossed), ticker calls Oee.Shift_End(@ShiftId, @ActualEnd = @NowUtc) on the outgoing Shift. Proc updates the row, logs OperationLog.

- No auto-carryover of open events. Per UJ-10 (Option D, closed): open Oee.DowntimeEvent rows remain open across the shift boundary; the incoming operator closes them when the machine resumes (FDS-09-010). Same for open Lots.PauseEvent rows.

### LOT core skeleton

Phase 1 delivers minimal LOT procs — enough to let Phase 3 (Die Cast) create its first LOT. Full LOT lifecycle (Lot_Update, Lot_UpdateAttribute, genealogy) is Phase 2.

Lot_Create flow (narrated from Phase 3’s perspective — the proc is delivered here). Aligned to Data Model v1.9l + FDS-05-034 / FDS-05-035:

- Operator takes a basket from a machine’s active cavity and scans a fresh pre-printed LTT barcode at the terminal. Perspective builds the parameter set: @LotName = NULL (proc mints via IdentifierSequence_Next @Code='Lot'), @ItemId, @LotOriginTypeId, @CurrentLocationId (Cell), @PieceCount, @ToolId (NULL for non-die-cast origins; required for Die Cast — Perspective auto-populates from ToolAssignment_ListActiveByCell and operator confirms), @ToolCavityId (same rule), @Weight, @WeightUomId, @VendorLotNumber (Received only), @AppUserId, @TerminalLocationId.

- Proc validates parameters (no NULLs on required, FKs resolve).

- Proc validates business rules:

  - @Item eligible at @CurrentLocationId via Parts.v_EffectiveItemLocation (Direct ∪ BomDerived per FDS-02-012).

  - Piece count within Parts.Item.MaxLotSize (semantic PartsPerBasket).

  - If @LotOriginTypeCode = 'Manufactured' and the Cell has an active Tools.ToolAssignment (die-cast-origin check):

    - @ToolId and @ToolCavityId are required (per FDS-05-034).

    - Tools.ToolAssignment exists for @ToolId on @CurrentLocationId with ReleasedAt IS NULL.

    - @ToolCavityId belongs to @ToolId.

    - ToolCavity.StatusCode = 'Active'.

  - Non-die-cast origins (Received, Trim/Machining intermediate, Assembly, Serialized) SHALL pass NULL Tool/Cavity — proc does not require them.

- BEGIN TRANSACTION.

- Proc calls Lots.IdentifierSequence_Next @Code='Lot' which atomically increments LastValue (or invokes the SEQUENCE per B6) and returns the formatted string (e.g., MESL1710935). This is @MintedLotName.

- Proc inserts Lots.Lot row with LotName = @MintedLotName, LotStatusId = 'Good', ToolId, ToolCavityId. Returns new Id as @NewId.

- Proc inserts Lots.LotStatusHistory row: OldStatusId = NULL, NewStatusId = 'Good', ChangedByUserId = @AppUserId, TerminalLocationId = @TerminalLocationId.

- If B4 elected: Proc inserts Lots.LotGenealogyClosure self-row (AncestorLotId = @NewId, DescendantLotId = @NewId, Depth = 0) to seed the closure for this LOT.

- If B5 elected: TotalInProcess and InventoryAvailable initialize to 0 / @PieceCount respectively (no event yet; LOT is at its origin Cell).

- Proc calls Audit.Audit_LogOperation (or LotEventLog_LogEvent if B7 elected) with LogEntityTypeCode='Lot', LogEventTypeCode='LotCreated', EntityId=@NewId, Description='Created LOT <LotName> at <LocationName>' (plus Tool/Cavity in description for die-cast-origin LOTs).

- COMMIT.

- Final SELECT @Status, @Message, @NewId, @MintedLotName.

If any validation fails, no transaction opens, Audit.Audit_LogFailure is called with the attempted parameters (Tool/Cavity included), and the proc returns early. Note: IdentifierSequence_Next is invoked inside the transaction so a rolled-back LOT doesn’t burn a counter value (when B6 elected SEQUENCE, the sequence value IS burned regardless of rollback — accepted tradeoff for concurrency).

### Lot_AssertNotBlocked shared guard

Procedure called by every downstream proc that advances a LOT. Reads Lot.LotStatusId → LotStatusCode.BlocksProduction. Returns IsBlocked BIT, Message NVARCHAR(500). Internal — no audit, no FailureLog; callers that receive IsBlocked=1 log their own rejection via FailureLog and return early. Delivered in Phase 1; reused everywhere downstream per B2.

## API Layer (Named Queries → Stored Procedures)

### Location — Terminal resolution

| Procedure | Parameters | Notes | Dependencies | Executed When | Output |
| --- | --- | --- | --- | --- | --- |
| Location.Terminal_GetByIpAddress | @IpAddress NVARCHAR(45) | Reads LocationAttribute where AttributeName='IpAddress'; joins to parent Terminal Location and its parent Area. Computes TerminalMode from parent tier. Returns fallback Terminal if no match. Falls back gracefully, never errors on unknown IP. | Location.Location, Location.LocationAttribute, Location.LocationType, Location.LocationTypeDefinition | Perspective session start, via Gateway script | Single row: TerminalLocationId, TerminalName, ZoneLocationId, ZoneName, DefaultScreen, TerminalMode |
| Location.Terminal_List | (none) | Admin query — all Terminal-type Locations with attributes. Used by an admin screen (not operator-facing). | Location.Location, Location.LocationAttribute | Admin browsing Terminal inventory | Rowset per Terminal |

### AppUser — initials-based presence + AD elevation

| Procedure | Parameters | Notes | Dependencies | Executed When | Output |
| --- | --- | --- | --- | --- | --- |
| Location.AppUser_GetByInitials | @Initials NVARCHAR(10) | Resolves initials to an active AppUser row. Empty result set = unknown initials. No audit on lookup (initials-presence is not a security event). Used by Perspective on shift-start (Dedicated terminals) and on every Shared-terminal mutation. | Location.AppUser | Shift-start handoff; shared-terminal submit; 30-min idle re-confirm | Single row: Id, Initials, DisplayName, UserClass, IgnitionRole (or empty set if unknown). |
| Location.AppUser_AuthenticateAd | @AdAccount NVARCHAR(100), @TerminalLocationId BIGINT, @ActionCode NVARCHAR(50) | Elevation proc. Delegates the credential check to Ignition’s AD binding (the Perspective modal submits @AdAccount + password; if Ignition validates, it calls this proc with @AdAccount only). Proc looks up the matching AppUser.AdAccount, verifies the user is not deprecated, verifies IgnitionRole matches the role permitted for @ActionCode, and returns the AppUserId. On any reject, writes Audit.FailureLog with LogEventType='ElevationDenied'. On success, writes Audit.OperationLog with LogEventType='ElevationGranted'. | Location.AppUser, Audit.Audit_LogOperation, Audit.Audit_LogFailure | Every elevated action per FDS-04-007 | Single row: Status BIT, Message NVARCHAR(500), AppUserId BIGINT (NULL on failure). |
| Location.AppUser_GetRoles | @AppUserId BIGINT | Returns the IgnitionRole for interactive users; empty result for operator-class users. Used by Perspective to gate elevated-screen visibility. | Location.AppUser | On elevation success | Rowset of role strings. |

Explicitly NOT delivered: clock# + PIN authentication procs. Phase G migration 0011_drop_appuser_legacy_auth.sql already dropped AppUser.ClockNumber and AppUser.PinHash columns. Any Phase 3+ proc that references those columns is a bug.

### Shift — runtime instances

| Procedure | Parameters | Notes | Dependencies | Executed When | Output |
| --- | --- | --- | --- | --- | --- |
| Oee.Shift_Start | @ShiftScheduleId BIGINT, @ActualStart DATETIME2(3), @Remarks NVARCHAR(500) NULL, @AppUserId BIGINT, @TerminalLocationId BIGINT | Inserts a new Oee.Shift row. Rejects if an open Shift (ActualEnd NULL) already exists for this ShiftSchedule (per B3). | Oee.Shift, Oee.ShiftSchedule, Audit.Audit_LogOperation | Gateway ShiftBoundaryTicker | Status, Message, NewId |
| Oee.Shift_End | @ShiftId BIGINT, @ActualEnd DATETIME2(3), @Remarks NVARCHAR(500) NULL, @AppUserId BIGINT, @TerminalLocationId BIGINT | Closes the Shift: updates ActualEnd. Rejects if ActualEnd already set. No auto-carryover logic — open events stay open per UJ-10 / FDS-09-010. | Oee.Shift, Audit.Audit_LogOperation | Gateway ShiftBoundaryTicker or manual override | Status, Message |
| Oee.Shift_GetActive | @LocationId BIGINT NULL, @NowUtc DATETIME2(3) = SYSDATETIME() | Returns the schedule active at @NowUtc matching the day-of-week bitmask. Does not create a Shift row. | Oee.ShiftSchedule | Gateway ShiftBoundaryTicker; supervisor dashboard | Single row or empty |
| Oee.Shift_GetOpen | @ShiftScheduleId BIGINT | Returns the open Shift (if any) for this schedule. Used by the ticker to detect whether a Shift_Start is needed. | Oee.Shift | Gateway ShiftBoundaryTicker | Single row or empty |

### Lot — core skeleton (minimal; Phase 2 expands)

| Procedure | Parameters | Notes | Dependencies | Executed When | Output |
| --- | --- | --- | --- | --- | --- |
| Lots.Lot_Create | @ItemId, @LotOriginTypeId, @CurrentLocationId, @PieceCount, @Weight, @WeightUomId, @ToolId, @ToolCavityId, @VendorLotNumber, @MinSerialNumber, @MaxSerialNumber, @AppUserId, @TerminalLocationId | Creates a Lot with status ‘Good’. Mints LotName via IdentifierSequence_Next @Code='Lot' inside the transaction. Validates Item eligibility via v_EffectiveItemLocation, piece count ≤ Parts.Item.MaxLotSize (PartsPerBasket). Validates Tool/Cavity per FDS-05-034 for die-cast-origin. Inserts initial LotStatusHistory row. If B4 elected: inserts self-row in LotGenealogyClosure. Audit via Audit.Audit_LogOperation (or LotEventLog_LogEvent if B7). | Lots.Lot, Lots.LotStatusHistory, Lots.IdentifierSequence, Lots.LotGenealogyClosure (if B4), Parts.Item, Parts.v_EffectiveItemLocation, Tools.Tool, Tools.ToolCavity, Tools.ToolAssignment, Lots.LotOriginType, Lots.LotStatusCode, Audit.Audit_LogOperation | Phase 3+ station produces a new LOT | Status, Message, NewId, MintedLotName NVARCHAR(50) |
| Lots.IdentifierSequence_Next | @Code NVARCHAR(30) | Atomically returns the next formatted identifier string. Implementation per Phase 0 B6 decision (row-locked update OR SEQUENCE wrapper). Raises on unknown @Code or rollover breach. | Lots.IdentifierSequence (or sequence object) | Any identifier minting path | Single row: Value NVARCHAR(50). |
| Lots.Lot_Get | @LotId BIGINT NULL, @LotName NVARCHAR(50) NULL | Returns the Lot row. If B5 elected: the materialized columns TotalInProcess and InventoryAvailable are returned directly. If B5 not elected: view-joined to v_LotDerivedQuantities at read time. Empty result set = not found. | Lots.Lot, optionally Lots.v_LotDerivedQuantities | Any screen displaying a LOT | Single row of Lot columns + derived quantities |
| Lots.Lot_List | @ItemId NULL, @CurrentLocationId NULL, @LotStatusId NULL, @LimitRows INT = 100 | Filterable listing. Read-only, no audit. Same view-vs-materialized rule as Lot_Get. | Lots.Lot | LOT search screen | Rowset of Lot columns |
| Lots.Lot_UpdateStatus | @LotId, @NewLotStatusId, @Reason, @AppUserId, @TerminalLocationId, @RowVersion ROWVERSION | Updates Lot.LotStatusId with optimistic-lock check. Inserts LotStatusHistory row. Rejects no-op (new = current). Phase 1 only accepts Good → Closed transitions; Phase 2 expands. | Lots.Lot, Lots.LotStatusHistory, Lots.LotStatusCode, Audit.Audit_LogOperation | Phase 2+ for general transitions; Phase 7 for holds | Status, Message |
| Lots.Lot_MoveTo | @LotId, @ToLocationId, @AppUserId, @TerminalLocationId | Updates Lot.CurrentLocationId and inserts LotMovement row with FromLocationId = prior, ToLocationId = new. Calls Lot_AssertNotBlocked first (per B2). | Lots.Lot, Lots.LotMovement, Lots.Lot_AssertNotBlocked, Audit.Audit_LogOperation | Any station that receives a scanned LOT | Status, Message |
| Lots.Lot_AssertNotBlocked | @LotId BIGINT | Internal shared guard. Returns IsBlocked BIT, Message NVARCHAR(500). No audit. Called by every advancing proc (B2). | Lots.Lot, Lots.LotStatusCode | Every mutation that advances a LOT | Single row |

### Audit — shared operation logger

| Procedure | Parameters | Notes | Dependencies | Executed When | Output |
| --- | --- | --- | --- | --- | --- |
| Audit.Audit_LogOperation | @AppUserId, @TerminalLocationId, @LocationId NULL, @LogSeverityCode = 'Info', @LogEventTypeCode, @LogEntityTypeCode, @EntityId, @Description, @OldValue NULL, @NewValue NULL | Inserts into Audit.OperationLog. If B7 elected: routes LOT-event entity types to Lots.LotEventLog instead. Resolves code strings to FK ids internally. Returns no result set (audit writers silent). | Audit.OperationLog, optionally Lots.LotEventLog | Every Arc 2 mutation proc | (none) |

## Gateway Scripts

| Script | Purpose | Trigger | External System | Audit |
| --- | --- | --- | --- | --- |
| Terminal_ResolveFromSession | On Perspective session start, read client IP, call Terminal_GetByIpAddress, stash Terminal / Zone / DefaultScreen / TerminalMode into session.custom.terminal.*. If unregistered IP, fall back to global-default Terminal and flag the session. | Perspective session startup event | — | — (read-only) |
| PresenceIdleWatcher (Perspective view-side, not Gateway) | Dedicated terminals only. Per-view 30-minute idle detector resets on any interaction. At timeout, shows the “Operate as [XY]? Yes / No — change” modal. On No — change, clears session.custom.user.* and routes to initials entry. | Perspective interaction events | — | — |
| ShiftBoundaryTicker | Every 60 seconds: for each configured schedule, resolve active schedule, detect boundary crossings, call Shift_End on outgoing + Shift_Start on incoming. No auto-carryover — open events stay open per UJ-10. | Gateway timer (60s) | — | OperationLog on Shift_Start / Shift_End |
| PartitionMaintenance (if Phase 0 B2 elected partitioning) | Daily — creates next month’s partition + ages oldest partition into archive boundary. Switches partitions older than 90 days to columnstore (B3). | Gateway timer (24h) | — | OperationLog on each partition switch |

Removed: AdAuthenticator Gateway script is not needed — AD credential validation is delegated to Ignition’s built-in AD binding (invoked by the Perspective elevation modal), with AppUser_AuthenticateAd performing only the post-validation role check + audit write.

## Perspective Views

| View | Purpose |
| --- | --- |
| Initials Entry (Dedicated terminals) | Shift-start handoff and 30-minute re-confirm modal. Operator scans or types initials. Submits AppUser_GetByInitials; inline error on unknown. Sets session.custom.user.* on success. No password, no PIN. |
| Terminal Selector | Shown only for unregistered-IP sessions. Operator selects terminal from a list or scans a terminal barcode. Updates session.custom.terminal.* from a manual selection proc. |
| Cell Context Selector (Shared terminals) | Per FDS-02-009/-011 — operator selects active Cell context by scan or dropdown. Persists across the session until explicit change. Dedicated terminals do not show this view. |
| Home Router | Stateless: reads session.custom.terminal.defaultScreen and navigates. Falls back to a generic Home tile grid if DefaultScreen is NULL. |
| 30-Min Idle Re-Confirm Modal | Dedicated terminals only. “Operate as XX? Yes / No — change.” Yes continues presence; No — change clears and returns to Initials Entry. |
| Per-Mutation Initials Field | Every mutation screen shows a prominent Initials field, pre-populated from session.custom.user.initials on Dedicated terminals, empty on Shared. Operator can override before submit. |
| Elevation Modal (per-action AD) | Triggered by elevated actions per FDS-04-007. AD username + password inline; integrated auth via Ignition AD binding where available. On success, action proceeds with the elevated @AppUserId; no sticky session. Every attempt logged. |

## Test Coverage

New test suite at sql/tests/0014_PlantFloor_Foundation/ (next unclaimed test-suite number — Arc 1 consumed 0001–0019):

| File | Covers |
| --- | --- |
| 010_Terminal_GetByIpAddress.sql | Known IP resolves to correct Terminal + Zone + DefaultScreen + derived TerminalMode (Dedicated for Cell parent, Shared for WC/Area parent); unknown IP returns fallback; Terminal without DefaultScreen attribute returns NULL DefaultScreen; deprecated Terminal not returned. |
| 020_AppUser_GetByInitials.sql | Known initials return the AppUser row; unknown initials return empty result set; deprecated AppUser returns empty; mixed-class lookup (operator + interactive) covered. |
| 025_AppUser_AuthenticateAd.sql | Valid AD account + permitted role + valid action code returns AppUserId + OperationLog ‘ElevationGranted’; wrong role rejects with FailureLog ‘ElevationDenied’; deprecated AD user rejects; unknown @ActionCode rejects; missing @AdAccount rejects. |
| 030_Shift_lifecycle.sql | Shift_Start creates row; Shift_Start rejects when open Shift exists (B3); Shift_End closes row; Shift_End rejects when no open Shift; Shift_GetActive returns schedule by day-of-week bitmask. |
| 035_IdentifierSequence.sql | IdentifierSequence_Next returns correctly formatted strings for MESL{0:D7} and MESI{0:D7}; raises on unknown @Code; raises on rollover breach at EndingValue; concurrent callers see strictly-increasing values (per Phase 0 B6 chosen mechanism). |
| 040_Lot_Create.sql | Valid manufacture creates Lot + LotStatusHistory with Tool/Cavity set; minted LotName matches MESL{0:D7} format; die-cast-origin LOT without @ToolId rejects; die-cast-origin LOT with @ToolId not mounted on Cell rejects; cavity not belonging to tool rejects; cavity in Closed/Scrapped state rejects; non-die-cast-origin LOT with NULL Tool/Cavity accepted; ineligible Item-at-Location rejects (via v_EffectiveItemLocation Direct ∪ BomDerived); piece count over MaxLotSize rejects; missing @AppUserId rejects. |
| 045_LotGenealogyClosure_self.sql (if B4 elected) | Lot_Create inserts self-row in LotGenealogyClosure with Depth=0; concurrent creates don’t collide on the closure unique constraint; rolled-back Lot_Create does not leave a closure row. |
| 050_Lot_Get_List.sql | Lot_Get by Id and by LotName returns Tool/Cavity FKs + derived quantities (materialized or view per B5); empty result for non-existent; Lot_List filters work; limit applied. |
| 060_Lot_UpdateStatus.sql | Valid transition applies; stale @RowVersion rejects; no-op (same status) rejects; invalid target status rejects. |
| 070_Lot_MoveTo.sql | Valid move updates CurrentLocationId + inserts LotMovement; move from unblocked Lot succeeds; move from blocked Lot (Hold/Scrap/Closed) rejects via Lot_AssertNotBlocked. |
| 080_Lot_AssertNotBlocked.sql | Good returns IsBlocked=0; Hold/Scrap/Closed return IsBlocked=1 with correct Message; non-existent Lot returns IsBlocked=1 with ‘LOT not found’ message. |

Target: 80–105 passing tests in suite 0014 (up from v0.x target — adds closure-table tests + Tool/Cavity validation + IdentifierSequence + AD elevation).

## Phase 1 complete when

- Migration 0014_arc2_phase1_shop_floor_foundation.sql applied to dev. All Phase 1 CREATE / ALTER / seed delivered.

- OI-35 architectural decisions baked in per Phase 0 outputs — partition functions in place, closure table CREATEd (if B4), materialized columns added (if B5), OperationLog split (if B7), filtered indexes per B8.

- All repeatable procs present and up-to-date.

- No proc anywhere in the repo references AppUser.ClockNumber or AppUser.PinHash (both columns dropped by Phase G migration 0011). Grep verification: grep -ri 'ClockNumber\|PinHash' sql/ returns zero hits in active code.

- All tests in sql/tests/0014_PlantFloor_Foundation/ pass (target 80–105).

- Reset script (Reset-DevDatabase.ps1) discovers and applies the new migration and runs the new test suite.

- Gateway script Terminal_ResolveFromSession implemented and tested against Perspective sessions from known + unknown IPs.

- Gateway script ShiftBoundaryTicker implemented; verified end-to-end against a dev ShiftSchedule that crosses a boundary within the test window.

- Gateway script PartitionMaintenance implemented (if B2 elected); verified manually against a dev partition at a month boundary.

- Perspective views: Initials Entry, Terminal Selector, Cell Context Selector (Shared), Home Router, 30-Min Idle Re-Confirm Modal, Elevation Modal all built and routed correctly.

- Audit.Audit_LogOperation code-string → FK resolution verified for LogEventType values: 'ShiftStarted', 'ShiftEnded', 'LotCreated', 'LotStatusChanged', 'LotMoved', 'ElevationGranted'. Audit.Audit_LogFailure verified for 'ElevationDenied'. Any missing Audit.LogEventType rows seeded.

- Downstream phases can call Lot_Create (with Tool/Cavity FKs), IdentifierSequence_Next, AppUser_GetByInitials, AppUser_AuthenticateAd, Lot_MoveTo, Lot_UpdateStatus, and Lot_AssertNotBlocked against the delivered contract.

- End-to-end integration check: a dev operator scans initials at a dev Dedicated Terminal, presence persists, the operator creates a die-cast LOT (Tool auto-populated from active ToolAssignment, operator confirms, cavity selected), the LOT is minted with MESL{0:D7} name, a placeholder elevated action triggers the AD Elevation Modal and logs both OperationLog + FailureLog rows appropriately. Closure table row inserted (if B4). Materialized derived columns reflect zero in-process / full-piece-count available (if B5).

# Phase 2 — LOT Lifecycle Completion

Goal: Fill out the complete LOT surface — all mutation procs, append-only history streams, full genealogy (split / merge / consumption), pause lifecycle, derived quantity reads, and label reprint — so downstream operator-station phases compose from a stable LOT API.

Dependencies: Phase 1 (foundation). Most Lots schema tables already exist from Phase 1 migration.

Status: Blocked on Phase 1.

## Data Model Changes

Migration sql/migrations/versioned/0015_arc2_phase2_lot_lifecycle.sql (next unclaimed after Phase 1).

New tables:

- Lots.PauseEvent (OI-21 / FDS-05-038) — append-only place + close lifecycle for operator-driven LOT pauses at a workstation. Columns: Id BIGINT PK, LotId BIGINT NOT NULL FK → Lots.Lot.Id, LocationId BIGINT NOT NULL FK → Location.Location.Id (Cell-tier), PausedByUserId BIGINT NOT NULL FK → AppUser.Id, PausedAt DATETIME2(3) NOT NULL DEFAULT SYSUTCDATETIME(), PausedReason NVARCHAR(500) NULL, ResumedByUserId BIGINT NULL FK → AppUser.Id, ResumedAt DATETIME2(3) NULL, ResumedRemarks NVARCHAR(500) NULL. Constraints: CK_PauseEvent_ResumePaired pairing the resume cols; filtered UNIQUE UQ_PauseEvent_OpenLotLocation (LotId, LocationId) WHERE ResumedAt IS NULL. Filtered indexes: IX_PauseEvent_OpenByLocation (LocationId) WHERE ResumedAt IS NULL (Paused-LOT indicator counter) + IX_PauseEvent_Lot (LotId, PausedAt DESC) (per-LOT pause history). Audit.LogEntityType +1 row (PauseEvent).

New views (if Phase 0 B5 NOT elected — view stays as primary read path):

- Lots.v_LotDerivedQuantities (LotId, TotalInProcess, InventoryAvailable) (OI-23 / FDS-05-031) — joins Lots.Lot.PieceCount with aggregations over Workorder.ProductionEvent (cumulative checkpoint counters) and Workorder.ConsumptionEvent. Lot_Get and Lot_List JOIN this view at read time. If B5 elected, view remains as a diagnostic fallback; primary read path is the materialized columns on Lots.Lot.

Indexes: Phase 2 indexes any hot-read paths exposed by testing (e.g., Lots.LotGenealogy(ParentLotId) and Lots.LotGenealogy(ChildLotId) if not already covered by Phase 1 partition-aligned indexes).

Tables used:

| Table | Role |
| --- | --- |
| Lots.Lot | Header — expanded update surface |
| Lots.LotStatusHistory | Append on every Lot_UpdateStatus |
| Lots.LotMovement | Append on every Lot_MoveTo |
| Lots.LotAttributeChange | Append on every Lot_UpdateAttribute |
| Lots.LotGenealogy | Append on Split / Merge / Consumption |
| Lots.LotGenealogyClosure (if B4) | Maintained alongside LotGenealogy for O(1) ancestor walks |
| Lots.GenealogyRelationshipType | Code table — Split, Merge, Consumption |
| Lots.LotLabel | Append on every label print/reprint |
| Lots.PrintReasonCode | Code table |
| Lots.LabelTypeCode | Code table |
| Lots.PauseEvent | NEW — operator-driven LOT pause lifecycle |
| Tools.DieRankCompatibility | Read-only — Lot_Merge consults for cross-die merge approval (S-08) |

## Open Items Affecting This Phase

| Item | Status |
| --- | --- |
| UJ-08 merge rules | ✅ Closed (Option A). Proc-enforced rules per OI-05 / FDS-05-025..030: same ItemId, post-sort only, die-rank-compat from Tools.DieRankCompatibility (S-08), no Hold × Good mixing. Supervisor AD elevation per FDS-04-007 unblocks edge cases. S-08 die rank matrix is owed but not blocking — supervisor override is the escape hatch. |
| OI-21 Pausable LOT | ✅ Closed (design locked). PauseEvent CREATE + 4 procs delivered in this phase. |
| OI-23 Lot derived quantities | ✅ Closed (view) — but may flip to materialized columns per Phase 0 B5. Phase 2 honors the elected approach. |
| B10 serial migration | Pending Phase 0 (UJ-05 still in default state). Not relevant here — Phase 7 consumes this. Confirm B10 is finalized before Phase 7 starts. |

## State & Workflow

### Full Lot_Update

Lot_Update is distinct from Lot_UpdateStatus. It covers mutations to LOT header fields other than status — piece count correction, weight correction, vendor-lot-number correction for received LOTs. Each field change is captured as a separate LotAttributeChange row so the before/after audit is field-level.

- Perspective sends the full LOT payload with the operator’s intended new values.

- Proc validates optimistic lock via @RowVersion.

- Proc validates Lot_AssertNotBlocked (per B2 — even “corrections” on a held LOT are not allowed; release the hold first).

- Proc compares each mutable field. For each changed field, insert LotAttributeChange row with AttributeName, OldValue, NewValue, ChangedByUserId, TerminalLocationId, ChangedAt.

- Update the Lot row with the new values; UpdatedByUserId, UpdatedAt, RowVersion auto-updated.

- If B5 elected: if PieceCount changed, also recalculate InventoryAvailable accordingly.

- Audit via Audit_LogOperation with LogEventType='LotUpdated'.

### Genealogy — three shapes

Split. One parent LOT becomes multiple child LOTs. Lot_Split is consumed by Phase 5 (Machining OUT sub-LOT split) and Phase 7 (Sort Cage). Sequence:

- Parameter validation, Lot_AssertNotBlocked on the parent.

- Business rule: sum of child piece counts ≤ parent piece count.

- For each child spec: call Lot_Create (which transactionally seeds LotGenealogyClosure self-row if B4); insert LotGenealogy row (ParentLotId, ChildLotId, RelationshipType='Split', PieceCount = child's share, ...); if B4: insert closure rows (AncestorLotId, ChildLotId, Depth+1) for every existing ancestor of the parent plus the parent itself.

- Reduce parent piece count via Lot_UpdateAttribute. If residual is 0, Lot_UpdateStatus parent → Closed.

- Audit via Audit_LogOperation with LogEventType='LotSplit'.

Merge. Multiple source LOTs combine into one output. Per FDS-05-025..030 + UJ-08 (closed Option A): same ItemId, post-sort only, die-rank-compatibility from Tools.DieRankCompatibility (S-08), no Hold × Good mixing, supervisor AD override unblocks edge cases.

Lot_Merge sequence:

- Parameter validation: ≥2 source LOTs listed.

- Lot_AssertNotBlocked on each source.

- Business rules: same ItemId, all sources Good, die-rank-compatibility check (when sources have differing ToolId, look up DieRankCompatibility matrix; reject with clear message until matrix populated; supervisor override from FDS-04-007 always works as escape hatch).

- Create the merged output via Lot_Create with ToolId = NULL, ToolCavityId = NULL (blended-origin material can’t be denormalized — Tool-specific trace reconstructed via LotGenealogy walk of pre-merge sources per FDS-05-030).

- For each source: insert LotGenealogy row (ParentLotId = sourceId, ChildLotId = outputId, RelationshipType='Merge', ...); if B4: insert closure rows (AncestorLotId, outputId, ...) for every ancestor of every source. Lot_UpdateStatus source → Closed.

- Audit with LogEventType='LotMerged'.

- Return output Lot Id.

Consumption. One or more source LOTs are consumed to produce a child LOT or to fill a serialized part’s container. Handled by LotGenealogy_RecordConsumption (low-level) and invoked by Phase 5 Machining IN (BOM-driven rename) and Phase 6 Assembly (ConsumptionEvent_Record).

LotGenealogy_RecordConsumption is narrow: given a source LOT, a produced LOT or container tray position, and a piece count, insert the LotGenealogy row with RelationshipType='Consumption'; if B4: insert closure rows. Phases 5 + 6 wire this into their workflows with surrounding validation (BOM check, interlock bypass handling, container-tray placement).

### Genealogy traversal

Lot_GetGenealogyTree walks the graph. Two implementations possible per Phase 0 B4:

- If B4 NOT elected: Recursive CTE walking LotGenealogy. OPTION (MAXRECURSION 100). @Direction selects Ancestors / Descendants / Both.

- If B4 elected: Direct query against LotGenealogyClosure. O(1) per ancestor; no recursion. Same return shape as the CTE version. Honda audits at year 15 stay fast regardless of partition count.

### Label reprint

LotLabel_Reprint captures a new LotLabel row with a PrintReasonCode (label damaged, LOT attribute corrected, split generated a new child LTT, merge issued a new parent). The original LotLabel row is not modified — labels are append-only. Perspective’s reprint dialog forces a reason selection; the Gateway ZPL dispatcher renders and prints as with LotLabel_Print.

### LOT pause at workstation (OI-21 / FDS-05-038)

Pause is a (Lot, Location) lifecycle event recording an operator’s deliberate shift of focus away from a partially-progressed LOT at a Cell. The paused LOT remains in-process at the original Cell with its prior partial-start state intact (FDS-05-032); the operator MAY freely run other LOTs at that Cell while the pause is open.

Storage is Lots.PauseEvent — append-only place + close lifecycle (mirrors Quality.HoldEvent). Pause is orthogonal to Workorder.WorkOrderStatus, Workorder.OperationStatus, and Lots.LotStatusCode — no Paused row in any of those code tables. Pause does NOT write a Oee.DowntimeEvent.

Cross-location concurrency. The same LOT MAY be paused at multiple Cells simultaneously. Filtered UNIQUE on (LotId, LocationId) WHERE ResumedAt IS NULL enforces at most one open pause per (LotId, LocationId).

Operator UX — no auto-prompt. When an operator selects or scans a fresh LOT at a Cell that has a paused LOT open, the system SHALL NOT automatically prompt “resume paused LOT?” Instead, every workstation Perspective view binds to a Paused-LOT indicator that shows the current open-pause count for the operator’s Cell; tapping the indicator opens a list view (LotName, Part, PausedAt, PausedByUserId) backed by LotPause_GetByLocation @LocationId and lets the operator resume any LOT explicitly. Resume MAY be performed by a different operator from the one who paused.

No TTL. Paused LOTs SHALL NOT be auto-resumed or auto-cancelled. They MAY persist across shifts and operators.

### LOT derived quantities

The Lot Details header surfaces two derived quantities. Read path depends on Phase 0 B5:

- TotalInProcess — pieces at all non-terminal workstations (started but not yet completed out).

- InventoryAvailable — pieces still available for consumption or scrap.

If B5 elected: materialized columns on Lots.Lot, kept current by ProductionEvent_Record / ConsumptionEvent_Record writes. Lot_Get reads them directly.

If B5 NOT elected: view-backed via v_LotDerivedQuantities. Lot_Get JOINs the view at read time.

## API Layer (Named Queries → Stored Procedures)

### Lot — expanded mutations

| Procedure | Parameters | Notes | Output |
| --- | --- | --- | --- |
| Lots.Lot_Update | @LotId, @PieceCount NULL, @Weight NULL, @WeightUomId NULL, @VendorLotNumber NULL, @RowVersion ROWVERSION, @AppUserId, @TerminalLocationId | Full header update. Inserts one LotAttributeChange row per changed field. Rejects on stale @RowVersion. Lot_AssertNotBlocked. If B5: recalculates InventoryAvailable if PieceCount changed. | Status, Message |
| Lots.Lot_UpdateAttribute | @LotId, @AttributeName, @NewValue, @AppUserId, @TerminalLocationId | Single-field update helper. Used by Lot_Split to reduce parent piece count. | Status, Message |
| Lots.Lot_Split | @ParentLotId, @ChildrenJson (JSON array of {pieceCount, currentLocationId}), @AppUserId, @TerminalLocationId | Creates N child LOTs, inserts SPLIT genealogy rows + closure rows (B4), reduces parent piece count, closes parent if residual=0. Rejects if sum(children) > parent. Lot_AssertNotBlocked on parent. | Multi-row: header Status, Message; per-child ChildLotId, ChildLotName, PieceCount |
| Lots.Lot_Merge | @SourceLotIdsJson, @OutputItemId, @OutputLocationId, @AppUserId, @TerminalLocationId | Combines sources into one output. Proc-enforced rules per FDS-05-025..030. Closes all sources. | Status, Message, NewId |
| Lots.LotGenealogy_RecordConsumption | @SourceLotId, @ConsumedPieceCount, @ProducedLotId NULL, @ProducedContainerId NULL, @ProducedSerialNumber NULL, @AppUserId, @TerminalLocationId | Internal — inserts CONSUMPTION genealogy + closure rows. Called from Phase 5 Machining IN and Phase 6 Assembly. | Status, Message, NewId |

### Genealogy traversal

| Procedure | Parameters | Notes | Output |
| --- | --- | --- | --- |
| Lots.Lot_GetGenealogyTree | @LotId, @Direction NVARCHAR(20) = 'Both' | If B4: closure-table query. If not: recursive CTE with OPTION (MAXRECURSION 100). Same return shape either way. | Flat rowset with depth + relationship |
| Lots.Lot_GetParents | @LotId | One-hop up. | Rowset of parent Lots |
| Lots.Lot_GetChildren | @LotId | One-hop down. | Rowset of child Lots |
| Lots.Lot_GetAttributeHistory | @LotId | All LotAttributeChange + LotStatusHistory + LotMovement rows for a LOT, unioned and ordered by time. | Rowset of events |

### Labels

| Procedure | Parameters | Notes | Output |
| --- | --- | --- | --- |
| Lots.LotLabel_Print | @LotId, @LabelTypeCodeId, @PrintReasonCodeId, @AppUserId, @TerminalLocationId | Inserts LotLabel row with rendered ZPL. Called by initial create paths + reprint paths. | Status, Message, NewId, ZplContent NVARCHAR(MAX) |
| Lots.LotLabel_Reprint | @LotId, @PrintReasonCodeId, @AppUserId, @TerminalLocationId | Convenience wrapper — Initial=0. | Same shape as Print |

### LOT pause (OI-21)

| Procedure | Parameters | Notes | Output |
| --- | --- | --- | --- |
| Lots.LotPause_Place | @LotId, @LocationId, @PausedReason NVARCHAR(500) NULL, @AppUserId, @TerminalLocationId | Opens a pause. Rejects if open pause already exists for this (LotId, LocationId) per B3. Lot_AssertNotBlocked. | Status, Message, NewId |
| Lots.LotPause_Resume | @PauseEventId, @ResumedRemarks NVARCHAR(500) NULL, @AppUserId, @TerminalLocationId | Closes the pause. Rejects if already resumed. Resumer MAY be different from pauser. | Status, Message |
| Lots.LotPause_GetByLocation | @LocationId BIGINT | Returns all open pauses at a Cell — drives Paused-LOT indicator detail list. | Rowset: LotId, LotName, ItemId, ItemCode, PausedAt, PausedByUserId, PausedReason |
| Lots.LotPause_GetCountsByLocation | @LocationId BIGINT | Single integer — open-pause count for the Paused-LOT indicator badge. | Single row: OpenPauseCount INT |

## Gateway Scripts

None new in Phase 2 — all writes are operator-initiated through Perspective.

## Perspective Views

| View | Purpose |
| --- | --- |
| LOT Detail | Header + piece count + status + Tool/Cavity (Die Cast LOTs) + parents/children genealogy + history tab + paused-at list. Read-mostly; field edits via Lot_Update. |
| LOT Search | Filterable list of LOTs by Item, Location, Status. Calls Lot_List. |
| Genealogy Viewer | Visual tree from Lot_GetGenealogyTree. Closure-table-backed if B4. |
| Paused-LOT Indicator (cross-cutting) | Embedded on every workstation Perspective view. Shows open-pause count for the operator’s Cell; tap opens detail list. |

## Test Coverage

New test suite at sql/tests/0015_PlantFloor_Lot_Lifecycle/:

| File | Covers |
| --- | --- |
| 010_Lot_Update.sql | Field-level changes audit; row-version conflict; blocked-LOT rejection; B5 materialized recalculation. |
| 020_Lot_Split.sql | N-way split; sum-exceeds-parent rejection; closure rows inserted (B4); parent reduced/closed correctly. |
| 030_Lot_Merge.sql | Same-Item/same-Tool merge succeeds; cross-Tool with rank-compat=1 succeeds; cross-Tool with rank-compat=0 rejects; supervisor override path; merged LOT carries NULL Tool/ToolCavity. |
| 040_LotGenealogy_RecordConsumption.sql | Consumption genealogy + closure rows; multi-source consumption. |
| 050_Lot_GetGenealogyTree.sql | Ancestors / Descendants / Both; depth bound (B8); closure-vs-CTE result equivalence (when B4). |
| 060_LotPause_lifecycle.sql | Place + resume; double-place rejection (B3); cross-Cell concurrent pauses allowed; resumer ≠ pauser. |
| 065_LotPause_indicator.sql | _GetCountsByLocation returns correct open count; _GetByLocation returns correct list ordered by PausedAt. |
| 070_Label_print_reprint.sql | Initial print; reprint with reason; ZPL content rendered. |

Target: 90–120 passing tests in suite 0015.

## Phase 2 complete when

- Migration 0015_arc2_phase2_lot_lifecycle.sql applied. PauseEvent CREATEd; v_LotDerivedQuantities view CREATEd (or skipped if B5 elected).

- All Phase 2 procs (Lot mutation expansion, genealogy traversal, pause lifecycle, label print/reprint) delivered.

- All tests in sql/tests/0015_PlantFloor_Lot_Lifecycle/ pass.

- Perspective views: LOT Detail, LOT Search, Genealogy Viewer, Paused-LOT Indicator implemented.

- Phase 3+ stations can call Lot_Split, Lot_Merge, LotGenealogy_RecordConsumption, LotLabel_Print, LotPause_Place, LotPause_Resume, Lot_GetGenealogyTree against the delivered contract.

# Phase 3 — Die Cast Operator Station

Goal: Deliver the Die Cast workflow — LOT creation against an active Tool/Cavity, cumulative-checkpoint ProductionEvent capture, RejectEvent capture for early scrap, and PLC-driven downtime detection ingestion (the proc layer; PLC integration itself is Phase 6 territory).

Dependencies: Phase 1 (foundation), Phase 2 (LOT lifecycle).

Status: Blocked on Phases 1–2.

## Data Model Changes

Migration sql/migrations/versioned/0016_arc2_phase3_die_cast.sql (next unclaimed).

- Seed Parts.OperationTemplate rows for DieCastShot with the appropriate OperationTemplateField entries (no DieIdentifier / CavityNumber / WarmupShotCount — Tool/Cavity on Lot per B13; warm-up on DowntimeEvent per UJ-14).

- Seed Audit.LogEventType rows: DieCastCheckpointRecorded, RejectEventRecorded (if not already seeded).

- No new tables; no schema changes.

Tables used: Lots.Lot, Workorder.ProductionEvent, Workorder.ProductionEventValue, Workorder.RejectEvent, Quality.DefectCode, Tools.Tool, Tools.ToolCavity, Tools.ToolAssignment.

## Open Items Affecting This Phase

| Item | Status |
| --- | --- |
| A4 ShotCount semantics | Pending Phase 0 — cumulative counter (default) vs derived from aggregated LOT quantities. Phase 3 ships with cumulative; reframe is post-Phase-3 if MPP elects derived. |
| OI-09 cavity-parallel LOTs | ✅ Closed. N cavities → N peer LOTs (not sublots). Each LOT has its own ToolCavityId. |
| UJ-11 paper-to-screen | ✅ Closed (Option A — flagged risk). Couples to OI-31 rollout shape. |
| UJ-14 warm-up shots | ✅ Closed (Option A). DowntimeEvent.ShotCount only — no ProductionEventValue.WarmupShotCount. |
| OI-10 tool life | ✅ Superseded by Phase B Tools (Phase G of Arc 1). Tool identity and history live in Tools schema; shot counts derive from ProductionEvent. |

## State & Workflow

### Cavity-parallel LOTs at Die Cast

A multi-cavity die produces N parallel independent LOTs, not sublots. Each cavity’s basket is a peer LOT with its own ToolCavityId set at creation (FDS-05-034). Each LOT has its own piece count, fills at its own rate, closes independently. There is no parent/child FK between cavity peers — LotGenealogy is flat at Die Cast. One LTT label per LOT.

Sub-LOT splitting is a separate concept that fires at Machining OUT (per FDS-05-009 / Phase 5) — it splits a machined LOT across downstream destinations on lines that sublot, and is unrelated to die cavities.

### Die Cast LOT creation walkthrough

Die Cast terminals are typically Shared — parented to a Die Cast Area or Die Cast WorkCenter rather than a single press. One terminal serves multiple presses; the operator selects the active Cell context (the specific press they’re logging a basket for) by scan or dropdown per FDS-02-009. The walkthrough below assumes the Shared model; if a deployment chooses to dedicate a terminal to a single press (Cell-parented), the Cell-context-selection step is omitted and the Cell auto-resolves from the terminal’s parent.

- The operator approaches a Shared Die Cast terminal. Initials are not pre-populated (Shared terminals prompt per-action per FDS-04-009).

- The operator selects the active Cell context (scan a press barcode or pick from a dropdown of presses descendant of the terminal’s parent). Selection writes to session.custom.terminal.activeCellLocationId and persists until the operator changes it.

- A die is mounted on the selected press. The active Tools.ToolAssignment row for that Cell points at it. As the shift runs, castings drop into per-cavity baskets beside the press.

- When a cavity’s basket fills, the operator peels a pre-printed LTT barcode label off the stack (per FRS 2.2.1) and sticks it on the basket. The operator walks to the terminal, enters initials inline on the LOT-creation screen (Shared-terminal pattern), and scans the LTT.

- Perspective opens the LOT creation form. The Cell is the active context selected in step 2. The Tool field pre-populates from Tools.ToolAssignment_ListActiveByCell(@SelectedCellLocationId). The operator confirms.

- If the physical die has been swapped without the MES being updated, the operator hits Edit — an AD elevation prompt fires per FDS-04-007, a supervisor authenticates, the inline Tools.ToolAssignment_Release + _Assign correct the system of record in one transaction, and the Tool field updates.

- The operator picks the cavity from the cavity dropdown (filtered to active cavities on the mounted Tool via Tools.ToolCavity_ListActiveByTool), confirms piece count, and submits.

- Perspective calls Lots.Lot_Create with the @ItemId (the cast/trim Item produced at this press, looked up from the Tool’s configuration), @LotOriginTypeId = 'Manufactured', @CurrentLocationId = (selected Cell's Id), @PieceCount, @ToolId, @ToolCavityId, @AppUserId, @TerminalLocationId.

- Proc validates per FDS-05-034: Item eligible at the selected Cell (v_EffectiveItemLocation Direct ∪ BomDerived), piece count ≤ Parts.Item.MaxLotSize (PartsPerBasket), Tool mounted on Cell, Cavity belongs to Tool, Cavity Active.

- Proc mints LotName via IdentifierSequence_Next @Code='Lot' (e.g., MESL1710935).

- Proc inserts Lots.Lot, Lots.LotStatusHistory (initial Good), and (if B4) the closure self-row.

- Proc writes a first checkpoint ProductionEvent for this LOT — EventAt = SYSUTCDATETIME(), LotId, OperationTemplateId = DieCastShot, cumulative ShotCount and ScrapCount for the cavity at this moment, AppUserId, TerminalLocationId. No LocationId, no ItemId, no DieIdentifier, no CavityNumber (all derivable from the LOT’s FKs per B14).

- Audit LotCreated + DieCastCheckpointRecorded. Print LTT label via LotLabel_Print (Phase 2).

A second cavity’s basket fills on its own rhythm and is logged separately as a peer LOT — different LotName, different ToolCavityId, different LTT. Cavity-parallel LOTs are peers, not sublots. They share a Tool but nothing else. Each fills, closes, and moves independently via an explicit “Complete + Move” when the basket leaves the press (Phase 4 Movement Scan pattern).

### Die Cast warm-up shots (UJ-14 closed)

Warm-up shots are tracked as a downtime sub-category, not as production. Oee.DowntimeEvent.ShotCount carries the warm-up shot count when DowntimeReasonType = Setup. Warm-up shots are not entered on the LOT creation screen — they’re recorded against the prior downtime event (machine startup). Good production shots count toward ProductionEvent.ShotCount cumulative.

### Tool life tracking (OI-10 superseded)

Tool identity, cavity status (Active / Closed / Scrapped), and check-in/out history live in the Tools schema (delivered in Arc 1 Phase G). Shot counts derive from ProductionEvent filtered by Lot.ToolId / Lot.ToolCavityId. There is no per-Tool live counter column — derivation is the system of record. Tool-life threshold alarms remain FUTURE — delivered later via a scheduled Gateway Script that reads the derived shot counts.

### Reject capture at Die Cast

The operator enters reject events against the current LOT — defect code (e.g., DC-POR-01 Porosity), quantity, optional remarks. Per FRS Section 4, reject/scrap data is retained for analysis but is not part of the permanent production record in the same way good counts are — MPP MAY elect not to record rejects at every step. Phase 3 delivers the proc; the operator decides per-LOT.

### Downtime entry at Die Cast

A press stops; the operator logs the event via the Phase 8 Downtime Entry view — selects machine, reason code (e.g., EQ-DIE-STICK), start time, end time. If the PLC detected the stop first, the DowntimeEvent would have been created automatically with source=PLC and a NULL reason; the operator just assigns the reason code (per B7 — late-binding reason codes). Phase 3 doesn’t deliver downtime procs — that’s Phase 8.

## API Layer (Named Queries → Stored Procedures)

| Procedure | Parameters | Notes | Dependencies | Output |
| --- | --- | --- | --- | --- |
| Workorder.ProductionEvent_Record | @LotId, @OperationTemplateId, @WorkOrderOperationId NULL, @EventAt, @ShotCount NULL, @ScrapCount NULL, @WeightValue NULL, @WeightUomId NULL, @DataCollectionValuesJson NULL, @AppUserId, @TerminalLocationId, @Remarks NULL | Inserts a checkpoint event. Validates Lot_AssertNotBlocked. If B5: updates Lot.TotalInProcess / InventoryAvailable. Returns NewId. | Workorder.ProductionEvent, Workorder.ProductionEventValue, Lots.Lot, Lots.Lot_AssertNotBlocked, Audit.Audit_LogOperation | Status, Message, NewId |
| Workorder.RejectEvent_Record | @LotId, @DefectCodeId, @Quantity, @ChargeToArea NULL, @Remarks NULL, @AppUserId, @TerminalLocationId | Inserts a reject event. Independent of ProductionEvent (rejects can fire any time). | Workorder.RejectEvent, Quality.DefectCode, Audit.Audit_LogOperation | Status, Message, NewId |
| Tools.ToolAssignment_ListActiveByCell | @CellLocationId BIGINT | Returns active Tool assigned to this Cell (zero or one row in MVP for Die Cast — known limitation: filtered UNIQUE on Cell prevents multi-Tool Cells, fine for Die Cast / not for Machining cells with multiple cutters; revisit post-MVP). | Tools.ToolAssignment | Single row or empty |
| Tools.ToolCavity_ListActiveByTool | @ToolId BIGINT | Returns active cavities for a Tool. | Tools.ToolCavity | Rowset |

## Gateway Scripts

| Script | Purpose | Trigger |
| --- | --- | --- |
| DieCastCycleReader (per-press) | Reads PLC CycleComplete edge, increments a per-Cavity in-memory shot counter that Perspective queries when the operator opens the LOT creation screen (informs @ShotCount parameter). Optional — operator can override. | PLC tag edge (TOPServer) |

## Perspective Views

| View | Purpose |
| --- | --- |
| Die Cast LOT Entry (purpose-built top-level view) | Composes the Cell Context Selector (Shared terminals — selects active press), Per-Mutation Initials Field, and Die-Cast-specific form (Tool pre-populated from active assignment with elevated Edit, Cavity dropdown filtered to active cavities, piece count + weight inputs). Submits Lot_Create + first ProductionEvent_Record. Inline reject entry triggers RejectEvent_Record. Embedded Paused-LOT Indicator surfaces any paused LOTs for the active Cell. |

No separate Die Cast LOT Detail view. After submit, navigation routes to the polymorphic Phase 2 LOT Detail view (parameterized by the new LotId). That view conditionally renders Tool / Cavity rows when populated — which they are for Die Cast–origin LOTs — and skips them for other origins. One LOT Detail surface across the entire plant.

## Test Coverage

New test suite at sql/tests/0016_PlantFloor_DieCast/:

| File | Covers |
| --- | --- |
| 010_ProductionEvent_Record.sql | Checkpoint insertion; LAG-derived deltas equal cumulative diff; missing required params reject; blocked-LOT rejection; B5 materialized column updates. |
| 020_RejectEvent_Record.sql | Insertion; defect code FK validation; quantity must be positive. |
| 030_DieCast_walkthrough.sql | End-to-end scenario: ToolAssignment lookup against a selected Cell → Lot_Create with Tool/Cavity → first ProductionEvent → second ProductionEvent at later time → LAG delta correct. |
| 040_CavityParallel_peers.sql | Two LOTs created on the same Tool, different Cavities, no parent-child FK; each closes independently. |

Target: 50–70 passing tests in suite 0016.

## Phase 3 complete when

- Migration 0016_arc2_phase3_die_cast.sql applied. OperationTemplate seeds in place. LogEventType seeds in place.

- ProductionEvent_Record and RejectEvent_Record procs delivered with checkpoint shape (no GoodCount / NoGoodCount parameters).

- ToolAssignment_ListActiveByCell and ToolCavity_ListActiveByTool procs delivered.

- All tests in sql/tests/0016_PlantFloor_DieCast/ pass (target 50–70).

- Perspective Die Cast LOT Entry view implemented with Tool auto-populate + elevated Edit + Cavity dropdown.

- Gateway DieCastCycleReader implemented (optional — operator override path covers if not yet wired).

- End-to-end integration check: an operator at a Shared Die Cast terminal selects a press as Cell context, creates a Cavity-A LOT, then later creates a Cavity-B LOT on the same press; both peer LOTs exist with their respective ToolCavityId; first ProductionEvent written for each with cumulative ShotCount; one reject event recorded; LTT labels printed; navigation to Phase 2 LOT Detail shows Tool/Cavity rendered correctly.

# Phase 4 — Movement + Trim + Receiving

Goal: Deliver the cross-cutting Movement Scan pattern that every downstream operator station reuses, the Trim Shop checkpoint workflow (LOT keeps cast-part identity through Trim — yield loss only; tracked at Area resolution: check-in → process → check-out), the Trim OUT 1:1 whole-LOT move to the destination Machining line (FDS-06-006 — no split at Trim; sub-LOT splitting moved to Machining OUT / Phase 5 per FDS-05-009), and the Receiving Dock pass-through-part flow.

Dependencies: Phase 1 (foundation), Phase 3 (ProductionEvent_Record). (No longer depends on Phase 2 Lot_Split — Trim OUT moves the LOT whole; the split moved to Phase 5.)

Status: Blocked on Phases 1–3.

## Data Model Changes

Migration sql/migrations/versioned/0017_arc2_phase4_movement_trim_receiving.sql (next unclaimed).

- Seed Parts.OperationTemplate rows for TrimIn, TrimOut, ReceivingScan with appropriate OperationTemplateField entries. TrimOut is a whole-LOT move — it carries no split flag (the RequiresSubLotSplit column now lands in Phase 5’s migration 0018 on the MachiningOut template).

- Seed Audit.LogEventType rows: LotMoved, TrimCheckpointRecorded, TrimOutRecorded, ReceivingScanRecorded (where missing).

- No new tables. No schema additions (the RequiresSubLotSplit ALTER moved to Phase 5 / migration 0018).

Tables used: Lots.Lot, Lots.LotMovement, Workorder.ProductionEvent, Workorder.RejectEvent, Parts.OperationTemplate, Parts.v_EffectiveItemLocation, Parts.Item.MaxParts (OI-12 cap), Location.LocationAttribute (LinesideLimit). (No Lots.LotGenealogy / closure writes in Phase 4 — Trim OUT moves the LOT whole; genealogy split edges are written in Phase 5 at Machining OUT.)

## Open Items Affecting This Phase

| Item | Status |
| --- | --- |
| OI-11 Casting → Trim part-identity rename | ✅ Superseded — rename moved to Trim → Machining (FDS-05-033 v0.11m). Trim Shop is yield loss only, no rename. |
| OI-12 MaxParts per-Item per-Location cap | ✅ Closed. Movement Scan validates incoming quantity against Parts.Item.MaxParts at the destination Cell. |
| OI-18 ItemLocation hierarchy cascade | ✅ Closed. Parts.v_EffectiveItemLocation (Direct ∪ BomDerived per FDS-02-012) walks Cell → WorkCenter → Area → Site at scan-in. |
| UJ-03 Sub-LOT split trigger | ➡️ Moved to Phase 5. The split no longer fires at Trim OUT — Trim OUT is a whole-LOT move. The RequiresSubLotSplit flag and the split UX live on the MachiningOut template (Phase 5). See Phase 5’s Open Items table for the current UJ-03 status. |

## State & Workflow

### Movement Scan Screen — reusable pattern (LOT inbound)

Every operator station that receives a scanned LOT-in uses the same Movement Scan pattern. This is the inbound flow. Outbound flows (Trim OUT, Machining OUT) are described in their own sections below — they are NOT part of Movement Scan.

- Operator scans LTT at the destination terminal.

- Perspective calls Lots.Lot_Get with @LotName for header data.

- Perspective calls Parts.ItemLocation_CheckEligibility(@ItemId, @CellLocationId) (which reads v_EffectiveItemLocation Direct ∪ BomDerived). On reject, surface the FDS-02-012 reject message: “Part {PartNumber} is not configured for {CellCode} and is not a component of any part eligible there.”

- Perspective calls Parts.Item_GetMaxParts(@ItemId) and Lots.Lot_GetCellLineQuantity(@CellLocationId, @ItemId) (sums existing pieces of this Item at this Location across all open LOTs). If existing + incoming > MaxParts, reject with OI-12 message.

- On accept: Lots.Lot_MoveTo writes the LotMovement row.

- Phase-specific follow-on on the inbound side: Trim IN writes a checkpoint ProductionEvent; Machining IN (Phase 5) does NOT use this Movement Scan pattern at all — Machining IN is FIFO pick + BOM-driven rename, not scan-to-receive; Receiving creates the LOT via Lot_Create rather than moving an existing LOT. Outbound flows that complete an operation and route LOT(s) to the next station live in their own sections (Trim OUT below; Phase 5 Machining OUT is fully PLC-driven).

### Trim Shop — Trim IN (checkpoint + yield loss)

A LOT arrives at the Trim Shop and an operator scans the LTT.

- Movement Scan pattern fires Lot_MoveTo from the upstream Die Cast Cell to the Trim Shop Area (Trim is tracked at Area resolution — check-in → process → check-out, not at line or cell level).

- The scan also triggers a checkpoint ProductionEvent with OperationTemplateId = TrimIn, EventAt = SYSUTCDATETIME(), cumulative ShotCount (carries forward — Trim doesn’t add shots) and ScrapCount (carries forward). Because this is the LOT’s second event, deltas pop out from LAG() at read time.

- The operator runs sprue removal, deburr, wash. If the basket needs a piece-count correction (weight-based estimation per FRS 2.2.3), the operator updates via Lot_Update (Phase 2) — LotAttributeChange records the before/after.

- If sprue/deburr/wash yields scrap, the operator records RejectEvent_Record (Phase 3) on the same LOT — the LOT still carries its cast/trim Item identity; trim is yield loss, not a rename. There is no ConsumptionEvent, no new LOT, no genealogy edge from Trim work itself.

### Trim OUT — outbound flow (1:1 whole-LOT move)

When the operator completes Trim work and triggers Trim OUT, the LOT moves whole to its destination Machining line — Trim OUT does not split (sub-LOT splitting moved to Machining OUT / Phase 5 per FDS-05-009). The operator selects a single destination by scan or dropdown (per FDS-02-009), or routing supplies it where the line’s Operation Template defines it.

- Operator selects the destination Machining line (scan or dropdown).

- On confirm, Perspective calls Workorder.TrimOut_Record:

  - Writes a closing ProductionEvent with OperationTemplateId = TrimOut and the final cumulative counters.

  - Calls Lots.Lot_MoveTo from the Trim Shop Area to the destination — this places the whole LOT in that line’s FIFO queue (read by Phase 5 Machining IN via Lot_GetWipQueueByLocation).

  - The parent LOT stays whole and open — no split, no children, no genealogy edge, no closure-table additions.

  - Audit TrimOutRecorded.

- The LOT retains its cast/trim ItemId until the rename at Machining IN (FDS-05-033).

There is no multi-destination / Flex-Repeater UX at Trim OUT in this model — that machinery now lives at Machining OUT (Phase 5), driven by the RequiresSubLotSplit flag on the MachiningOut Operation Template.

### Receiving Dock — pass-through parts

A truck delivers 6MA Cam Holder housings (pass-through — MPP doesn’t manufacture). The Receiving operator scans the packing slip on a Receiving terminal:

- Perspective opens the Receiving screen. Inputs: @PartNumber (resolves to @ItemId), @VendorLotNumber, @PieceCount.

- Perspective calls Lots.Lot_Create with @LotOriginTypeId = 'Received', @CurrentLocationId = (Receiving Dock's Id), NULL Tool/Cavity (non-die-cast), @VendorLotNumber. Mints the LOT.

- LTT label prints. The received LOT is identical to a manufactured LOT downstream — same movement, hold, consumption, genealogy. Difference is LotOriginType = 'Received'.

Per FRS 5.6.1 and Scope Matrix row 3, receiving pass-through parts is MVP. Full operational workflows (receiving inspection, vendor lot verification, staging procedures specific to pass-through) are FUTURE — the schema supports them; the Perspective screens beyond basic Receiving are deferred.

### Supplier-identified serial ranges

Some pass-through parts arrive with vendor-issued serial number ranges (e.g., PNA mounting pins). Phase 4 Receiving captures @MinSerialNumber and @MaxSerialNumber on Lot_Create — Phase 6 Assembly’s ConsumptionEvent validates that consumed serials fall within the LOT’s range.

## API Layer (Named Queries → Stored Procedures)

| Procedure | Parameters | Notes | Output |
| --- | --- | --- | --- |
| Parts.ItemLocation_CheckEligibility | @ItemId, @CellLocationId | Reads v_EffectiveItemLocation. Returns IsEligible BIT + the matching path (Direct / BomDerived / NULL). | Single row |
| Parts.Item_GetMaxParts | @ItemId | Returns MaxParts INT NULL for the Item. | Single row |
| Lots.Lot_GetCellLineQuantity | @CellLocationId, @ItemId | Sums existing pieces of this Item at this Location across all open LOTs. Used by Movement Scan to validate against MaxParts. | Single row |
| Workorder.TrimOut_Record | @ParentLotId, @OperationTemplateId, @ShotCount, @ScrapCount, @DestinationCellLocationId, @AppUserId, @TerminalLocationId | Writes the closing Trim ProductionEvent, then calls Lot_MoveTo once to move the whole LOT to the destination Machining line. No split — single transaction, whole-LOT move only. (Splitting moved to MachiningOut_Record in Phase 5.) | Single row: Status, Message, ProductionEventId |
| Lots.Lot_GetWipQueueByLocation | @LocationId BIGINT, @IncludeDescendants BIT = 0 | Returns the LOTs at the given location in arrival order (LastMovementAt ASC). Used by Phase 5 Machining IN to display FIFO queue. | Rowset |

## Gateway Scripts

| Script | Purpose | Trigger |
| --- | --- | --- |
| LttZplDispatcher | Receives system.util.sendMessage events from LotLabel_Print (Phase 2) — assembles ZPL from a template + dispatches to the Zebra at the operator’s terminal. Updates the LotLabel row with print-ack timestamp. | Gateway message handler |

## Perspective Views

| View | Purpose |
| --- | --- |
| Movement Scan (cross-cutting embedded component) | Embedded pattern reused in every station that receives LOTs (Trim IN, Receiving — though Receiving uses Lot_Create, not Lot_MoveTo). Validates eligibility + MaxParts; calls Lot_MoveTo. |
| Trim Station IN (purpose-built top-level view) | Composes Movement Scan + Per-Mutation Initials Field + checkpoint ProductionEvent write + reject capture. Embedded Paused-LOT Indicator. |
| Trim Station OUT (purpose-built top-level view) | Composes a closing ProductionEvent write + a single destination selector (scan or dropdown) + TrimOut_Record (whole-LOT move). No split UX — one destination, one submit. (The multi-destination Flex-Repeater split UX moved to Phase 5’s Machining OUT view.) |
| Receiving Dock (purpose-built top-level view) | LOT creation from packing-slip data — Lot_Create with LotOriginType='Received'. Captures vendor lot number + supplier-issued serial range. |

After submit, navigation from any Trim view routes to the polymorphic Phase 2 LOT Detail view for the moved/split LOT(s).

## Test Coverage

New test suite at sql/tests/0017_PlantFloor_Movement_Trim/:

| File | Covers |
| --- | --- |
| 010_ItemLocation_CheckEligibility.sql | Direct match; BomDerived match; cascade Cell → WorkCenter → Area; ineligible (no path) rejects with FDS-02-012 message. |
| 020_Item_GetMaxParts_and_Lot_GetCellLineQuantity.sql | MaxParts read; sum-by-Cell-by-Item correct across multiple open LOTs; deprecated LOTs excluded. |
| 030_Movement_Scan_pattern.sql | Eligible move succeeds + LotMovement row + checkpoint ProductionEvent (Trim); MaxParts overflow rejects with OI-12 message. |
| 040_TrimOut_Record_move_whole.sql | TrimOut_Record moves the whole LOT to the destination Machining line; closing ProductionEvent written; LotMovement row written; LOT visible in that line’s FIFO queue; parent stays open — no split, no children, no closure rows. |
| 050_TrimOut_Record_validation.sql | Missing destination rejects; non-Machining destination rejects (eligibility check); blocked LOT rejects via Lot_AssertNotBlocked. |
| 070_Receiving_pass_through.sql | Lot_Create with LotOriginType = 'Received'; vendor lot number captured; serial range captured. |

(Sub-LOT split tests — multi-way split, split-to-same-cell, flag-mismatch — moved to Phase 5 suite 0018, where the split now lives.)

Target: 55–75 passing tests in suite 0017.

## Phase 4 complete when

- Migration 0017_arc2_phase4_movement_trim_receiving.sql applied. OperationTemplate seeds in place. LogEventType seeds in place.

- Movement Scan pattern delivered (helper procs + Perspective component).

- TrimOut_Record proc delivered — whole-LOT move to the destination Machining line (no split).

- Lot_GetWipQueueByLocation delivered (consumed by Phase 5).

- All tests in sql/tests/0017_PlantFloor_Movement_Trim/ pass (target 55–75).

- Perspective Movement Scan, Trim Station IN, Trim Station OUT (whole-LOT move), Receiving Dock views implemented.

- Gateway LttZplDispatcher implemented and tested against Zebra emulator + real Zebra at the dev Trim terminal.

- End-to-end integration check: A LOT created in Phase 3 moves to Trim → Trim IN checkpoint event written → Trim OUT moves the whole LOT to one Machining line → LOT visible in that line’s FIFO queue via Lot_GetWipQueueByLocation (no split at Trim — the sub-LOT split is exercised in Phase 5).

# Phase 5 — Machining

Goal: Deliver the Machining workflow — FIFO pick at Machining IN (whole cast/trim LOTs from Trim OUT) with the BOM-driven part-identity rename (FDS-05-033); the Machining OUT split-or-auto-move branch (FDS-06-008 + FDS-05-009) — an operator-initiated sub-LOT split on sublotting lines (those with a dedicated Machining OUT terminal, RequiresSubLotSplit=1), and PLC-driven auto-completion with auto-move to the coupled Assembly Cell on non-sublotting coupled lines; and reject capture for out-of-tolerance pieces. Machining OUT therefore has an operator screen only on sublotting lines; coupled lines remain fully event-driven with no operator OUT screen.

Dependencies: Phase 1 (foundation), Phase 2 (Lot_Split — now consumed here for the Machining OUT split — + LotGenealogy_RecordConsumption), Phase 3 (ProductionEvent_Record, RejectEvent_Record), Phase 4 (Trim OUT places whole cast/trim LOTs into this phase’s FIFO queues; Lot_GetWipQueueByLocation is the queue read).

Status: Blocked on Phases 1–4.

## Data Model Changes

Migration sql/migrations/versioned/0018_arc2_phase5_machining.sql (next unclaimed).

- ALTER Parts.OperationTemplate ADD RequiresSubLotSplit BIT NOT NULL DEFAULT 0 — controls the Machining OUT outbound flow (relocated here from Phase 4 per FDS v1.3 / Phased Plan v1.1). When 1, the line sublots: the Machining OUT screen presents the multi-destination split UX (one sub-LOT per destination). When 0 (default), the line does not sublot — Machining OUT is the PLC-driven auto-move (coupled) or manual whole-move (uncoupled). Versioned per the existing OperationTemplate clone-to-modify pattern. Engineering authors per Item per Cell via the Configuration Tool; the physical correlate is whether the line has a dedicated Machining OUT terminal.

- Seed Parts.OperationTemplate rows for MachiningIn and MachiningOut with the appropriate OperationTemplateField entries (cycle time, fixture, program — final list confirmed during Phase 0 A5 walkthrough alongside DefaultScreen / ConfirmationMethod seeding). Initial MachiningOut seed rows carry RequiresSubLotSplit = 1 for lines known to sublot; the rest default to 0 and Engineering edits per Item later.

- Seed Audit.LogEventType rows: MachiningInPicked, MachiningOutCompleted, MachiningOutAutoMoved, MachiningOutSubLotSplit (where missing).

- No new tables.

Data model follow-up flagged: the RequiresSubLotSplit BIT column on Parts.OperationTemplate lands in this migration (moved from the Phase 4 plan). MPP_MES_DATA_MODEL.md still describes it (and Item.DefaultSubLotQty) under Trim OUT semantics — that reword to Machining OUT is a still-pending data-model revision (deferred 2026-06-03).

Tables used: Lots.Lot, Workorder.ProductionEvent, Workorder.ConsumptionEvent, Workorder.RejectEvent, Lots.LotGenealogy (+ LotGenealogyClosure if B4), Lots.LotMovement, Parts.Bom, Parts.BomLine, Parts.OperationTemplate (now with RequiresSubLotSplit), Location.LocationAttribute (CoupledDownstreamCellLocationId per FDS-06-008). Procs: Lots.Lot_Split (Machining OUT split), Lots.Lot_MoveTo.

## Open Items Affecting This Phase

| Item | Status |
| --- | --- |
| A4 ShotCount semantics | Pending Phase 0 — affects Machining ProductionEvent contents same as Die Cast. |
| OI-18 ItemLocation hierarchy cascade | ✅ Closed. v_EffectiveItemLocation Direct ∪ BomDerived applies at Machining IN — the cast/trim parent must be eligible at the Machining Cell (BomDerived path resolves through the machined-Item BOM whose child is the cast/trim Item). |
| UJ-03 Sub-LOT split trigger | 🔶 In Review (Ben pending). Resolved structurally via Parts.OperationTemplate.RequiresSubLotSplit BIT on the MachiningOut template (this phase) — Engineering authors per Item per Cell whether Machining OUT splits or moves whole. The split fires at Machining OUT (per MPP, confirmed 2026-06), not Trim OUT. Machining IN consumes a whole cast/trim LOT and produces a renamed machined LOT one-to-one; the machined LOT is what gets split (if at all) at Machining OUT. Ben’s remaining input is whether split-default-quantities need a per-Item override beyond the system-wide N=2 even-split default. |
| FDS-06-008 Auto-move on completion | ✅ Closed. CoupledDownstreamCellLocationId LocationAttribute on the Machining Cell drives the auto-move target. NULL = legacy uncoupled path (operator-driven move via Phase 4 Movement Scan). |

## State & Workflow

### Machining IN — FIFO pick + BOM-driven rename

The operator at a Machining Cell terminal sees the Cell’s FIFO queue — whole cast/trim LOTs that landed here at Trim OUT (Phase 4, 1:1 move) are visible in arrival order. There is no scan-to-receive at Machining IN. The pick + rename is the receive event.

- Perspective calls Lots.Lot_GetWipQueueByLocation @LocationId = (this Cell's Id) — returns the LOTs ordered by LastMovementAt ASC.

- The Machining IN view renders the queue. The operator picks the next entry (by tap or scan of the LTT for confirmation). Override of FIFO order is allowed — Perspective prompts for an optional “queue override reason” when a non-first entry is picked, captured to the resulting ProductionEvent’s ProductionEventValue rows.

- On pick, the system applies the BOM-driven part-identity rename (FDS-05-033). The picked LOT carries the cast/trim Item (e.g., 5G0-TRIM-4102); the active Parts.Bom for the machined Item (5G0-MACHINED-4102) has a single BomLine with ChildItemId = 5G0-TRIM-4102 at QtyPer = 1.

- Perspective calls Workorder.MachiningIn_PickAndConsume (composite proc):

  - Validates Lot_AssertNotBlocked on the picked LOT.

  - Validates eligibility — the picked LOT’s Item must resolve via v_EffectiveItemLocation BomDerived path at this Cell (the cast/trim Item is eligible because it’s a child line on the machined Item’s BOM and the machined Item has Direct eligibility here).

  - Resolves the produced Item by BOM lookup — finds the active Parts.Bom whose only BomLine lists the picked LOT’s Item as the child. (If multiple BOMs match — degenerate misconfiguration — proc raises with a clear message.)

  - Calls Lots.Lot_Create to mint the machined LOT under the produced Item with LotOriginType='Manufactured' (NULL Tool/Cavity — Tool/Cavity belong to die-cast LOTs only per B13). Mints a fresh LotName via IdentifierSequence_Next.

  - Calls Lots.LotGenealogy_RecordConsumption to insert the genealogy + closure rows linking source LOT → produced machined LOT.

  - Writes a Workorder.ConsumptionEvent row recording the per-piece consumption (source piece count = produced piece count for a 1-line BOM at QtyPer=1).

  - Writes a checkpoint Workorder.ProductionEvent for the new machined LOT with OperationTemplateId = MachiningIn and EventAt = SYSUTCDATETIME().

  - Closes the source LOT (Lot_UpdateStatus → Closed) since all pieces have been consumed into the machined LOT.

  - Audit: MachiningInPicked.

- Perspective prompts the operator to scan a fresh LTT for the new machined LOT. The label prints via LotLabel_Print (Phase 2).

- The operator places the machined LOT in the machining setup and starts the cycle.

### Machining OUT — split (sublotting lines) or PLC auto-complete + auto-move (FDS-06-008 + FDS-05-009)

Machining OUT behavior is determined by the active MachiningOut OperationTemplate’s RequiresSubLotSplit flag (physical correlate: whether the line has a dedicated Machining OUT terminal).

Sublotting line — RequiresSubLotSplit = 1 (operator-initiated split, per FDS-05-009):

- The operator completes the Machining operation and triggers Machining OUT at the line’s Machining OUT terminal.

- Perspective pre-fills the machined LOT’s piece count and presents an auto-split preview — default N=2 even split (e.g., 48 → 24/24; 51 → 26/25). The operator MAY adjust the number of sub-LOTs and per-sub-LOT quantities; the total SHALL equal the parent’s piece count.

- A Flex Repeater renders N destination-selection rows — one per sub-LOT, each with its piece count + a destination selector (scan or dropdown per FDS-02-009). Routing MAY supply the destination set where the Operation Template defines it.

- On confirm, Perspective calls Workorder.MachiningOut_RecordSplit with @SplitChildrenJson ([{pieceCount, destinationLocationId}, ...]):

  - Writes a closing ProductionEvent with OperationTemplateId = MachiningOut and the final cumulative counters.

  - Calls Lots.Lot_Split for the N children. Each child inherits the parent’s machined Item (rename already happened at Machining IN per FDS-05-033) and is machining-origin (NULL Tool/Cavity per B13).

  - For each child, calls Lots.Lot_MoveTo from this Machining Cell to its destination.

  - Returns a multi-row result with each child’s LotName for LTT printing.

  - Audit: MachiningOutSubLotSplit.

- LTT labels print for each child sub-LOT — labels follow FDS-05-024 parent-reference rule (child LotName + parent LotName both shown).

Non-sublotting line — RequiresSubLotSplit = 0 (PLC-driven auto-complete, FDS-06-008):

Machining OUT is event-driven, not operator-initiated. The operator does not scan, sign off, or interact with the MES at the moment of completion.

- The Machining PLC asserts OperationComplete (or equivalent edge — final tag name confirmed during Phase 0 A5 / OperationTemplate field walkthrough).

- The Gateway script MachiningOpCompleteWatcher (per-Cell) reads the edge and resolves the active machined LOT at this Cell from Lots.Lot.CurrentLocationId.

- The Gateway script calls Workorder.MachiningOut_AutoComplete @LotId, @CellLocationId, @AppUserId = (a "system" AppUser row reserved for PLC-driven actions), @TerminalLocationId = NULL.

- The proc:

  - Validates Lot_AssertNotBlocked on the machined LOT.

  - Writes a checkpoint Workorder.ProductionEvent with OperationTemplateId = MachiningOut and EventAt = SYSUTCDATETIME().

  - Reads the CoupledDownstreamCellLocationId LocationAttribute on the Machining Cell.

  - If CoupledDownstreamCellLocationId is non-NULL: calls Lots.Lot_MoveTo from this Machining Cell to the coupled downstream Cell. Audit: MachiningOutAutoMoved.

  - If CoupledDownstreamCellLocationId is NULL: writes only the ProductionEvent. Audit: MachiningOutCompleted. The LOT stays at the Machining Cell awaiting an explicit operator-driven movement (legacy uncoupled path — the operator uses the Phase 4 Movement Scan to move the LOT manually).

- The basket physically rolls to the coupled Cell (typically the paired Assembly Cell within the same WorkCenter). The Assembly Cell sees the machined LOT arrive in its queue without any operator action between Machining and Assembly.

(Coupling note: a sublotting line is configured with CoupledDownstreamCellLocationId NULL — its Machining OUT terminal drives the FDS-05-009 split rather than an auto-move. So RequiresSubLotSplit = 1 lines are also uncoupled; the two settings are consistent, not independent knobs.)

### Reject capture at Machining

If parts come off out-of-tolerance during the cycle, the operator records RejectEvent_Record (Phase 3) against the machined LOT — defect code from a Machining-Area-filtered DefectCode picker (e.g., MS-OOT-01 Dimensional, MS-TOOLMARK-02), quantity, optional remarks. Reject capture is independent of the Machining OUT event — it can fire at any time during the cycle (before, during, after the OUT auto-complete).

### Rework LOTs

Machining may process a rework LOT returning from Phase 7’s Sort Cage. Rework LOTs appear in the Cell’s FIFO queue if their CurrentLocationId is this Machining Cell. No special handling — they look identical in the queue. The MachiningIn pick + rename mechanic still applies (rework consumes the rework LOT and produces a new machined LOT under the same Item, completing the second-pass genealogy).

## API Layer (Named Queries → Stored Procedures)

| Procedure | Parameters | Notes | Dependencies | Output |
| --- | --- | --- | --- | --- |
| Workorder.MachiningIn_PickAndConsume | @SourceLotId BIGINT, @CellLocationId BIGINT, @QueueOverrideReason NVARCHAR(500) NULL, @AppUserId, @TerminalLocationId | Composite: validates eligibility + BOM lookup; mints machined LOT via Lot_Create; writes ConsumptionEvent + LotGenealogy (+ closure) + checkpoint ProductionEvent; closes source sub-LOT. Single transaction. | Lots.Lot_Create, Lots.LotGenealogy_RecordConsumption, Lots.Lot_UpdateStatus, Workorder.ProductionEvent, Workorder.ConsumptionEvent, Parts.Bom, Parts.BomLine, v_EffectiveItemLocation, Audit.Audit_LogOperation | Status, Message, NewMachinedLotId BIGINT, NewMachinedLotName NVARCHAR(50), ConsumptionEventId BIGINT, ProductionEventId BIGINT |
| Workorder.MachiningOut_AutoComplete | @LotId BIGINT, @CellLocationId BIGINT, @AppUserId BIGINT, @TerminalLocationId NULL | PLC-triggered on non-sublotting lines (RequiresSubLotSplit=0). Writes Machining OUT checkpoint ProductionEvent + reads CoupledDownstreamCellLocationId + auto-Lot_MoveTo if non-NULL. | Workorder.ProductionEvent, Lots.Lot_MoveTo, Location.LocationAttribute, Audit.Audit_LogOperation | Status, Message, ProductionEventId, AutoMoved BIT, ToLocationId BIGINT NULL |
| Workorder.MachiningOut_RecordSplit | @ParentLotId BIGINT, @OperationTemplateId BIGINT, @SplitChildrenJson NVARCHAR(MAX) ([{pieceCount, destinationLocationId}, ...]), @AppUserId, @TerminalLocationId | Operator-triggered on sublotting lines (RequiresSubLotSplit=1). Validates the JSON child count + that the sum equals the parent piece count; writes the closing ProductionEvent; calls Lot_Split for the N children; then Lot_MoveTo for each child to its destination. Single transaction. | Lots.Lot_Split, Lots.Lot_MoveTo, Workorder.ProductionEvent, Lots.LotGenealogy, Audit.Audit_LogOperation | Multi-row: header Status, Message, ProductionEventId; per-child row (ChildLotId, ChildLotName, DestinationLocationId) |

## Gateway Scripts

| Script | Purpose | Trigger | External System | Audit |
| --- | --- | --- | --- | --- |
| MachiningOpCompleteWatcher (per Cell) | Watches PLC OperationComplete edge on each non-sublotting Machining Cell (RequiresSubLotSplit=0). On edge, resolves the active machined LOT and calls MachiningOut_AutoComplete. (Sublotting cells have no PLC auto-complete — their Machining OUT is operator-driven via MachiningOut_RecordSplit.) | PLC tag edge (TOPServer) | PLC | OperationLog via the proc’s audit; InterfaceLog on every PLC read/write per B4 |
| MachiningCycleReader (optional, per Cell) | Reads PLC CycleComplete per individual cycle and stamps cumulative cycle-time onto the Machining IN ProductionEventValue. Optional — operator can enter cycle time manually if PLC doesn’t expose the tag. | PLC tag edge | PLC | InterfaceLog on read |

## Perspective Views

| View | Purpose |
| --- | --- |
| Machining IN (purpose-built top-level view) | Composes the FIFO Queue list (Flex Repeater binding Lot_GetWipQueueByLocation → embedded view per queue entry: LotName, parent LotName, piece count, arrival time, “Pick” button) + Per-Mutation Initials Field + BOM-Driven Rename Confirmation Modal + Cell Context Selector (Shared terminals only) + Paused-LOT Indicator. Submit on Pick fires MachiningIn_PickAndConsume. |
| BOM-Driven Rename Confirmation Modal (cross-cutting embedded component) | Displays “This LOT is {SourceItem}. Receive as {ProducedItem}?” with Confirm / Cancel. Reusable across any phase that does BOM-driven rename. |
| Machining OUT Split (purpose-built top-level view — sublotting lines only) | Shown only on lines whose MachiningOut template has RequiresSubLotSplit=1. Auto-split preview (editable N + per-child piece counts) + a Flex Repeater + Embedded View of destination selectors (one row per sub-LOT). Single submit fires MachiningOut_RecordSplit. |
| Cell Selector Repeater Entity (cross-cutting embedded view) | The embedded view the Flex Repeater renders per row in Machining OUT Split (and any future view that picks N destinations). One sub-LOT row, one destination selector (scan or dropdown), one piece-count display. Pure composition — no business logic. (Moved here from Phase 4 with the split.) |

No operator OUT screen on non-sublotting lines. On coupled / uncoupled lines (RequiresSubLotSplit=0) Machining OUT is fully PLC-driven — operators see the machined LOT arrive at the coupled downstream Cell (typically Assembly) via that Cell’s queue read; the Phase 2 LOT Detail view shows the full event timeline if needed. Sublotting lines (RequiresSubLotSplit=1) use the Machining OUT Split view above.

## Test Coverage

New test suite at sql/tests/0018_PlantFloor_Machining/:

| File | Covers |
| --- | --- |
| 010_MachiningIn_PickAndConsume_happy.sql | Whole cast/trim LOT in queue → pick → BOM resolves machined Item → new machined LOT minted → ConsumptionEvent + genealogy (+ closure) + checkpoint event written → source LOT closed. |
| 020_MachiningIn_eligibility.sql | BomDerived eligibility resolves through the machined Item’s BOM; ineligible (no path) rejects with FDS-02-012 message. |
| 030_MachiningIn_BOM_lookup_edge_cases.sql | Missing BOM rejects; multiple BOMs matching the source Item rejects with clear message; deprecated BOM not used. |
| 040_MachiningOut_AutoComplete_coupled.sql | RequiresSubLotSplit=0, CoupledDownstreamCellLocationId non-NULL → ProductionEvent + LotMovement to coupled Cell; AutoMoved=1 returned. |
| 050_MachiningOut_AutoComplete_uncoupled.sql | RequiresSubLotSplit=0, CoupledDownstreamCellLocationId NULL → ProductionEvent only, no LotMovement; AutoMoved=0 returned. |
| 060_MachiningOut_blocked_lot.sql | Held LOT at Machining Cell → AutoComplete rejects via Lot_AssertNotBlocked. |
| 070_MachiningOut_RecordSplit.sql | RequiresSubLotSplit=1 — 2-way split into two destinations; child LOTs inherit the machined Item; LotGenealogy Split edges + closure rows; LotMovement per child; parent closed; children visible in their destination queues. |
| 075_MachiningOut_RecordSplit_same_destination.sql | RequiresSubLotSplit=1 — N children all routed to the same destination (legitimate edge case). |
| 080_MachiningOut_RecordSplit_validation.sql | Sum-of-children ≠ parent rejects; missing destination rejects; blocked parent LOT rejects via Lot_AssertNotBlocked. |
| 090_Rework_LOT_in_queue.sql | Rework LOT routed back to a Machining Cell from Sort Cage flows through the same MachiningIn pick + rename without special handling. |

Target: 80–110 passing tests in suite 0018.

## Phase 5 complete when

- Migration 0018_arc2_phase5_machining.sql applied — including the RequiresSubLotSplit ALTER (moved from Phase 4). OperationTemplate seeds in place. LogEventType seeds in place.

- MachiningIn_PickAndConsume composite proc delivered.

- MachiningOut_AutoComplete PLC-trigger proc delivered.

- MachiningOut_RecordSplit operator-split proc delivered (sublotting lines).

- All tests in sql/tests/0018_PlantFloor_Machining/ pass (target 80–110).

- Perspective Machining IN view implemented with FIFO Queue Repeater + BOM-Driven Rename Confirmation Modal.

- Perspective Machining OUT Split view implemented (Flex Repeater destination selectors) for sublotting lines.

- Gateway MachiningOpCompleteWatcher per-Cell implemented and tested against PLC OperationComplete edge in dev (non-sublotting cells).

- End-to-end integration check (coupled path): A Phase 4 Trim OUT whole-LOT move sends a LOT to a Machining Cell whose CoupledDownstreamCellLocationId points at a paired Assembly Cell. Operator picks from FIFO → BOM-driven rename produces machined LOT → cycle runs → PLC asserts OperationComplete → auto-complete writes ProductionEvent + auto-move to Assembly Cell. Operator never scans Machining OUT.

- End-to-end integration check (uncoupled path): Same flow, but with CoupledDownstreamCellLocationId NULL → auto-complete writes ProductionEvent only; LOT stays at Machining Cell; operator uses Phase 4 Movement Scan to move it manually.

- End-to-end integration check (sublotting path): A whole LOT picked + renamed at a RequiresSubLotSplit=1 line → operator triggers Machining OUT → splits into two sub-LOTs routed to two destinations → LTT labels print → both sub-LOTs visible in their destination queues; genealogy shows the Split edges from the machined parent.

# Phase 6 — Assembly + MIP + Container Pack

Goal: Deliver the Assembly workflow (serialized lines with PLC/MIP handshake, non-serialized lines with operator-driven count entry), tray-level container closure with three peer methods (ByCount / ByWeight / ByVision per FDS-06-014), BOM-based material verification with supervisor override (UJ-09), per-Cell ConfirmationMethod resolver (UJ-17), HardwareInterlockBypassed flag capture (UJ-16), and atomic container completion claiming an AIM Shipper ID from the local pool (Phase 7 schema, claim path here per UJ-04).

Dependencies: Phase 1 (foundation), Phase 2 (LOT lifecycle + label print), Phase 3 (ProductionEvent + Reject), Phase 4 (Movement Scan for inbound lineside material; auto-coupled inbound from Phase 5 Machining), Phase 5 (machined LOTs auto-arrive). Phase 7’s AimShipperIdPool schema CREATEs in Phase 7 — Phase 6 consumes via _Claim proc; the pool is filled by Phase 7’s topup loop.

Status: Blocked on Phases 1–5 + Phase 7 schema CREATE (cross-phase dependency: Phase 6 calls AimShipperIdPool_Claim which lives in Phase 7’s migration). Sequencing: Phase 7 ships its schema CREATE before Phase 6 ships its container-close proc, even though Phase 7’s overall delivery follows Phase 6.

## Data Model Changes

Migration sql/migrations/versioned/0019_arc2_phase6_assembly.sql (next unclaimed).

New tables (Container family — anchored here, consumed across Phases 6 + 7):

- Lots.Container — header for a packaging unit. Columns: Id BIGINT PK, ItemId BIGINT FK → Parts.Item.Id, ContainerConfigId BIGINT FK → Parts.ContainerConfig.Id, CurrentLocationId BIGINT FK → Location.Location.Id, ContainerStatusCodeId BIGINT FK → Lots.ContainerStatusCode.Id, OpenedAt DATETIME2(3) NOT NULL DEFAULT SYSUTCDATETIME(), CompletedAt DATETIME2(3) NULL, CreatedByUserId BIGINT FK → AppUser.Id, RowVersion ROWVERSION. Filtered indexes per OI-35 B8: IX_Container_OpenByLocation (CurrentLocationId, OpenedAt) WHERE ContainerStatusCodeId IN (Open codes).

- Lots.ContainerTray — child of Container. Columns: Id BIGINT PK, ContainerId BIGINT FK → Container.Id, TrayPosition INT NOT NULL, PartsClosedCount INT NOT NULL DEFAULT 0, ClosedAt DATETIME2(3) NULL, ClosedByUserId BIGINT FK → AppUser.Id NULL, ClosureMethod NVARCHAR(20) NULL (ByCount/ByWeight/ByVision — captured from Parts.ContainerConfig.ClosureMethod at the moment of closure for audit). Filtered UNIQUE (ContainerId, TrayPosition).

- Lots.ContainerSerial — junction: serial numbers in container tray positions. Columns: Id BIGINT PK, ContainerId BIGINT FK → Container.Id, ContainerTrayId BIGINT FK → ContainerTray.Id NULL, SerializedPartId BIGINT FK → SerializedPart.Id, TrayPosition INT NULL, HardwareInterlockBypassed BIT NOT NULL DEFAULT 0 (UJ-16 Option A). Filtered indexes for serial lookups and per-Container drilldown.

- Lots.SerializedPart — the laser-etched part itself. Columns: Id BIGINT PK, SerialNumber NVARCHAR(50) UNIQUE, ItemId BIGINT FK → Parts.Item.Id, ProducingLotId BIGINT FK → Lots.Lot.Id, EtchedAt DATETIME2(3) NOT NULL, EtchedByUserId BIGINT FK → AppUser.Id. SerialNumber mints via Lots.IdentifierSequence_Next @Code='SerializedItem' per B15.

Seeds:

- Parts.OperationTemplate rows for assembly operations per Item — one set per serialized line (5G0 family) and one per non-serialized line (6B2, RPY, etc.). Final list confirmed during Phase 0 A5 walkthrough.

- Audit.LogEntityType rows: Container, ContainerTray, ContainerSerial, SerializedPart.

- Audit.LogEventType rows: ContainerOpened, TrayClosed, ContainerCompleted, ContainerSerialAdded, MaterialSubstituteOverride (UJ-09), WorkOrderCompletionConfirmed (FDS-06-028 / OI-16).

Tables used (existing + new): Lots.Lot, Lots.LotGenealogy (+ closure if B4), Lots.LotMovement, Workorder.ConsumptionEvent, Workorder.ProductionEvent, Workorder.RejectEvent, Parts.Bom, Parts.BomLine, Parts.ContainerConfig (ClosureMethod, TraysPerContainer, PartsPerTray), Parts.Item.MaxParts (lineside cap), Location.LocationAttribute (ConfirmationMethod, RequiresCompletionConfirm).

## Open Items Affecting This Phase

| Item | Status |
| --- | --- |
| OI-16 PLC CompletionConfirmed BIT + RequiresCompletionConfirm LocationAttribute | ✅ Closed. Auto-finish gate per FDS-06-028 reads PLC CompletionConfirmed BIT (belt-and-suspenders alongside count-crosses-target); per-Terminal RequiresCompletionConfirm LocationAttribute (seeded in Phase 1) toggles the operator UX between large “Confirm Completion” button and passive popup. |
| OI-33 AIM pool empty-pool hard-fail | 🔶 Pending Phase 0 customer validation. Default direction (current FDS-07-010a): hard-fail — Container_Complete rolls back on empty pool, line stops, operator sees error. Phase 6 ships against the default; if Phase 0 elects soft-fallback the close path needs redesign. |
| UJ-09 Material verification at scan-in | ✅ Closed (Option C). Strict BOM check at material scan-in; BOM-mismatch surfaces a supervisor AD-elevated one-shot override per FDS-04-007 + FDS-06-011 — substitution is logged (MaterialSubstituteOverride audit). |
| UJ-13 ContainerConfig.ClosureMethod | ✅ Closed. Per-Item via Parts.ContainerConfig.ClosureMethod — three peer values ByCount / ByWeight / ByVision per FDS-06-014. |
| UJ-16 HardwareInterlockBypassed | ✅ Closed (Option A). BIT column on Lots.ContainerSerial (created in this phase’s migration). |
| UJ-17 Vision vs barcode | ✅ Closed (Option A). ConfirmationMethod LocationAttribute on Cell (seeded Phase 1); the Confirmation Method Resolver embedded component reads it and renders the appropriate UX. |
| UJ-18 Print failure surfacing | ✅ Closed. Gateway-broadcast-with-session-filter per FDS-07-006b. The print-failure banner embedded component (cross-cutting) appears on every workstation view including Assembly. |
| OI-35 B5 materialization | If elected (Phase 0): ConsumptionEvent_Record updates Lot.TotalInProcess / InventoryAvailable for the consumed source LOT. |

## State & Workflow

### Serialized assembly line — PLC/MIP handshake

Serialized lines (e.g., 5G0 Front Cover) carry full PLC/MIP integration. The line auto-loads parts from the upstream Machining Cell (auto-moved via FDS-06-008 / Phase 5) and from staged lineside LOTs of consumable materials (e.g., PNA mounting pins). Per-piece operator interaction is minimal — the operator monitors and intervenes on errors.

Per-piece flow: 1. The assembly machine loads a casting from the upstream LOT, presses in the components per BOM, and the laser etches a serial number 5G0F-NNNNNN (minted from IdentifierSequence_Next @Code='SerializedItem' if the MES mints; otherwise the MES validates a PLC-supplied serial). 2. The PLC writes DataReady=1. The MES reads PartSN, validates uniqueness, writes PartValid=1 back. The PLC releases the part. 3. The MES writes a Lots.SerializedPart row + a Workorder.ConsumptionEvent (one per BOM component consumed) + a Lots.LotGenealogy row linking each consumed source LOT to the produced SerializedPart. 4. The part drops into a tray position. ContainerSerial row inserted with ContainerId, ContainerTrayId, TrayPosition, SerializedPartId. If HardwareInterlockEnable = false on the PLC at the moment of placement, ContainerSerial.HardwareInterlockBypassed = 1 (UJ-16). 5. When the tray’s PartsClosedCount reaches Parts.ContainerConfig.PartsPerTray, the tray closes — ContainerTray.ClosedAt set, ClosureMethod captured (ByVision for serialized lines — camera per-piece validation drove the count; PLC TrayFullFlag confirms). 6. When accumulated tray closes reach TraysPerContainer × PartsPerTray for the Container, the Container completes (see “Container completion” below).

### Non-serialized assembly line — operator-driven count

Non-serialized lines (e.g., 6B2 Cam Holder, RPY Assembly Sets) use OPC PartDisposition flags + operator-confirmed counts. No per-piece serial. Tray-level closure still applies — same three closure methods, same accumulation logic — but the tray gate is operator-driven (ByCount) or scale-driven (ByWeight).

Per-tray flow: 1. The operator runs the operation. As parts accumulate in a tray, the OPC PartDisposition tag indicates per-piece pass/fail (and the running good count, depending on line). 2. When the operator (ByCount) or scale (ByWeight) signals tray full, Perspective calls Lots.ContainerTray_Close. The proc validates the count matches PartsPerTray, sets ContainerTray.ClosedAt, captures ClosureMethod, increments the parent Container’s running parts count. 3. ConsumptionEvents fire per tray for the BOM components consumed (one ConsumptionEvent per BOM line per tray). 4. Same accumulation rule as serialized — Container completes when accumulatedClosedTrayParts ≥ TraysPerContainer × PartsPerTray.

### Tray-level closure — three peer ClosureMethod values (FDS-06-014)

Closure validation happens at the tray level, with the container as the accumulator. Parts.ContainerConfig.ClosureMethod selects the per-tray trigger:

- ByCount: operator confirms tray quantity at the Per-Tray Close screen (or the PLC asserts TrayFullFlag based on a count the operator entered upstream).

- ByWeight: OmniServer scale publishes the per-tray weight; PLC compares against TargetWeight configured on ContainerConfig and asserts TrayFullFlag at threshold.

- ByVision: camera validates each part (pass/fail per piece); PLC accumulates the validated count and asserts TrayFullFlag at PartsPerTray.

The MES reads TrayFullFlag (or accepts the operator’s ContainerTray_Close submit on ByCount lines), writes the tray-close row, and derives the container fill from accumulated tray closes — no separate ContainerFullFlag PLC tag is required.

### Container completion (atomic close + AIM pool claim + async print)

When the container’s accumulated parts reach the configured capacity, Perspective (or a Gateway script on PLC-driven lines) calls Lots.Container_Complete:

- Validate the container is Open and the accumulated count matches TraysPerContainer × PartsPerTray.

- AIM pool claim (UJ-04 + OI-33). Call Lots.AimShipperIdPool_Claim @PartNumber, @ContainerId — atomic FIFO claim from the local pool, sub-millisecond, never blocked on AIM. Empty-pool behavior is hard-fail per FDS-07-010a (default; OI-33 customer validation pending). On empty pool the proc raises a business-rule error; the surrounding transaction rolls back; the operator sees an error banner (“AIM pool exhausted — contact IT”); the line stops on this terminal until pool refills.

- On successful claim: insert Lots.ShippingLabel row with PrintedAt = NULL, AimShipperId = (claimed Id), TerminalLocationId, ContainerId, etc. Update Container.ContainerStatusCodeId to Complete, set CompletedAt.

- OI-16 / FDS-06-028 auto-finish gate. Read the PLC CompletionConfirmed BIT (belt-and-suspenders alongside count-target-crossing). If RequiresCompletionConfirm LocationAttribute on the Terminal is 1, Perspective also requires the operator to tap a large “Confirm Completion” button before the close commits; if 0 (or NULL), the close proceeds with a passive popup.

- All four steps above run inside a single atomic transaction — close, claim, ShippingLabel insert, status flip — sub-millisecond when the AIM pool is healthy.

- Async print dispatch (UJ-18 / FDS-07-006a). After commit, Perspective fires system.util.sendRequestAsync('mes', 'print-shipping-label', {ShippingLabelId}). The Gateway handler renders ZPL and dispatches to the Zebra at TerminalLocationId. Three retries × 2s gap inline within the handler. On success, update ShippingLabel.PrintedAt. On exhaustion, set PrintFailedAt — drives the Print Failure Banner via the Gateway-broadcast safety-sweep (Phase 7).

### BOM material verification at scan-in (UJ-09 — Option C)

Strict BOM check + supervisor AD-elevated one-shot override:

- The operator scans an inbound lineside LOT for consumption.

- Perspective calls Workorder.ConsumptionEvent_RecordWithBomCheck @SourceLotId, @ProducingLotId, @CellLocationId, .... The proc resolves the active BOM for the producing Item at this Cell and validates the source LOT’s Item is a child line.

- Strict match: if the source Item is on the BOM, ConsumptionEvent writes normally.

- Mismatch: the proc returns Status=0, Message='Source Item {X} is not a configured component for {ProducedItem} at this Cell.' Perspective shows a supervisor-override modal (per FDS-04-007).

- On supervisor AD authentication via AppUser_AuthenticateAd @ActionCode='MaterialSubstituteOverride', Perspective re-calls the proc with @OverrideAppUserId = (supervisor's Id), @OverrideAuthorized = 1. The proc accepts the consumption, writes the ConsumptionEvent, and writes a MaterialSubstituteOverride audit row capturing both the operator’s and supervisor’s user ids.

- The override is one-shot per consumption event — next scan re-runs the strict check.

### ConfirmationMethod per Cell (UJ-17 / FDS-10-013)

The Confirmation Method Resolver (cross-cutting embedded component) reads the ConfirmationMethod LocationAttribute (seeded Phase 1) on the operator’s active Cell:

- Vision: rely on PLC VisionPartNumber for part-identity confirmation.

- Barcode: require the operator to scan the part’s barcode.

- Both: both checks must agree; mismatches trigger the OI-04 line-stop / 10-fail-escalation flow (FDS-10-005..012).

### HardwareInterlockBypassed (UJ-16)

When the PLC asserts HardwareInterlockEnable = false (a valid bypass mode per the touchpoint agreement, not an error), parts proceed without MES serial validation. The corresponding ContainerSerial row carries HardwareInterlockBypassed = 1 so the audit trail records that the part entered the container without validation. This is per-piece granular — a single bypass in the middle of an otherwise-validated container shows up on exactly the affected ContainerSerial rows.

## API Layer (Named Queries → Stored Procedures)

| Procedure | Parameters | Notes | Output |
| --- | --- | --- | --- |
| Lots.Container_Open | @ItemId, @ContainerConfigId, @CellLocationId, @AppUserId, @TerminalLocationId | Opens a new container at a Cell. Returns Id. | Status, Message, NewId |
| Lots.ContainerTray_Close | @ContainerId, @TrayPosition INT, @PartsCount INT, @ClosureMethod NVARCHAR(20), @AppUserId, @TerminalLocationId | Validates count vs PartsPerTray, sets ClosedAt, captures ClosureMethod, increments parent Container’s running parts count. | Status, Message, NewId, ContainerAccumulatedParts INT |
| Lots.ContainerSerial_Add | @ContainerId, @ContainerTrayId NULL, @TrayPosition NULL, @SerializedPartId, @HardwareInterlockBypassed BIT, @AppUserId, @TerminalLocationId | Inserts the per-piece serial assignment to a tray position. | Status, Message, NewId |
| Lots.SerializedPart_Mint | @ItemId, @ProducingLotId, @AppUserId, @TerminalLocationId | Mints a new SerializedPart. Calls IdentifierSequence_Next @Code='SerializedItem'. | Status, Message, NewId, SerialNumber NVARCHAR(50) |
| Lots.Container_Complete | @ContainerId, @PlcCompletionConfirmed BIT, @OperatorConfirmed BIT, @AppUserId, @TerminalLocationId | Atomic close: validates accumulated count, claims AIM ID via AimShipperIdPool_Claim, inserts ShippingLabel row, flips status. Hard-fails on empty pool per FDS-07-010a (OI-33 pending). Reads RequiresCompletionConfirm on Terminal — if 1, requires @OperatorConfirmed=1. | Status, Message, ShippingLabelId BIGINT, AimShipperId NVARCHAR(50) |
| Workorder.ConsumptionEvent_RecordWithBomCheck | @SourceLotId, @ProducingLotId, @CellLocationId, @ConsumedPieceCount, @ContainerSerialId NULL, @OverrideAppUserId NULL, @OverrideAuthorized BIT = 0, @AppUserId, @TerminalLocationId | Strict BOM check; rejects on mismatch unless @OverrideAuthorized=1 (with @OverrideAppUserId from prior AppUser_AuthenticateAd @ActionCode='MaterialSubstituteOverride'). On override, writes the audit row. | Status, Message, NewId |

## Gateway Scripts

| Script | Purpose | Trigger | External | Audit |
| --- | --- | --- | --- | --- |
| AssemblyMipHandler (per serialized line) | PLC handshake — reads PartSN, writes PartValid, monitors HardwareInterlockEnable, DataReady, ContainerFullFlag (legacy — being deprecated by tray-level closure but supported during cutover for any line that still drives container-level), CompletionConfirmed. Calls ConsumptionEvent_RecordWithBomCheck + SerializedPart_Mint + ContainerSerial_Add. On tray-fill / container-fill thresholds calls ContainerTray_Close + Container_Complete. | PLC tag edges | PLC (TOPServer) | Per-call OperationLog via procs; InterfaceLog on every PLC read/write per B4 |
| NonSerializedLineHandler (per non-serialized line) | OPC PartDisposition reader → operator-confirmed count + scale-driven count for ByWeight lines. Calls ContainerTray_Close on tray-full edge. | PLC tag edge / OmniServer scale | PLC, OmniServer | InterfaceLog |
| ShippingLabelDispatcher | Receives print-shipping-label messages, renders ZPL, dispatches to Zebra at TerminalLocationId, retries 3× 2s, updates ShippingLabel.PrintedAt or PrintFailedAt. | Gateway message handler | Zebra socket | InterfaceLog per attempt |

## Perspective Views

| View | Purpose |
| --- | --- |
| Assembly Serialized (purpose-built top-level view) | Composes Per-Mutation Initials Field + Confirmation Method Resolver + Paused-LOT Indicator + Print Failure Banner. Read-mostly during normal operation (PLC drives most events); operator UX activates on errors, line-stops, supervisor overrides. The OI-16 “Confirm Completion” gesture button (when RequiresCompletionConfirm=1) renders here. |
| Assembly Non-Serialized (purpose-built top-level view) | Composes the same cross-cutting components + an operator-driven Per-Tray Close form (ByCount / ByWeight rendered per ConfirmationMethod). |
| Confirmation Method Resolver (cross-cutting embedded component) | Reads ConfirmationMethod LocationAttribute → renders Vision / Barcode / Both UX appropriate to the active Cell. Reusable across Assembly + any future view that does part-identity confirmation. |
| Print Failure Banner (cross-cutting embedded component) | Subscribes to print-failure-alert Gateway-broadcast messages, filters by session.custom.terminal.terminalLocationId, renders banner when PrintFailedAt IS NOT NULL AND BannerAcknowledgedAt IS NULL. Actions: Retry / Reprint / Acknowledge. |
| Material Substitute Override Modal (cross-cutting embedded component) | UJ-09 — supervisor AD-elevated one-shot override for BOM-mismatch consumption. |

## Test Coverage

New test suite at sql/tests/0019_PlantFloor_Assembly/:

| File | Covers |
| --- | --- |
| 010_Container_lifecycle.sql | Open → multi-tray accumulate → Complete; status transitions; CompletedAt set. |
| 020_ContainerTray_Close_methods.sql | ByCount / ByWeight / ByVision all close with ClosureMethod captured; mismatched count rejects. |
| 030_ContainerSerial_Add_with_bypass.sql | Insert with HardwareInterlockBypassed=1; multiple bypassed serials in one container; audit row captures the flag. |
| 040_Container_Complete_happy.sql | Healthy AIM pool → claim succeeds, ShippingLabel inserted, status flips; print message dispatched. |
| 050_Container_Complete_empty_pool_hard_fail.sql | Empty pool → atomic ROLLBACK; container stays Open; operator-facing error message. |
| 060_Container_Complete_with_completion_confirm.sql | RequiresCompletionConfirm=1 + @OperatorConfirmed=0 rejects; =1 succeeds. |
| 070_BomCheck_strict.sql | Source on BOM succeeds; off-BOM rejects with FDS-06-011 message. |
| 080_BomCheck_supervisor_override.sql | Off-BOM + valid supervisor @OverrideAppUserId + @OverrideAuthorized=1 succeeds; audit row captures both AppUserIds. |
| 090_SerializedPart_Mint.sql | Mints via IdentifierSequence_Next; SerialNumber matches MESI{0:D7} format; rolls back on unrelated transaction failure does not burn the counter (per B6 row-locked-update model — note: if Phase 0 elected SEQUENCE, the counter does burn, accepted tradeoff). |

Target: 100–135 passing tests in suite 0019.

## Phase 6 complete when

- Migration 0019_arc2_phase6_assembly.sql applied. Container family CREATEd. Seeds in place.

- All Phase 6 procs delivered.

- All tests in sql/tests/0019_PlantFloor_Assembly/ pass.

- Perspective Assembly Serialized + Assembly Non-Serialized views implemented composing all cross-cutting components.

- Gateway AssemblyMipHandler per serialized line implemented and tested against PLC simulator + dev 5G0 MIP.

- Gateway ShippingLabelDispatcher implemented; 3-retry mechanism tested against Zebra emulator failures; PrintFailedAt set correctly on exhaustion.

- End-to-end integration check (serialized line): machined LOT auto-arrives from Phase 5 → assembly cycle consumes via PLC handshake → SerializedPart minted, ContainerSerial inserted with bypass=0 (or =1 on a deliberate bypass test) → tray closes via ByVision → container accumulates → Container_Complete claims AIM ID, inserts ShippingLabel, flips status → ZPL prints at the closing terminal’s Zebra.

- End-to-end integration check (non-serialized line): machined LOT auto-arrives → operator records per-tray close (ByCount or ByWeight) → container accumulates → Container_Complete + AIM claim + print as above.

- Empty-pool fail check: drain the AIM pool → attempt Container_Complete → expect business-rule error + ROLLBACK + operator banner.

# Phase 7 — Hold + Sort Cage + Shipping + AIM Pool Lifecycle

Goal: Deliver Hold lifecycle (place / release on LOTs and Containers — proc-enforced via FDS-08-007a), Sort Cage re-containerization with ContainerSerialHistory (UJ-05 default direction — update-in-place), Shipping Dock truck-out (every container scanned must be Complete + AIM-valid + non-Hold), AIM Shipper ID pool topup loop + tier alarms + config CRUD, and the Print Failure Safety Sweep timer.

Dependencies: Phase 1 (foundation), Phase 2 (LOT lifecycle), Phase 6 (Container family — Phase 6’s migration CREATEs Container + ContainerTray + ContainerSerial + SerializedPart; Phase 7’s migration adds the Hold + AIM pool tables and the SortCage history table that consume them).

Status: Blocked on Phase 6 schema CREATE. Sequencing note: Phase 7’s AimShipperIdPool_Claim proc is consumed by Phase 6’s Container_Complete — the pool tables CREATE in Phase 7’s migration; Phase 6 ships the consumer last (in the same delivery cycle).

## Data Model Changes

Migration sql/migrations/versioned/0020_arc2_phase7_hold_sort_shipping_aim.sql (next unclaimed).

New tables:

- Quality.HoldEvent (if not already in Phase 1 — confirm during Phase 0 scoping). Columns per Data Model v1.9l §5: Id, LotId NULL FK → Lots.Lot.Id, ContainerId NULL FK → Lots.Container.Id, HoldTypeCodeId BIGINT FK → Quality.HoldTypeCode.Id, Reason NVARCHAR(500), PlacedByUserId BIGINT FK → AppUser.Id, PlacedAt DATETIME2(3), ReleasedByUserId BIGINT FK → AppUser.Id NULL, ReleasedAt DATETIME2(3) NULL. Filtered UNIQUE for at-most-one-open per (LotId) and (ContainerId) per B3.

- Lots.AimShipperIdPool (per Data Model v1.9h / UJ-04). Columns: Id, AimShipperId NVARCHAR(50) UNIQUE, PartNumber NVARCHAR(50) (AIM IDs are fetched per-part-number), FetchedAt, FetchedInterfaceLogId BIGINT FK → Audit.InterfaceLog.Id, ConsumedAt NULL, ConsumedByContainerId NULL FK → Lots.Container.Id, ConsumedByUserId NULL FK → AppUser.Id. Filtered index IX_AimShipperIdPool_AvailableByPart (PartNumber, FetchedAt) WHERE ConsumedAt IS NULL — drives the FIFO-by-part-number claim.

- Lots.AimPoolConfig (per Data Model v1.9h). Single-row table holding configurable thresholds: TargetBufferDepth INT DEFAULT 50, TopupThreshold INT DEFAULT 30, AlarmWarningDepth INT DEFAULT 20, AlarmCriticalDepth INT DEFAULT 10. CHECK (Id = 1) enforces single-row.

- Lots.ContainerSerialHistory (UJ-05 default direction — update-in-place). Columns: Id, ContainerSerialId BIGINT FK → ContainerSerial.Id, OldContainerId BIGINT FK → Container.Id, NewContainerId BIGINT FK → Container.Id, OldTrayPosition INT NULL, NewTrayPosition INT NULL, MigrationReasonCode NVARCHAR(50) (SortCage, Repack, RangeAdjustment), MigratedAt DATETIME2(3), MigratedByUserId BIGINT FK → AppUser.Id. Filtered index for per-SerializedPart history walk.

Seeds:

- Quality.HoldTypeCode: CustomerComplaint, QualityIssue, EngineeringHold, ProductionHold, ContainerHold. Final list confirmed Phase 0 A7 walkthrough alongside label-template scope.

- Lots.AimPoolConfig initial single row with default thresholds.

- Audit.LogEntityType rows: HoldEvent, AimShipperIdPool, AimPoolConfig, ContainerSerialHistory.

- Audit.LogEventType rows: HoldPlaced, HoldReleased, AimShipperIdClaimed, AimShipperIdToppedUp, AimPoolWarningAlarmFired, AimPoolCriticalAlarmFired, ContainerSerialMigrated, ShippingLabelVoided, ContainerShipped, PrintFailureSafetySweepRecovered.

Tables used (existing): all Phase 6 Container family, Lots.Lot, Lots.LotStatusHistory, Lots.LotStatusCode (BlocksProduction flag — Hold transitions a LOT to a status with BlocksProduction=1), Lots.ShippingLabel (Phase 6).

## Open Items Affecting This Phase

| Item | Status |
| --- | --- |
| OI-22 Hold Management screen | ✅ Closed. Dedicated top-level Perspective view (FDS-08-007a). |
| UJ-04 AIM pool design lock | ✅ Closed (2026-04-27). Pool model in this phase — sync FIFO claim by part number + Gateway-script-async topup loop + tier alarms (warning/critical/exhausted). |
| OI-33 AIM pool empty-pool hard-fail | 🔶 Pending Phase 0 customer validation. Default direction (current FDS-07-010a): hard-fail. Phase 7’s _Claim proc raises a business-rule error on empty pool (consumed by Phase 6’s atomic close which ROLLBACKs). |
| A6 Honda AIM Hold/Update contract | Pending Phase 0 — PlaceOnHold, ReleaseFromHold, UpdateAim signatures + error recovery for the Phase 7 hold + Sort Cage workflows. |
| A7 Label template scope | Pending Phase 0 — confirms Container / LOT / ContainerHold templates + any new (Sort Cage, Hold, Void). Couples to S-09 in the Seeding Registry. |
| UJ-05 Sort Cage serial migration | ⬜ Open (default direction committed). Update-in-place + Lots.ContainerSerialHistory is built; awaits MPP Quality + Honda compliance affirmation. If MPP rejects, Phase 7 reverts to void-and-recreate (no history table). |
| UJ-18 Print failure surfacing | ✅ Closed. Phase 7 hosts the safety-sweep timer (5-min cadence) + stranded-prints alarm at >5 (FDS-07-006b). |

## State & Workflow

### Hold placement (multi-LOT or multi-Container)

The Hold Management top-level view exposes filterable lists of open LOTs and open Containers. The supervisor selects one or many entries and places a hold. Required: AD elevation per FDS-04-007 (@ActionCode='HoldPlace').

Quality.Hold_Place sequence: 1. Validate AD elevation (caller already authenticated; @AppUserId is the elevated user). 2. For each LotId or ContainerId in the batch: call Lot_AssertNotBlocked (or container equivalent — a hold cannot be placed on an already-held entity per B3). 3. Insert HoldEvent row(s) with HoldTypeCodeId, Reason, PlacedByUserId, PlacedAt = SYSUTCDATETIME(). 4. For LOTs: transition Lot.LotStatusId → Hold via Lot_UpdateStatus (the new status carries BlocksProduction=1 — every downstream proc fails its Lot_AssertNotBlocked check). 5. For Containers in the batch that are already shipped (ShippingLabel.PrintedAt IS NOT NULL, ContainerStatusCode='Complete'): also call AIM PlaceOnHold per FDS-07-008 — Gateway-script-async via system.util.sendRequestAsync('mes', 'aim-place-on-hold', {ShipperId}). The Gateway script handles AIM signature + error recovery per Phase 0 A6. 6. Audit HoldPlaced per row.

### Hold release

Same pattern in reverse. Quality.Hold_Release @HoldEventId, @ReleaseRemarks, @AppUserId, @TerminalLocationId: 1. Validate the HoldEvent is open (ReleasedAt IS NULL). 2. Update the row: ReleasedByUserId, ReleasedAt. 3. For LOTs: transition LotStatusId back to its prior non-Hold status (read from LotStatusHistory). 4. For Containers that were on AIM hold: Gateway-script-async aim-release-from-hold. 5. Audit HoldReleased.

### Sort Cage re-containerization (UJ-05 default — update-in-place)

A held Container goes to the Sort Cage. Operators unpack, re-inspect each part, and re-pack into new Containers. The migration writes per-Serial migration rows to Lots.ContainerSerialHistory and updates ContainerSerial.ContainerId / TrayPosition to the new container in the same transaction.

Lots.SortCage_MigrateSerial @ContainerSerialId, @NewContainerId, @NewTrayPosition, @MigrationReasonCode='SortCage', @AppUserId, @TerminalLocationId: 1. Validate the source container is held; the destination container is open + at the Sort Cage location. 2. Insert ContainerSerialHistory row capturing Old* and New* values + reason. 3. Update ContainerSerial.ContainerId and ContainerSerial.TrayPosition in place. 4. The genealogy + ShippingLabel chains remain valid — backward trace from any serial number lands on the producing LOT regardless of container migrations. 5. When the destination Container reaches its capacity, normal Container_Complete runs (claims a fresh AIM ID; the old shipping label is voided via ShippingLabel_Void). 6. Audit ContainerSerialMigrated.

The Sort Cage Workflow Perspective view uses Flex Repeater + Embedded View for the per-serial migration rows — one row per serial in the held source container, each row showing serial number + old position + new container/tray dropdowns + migrate button.

### Shipping (truck-out)

The Shipping Dock view scans each Container’s Shipping Label as the truck loads. Per scan: 1. Validate ContainerStatusCode='Complete', no open hold (HoldEvent for this Container with ReleasedAt IS NULL rejects), ShippingLabel.IsVoid=0. 2. Update Container.CurrentLocationId → Shipping Dock (or Shipped location, depending on Phase 0 plant model). 3. Audit ContainerShipped.

A bulk variant accepts a JSON list of ShippingLabel Ids for a manifest-level scan.

### AIM Shipper ID pool — topup loop + alarms

The AIM Shipper ID pool is filled by a Gateway timer running every ~30 seconds (per FDS-07-010). The timer: 1. Calls Lots.AimShipperIdPool_GetDepth per Part Number — returns count of un-consumed IDs. 2. For each Part Number where depth < TopupThreshold: calls AIM GetNextNumber(@PartNumber) repeatedly via Gateway-script-async until depth reaches TargetBufferDepth. Each fetched ID writes an Audit.InterfaceLog row + a row in AimShipperIdPool. 3. Tier alarms (FDS-07-010b): - Depth ≤ AlarmWarningDepth → supervisor wallboard tile (no email/page). - Depth ≤ AlarmCriticalDepth → supervisor alarm + IT notification. - Depth = 0 → empty-pool state; subsequent _Claim calls hard-fail per OI-33 (pending validation). 4. Each alarm fires at most once per crossing (rising-edge detection); a separate clear-alarm fires when depth recovers above the threshold.

AimPoolConfig thresholds are exposed via the Configuration Tool (Phase 7 admin view) — Lots.AimPoolConfig_Get / _Update.

### Print Failure Safety Sweep (FDS-07-006b)

A Gateway timer runs every 5 minutes and queries:

SELECT * FROM Lots.ShippingLabel
WHERE PrintedAt IS NULL AND PrintFailedAt IS NULL
  AND CreatedAt < DATEADD(SECOND, -60, SYSUTCDATETIME())

These are stranded prints (Gateway restart between Container_Complete commit and message dispatch). For each, fire print-shipping-label again. If the same row strands twice in a row, write PrintFailedAt.

If the sweep finds more than 5 stranded labels at once, fire a supervisor alarm + IT notification — the Gateway likely needs investigation.

## API Layer

### Hold management

| Procedure | Parameters | Notes | Output |
| --- | --- | --- | --- |
| Quality.Hold_Place | @LotIdsJson, @ContainerIdsJson, @HoldTypeCodeId, @Reason, @AppUserId (elevated), @TerminalLocationId | Batch-place hold on N LOTs and/or N Containers. Per-row B3 enforcement. | Multi-row: header + per-row EntityType, EntityId, HoldEventId, Status |
| Quality.Hold_Release | @HoldEventId, @ReleaseRemarks, @AppUserId (elevated), @TerminalLocationId | Releases a single open hold. | Status, Message |
| Quality.Hold_GetOpenByLot | @LotId | Returns the open hold if any. | Single row or empty |
| Quality.Hold_GetOpenByContainer | @ContainerId | Same for containers. | Single row or empty |

### Container state transitions (Phase 7 additions)

| Procedure | Parameters | Notes | Output |
| --- | --- | --- | --- |
| Lots.Container_Ship | @ShippingLabelId, @AppUserId, @TerminalLocationId | Validates Complete + no hold + non-void; updates Container.CurrentLocationId to Shipping Dock; audits. | Status, Message |
| Lots.ShippingLabel_Void | @ShippingLabelId, @VoidReason, @AppUserId (elevated), @TerminalLocationId | Marks IsVoid=1, sets VoidedAt + VoidedByUserId. Used during Sort Cage re-pack. | Status, Message |
| Lots.ShippingLabel_Reprint | @ShippingLabelId, @PrintReasonCode, @AppUserId, @TerminalLocationId | Inserts a new ShippingLabel row (label rows are append-only) with Initial=0 and PrintReasonCode. | Status, Message, NewId |
| Lots.SortCage_MigrateSerial | @ContainerSerialId, @NewContainerId, @NewTrayPosition NULL, @MigrationReasonCode, @AppUserId, @TerminalLocationId | Inserts ContainerSerialHistory row + updates ContainerSerial in place. | Status, Message, NewHistoryId |

### AIM pool

| Procedure | Parameters | Notes | Output |
| --- | --- | --- | --- |
| Lots.AimShipperIdPool_Claim | @PartNumber, @ContainerId, @AppUserId | Atomic FIFO claim by Part Number. Hard-fails on empty pool (OI-33 default). Called by Phase 6’s Container_Complete. | Status, Message, AimShipperId NVARCHAR(50) |
| Lots.AimShipperIdPool_Topup | @PartNumber, @AimShipperId NVARCHAR(50), @FetchedInterfaceLogId BIGINT | Inserts a fetched row into the pool. Called by the Gateway topup script. | Status, Message, NewId |
| Lots.AimShipperIdPool_GetDepth | @PartNumber NULL | Returns un-consumed depth, optionally filtered by Part Number. | Rowset: (PartNumber, Depth) |
| Lots.AimShipperIdPool_GetByContainer | @ContainerId | Returns the AIM ID assigned to a container. | Single row |
| Lots.AimPoolConfig_Get | (none) | Returns the single config row. | Single row |
| Lots.AimPoolConfig_Update | @TargetBufferDepth, @TopupThreshold, @AlarmWarningDepth, @AlarmCriticalDepth, @AppUserId (elevated) | Updates the single config row. ConfigLog audit. | Status, Message |

## Gateway Scripts

| Script | Purpose | Trigger | External | Audit |
| --- | --- | --- | --- | --- |
| AimPoolTopup | Every ~30s: per Part Number, call _GetDepth; if below TopupThreshold, call AIM GetNextNumber(@PartNumber) repeatedly until TargetBufferDepth reached. Each fetch writes InterfaceLog + _Topup row. | Gateway timer (30s) | AIM HTTP/SOAP | InterfaceLog per call |
| AimPoolAlarmMonitor | Every ~60s: read pool depth per Part Number, compare to thresholds. Fire wallboard / supervisor alarm / IT notification on rising-edge crossings. Clear on falling-edge recovery. | Gateway timer (60s) | — | OperationLog on alarm fire / clear |
| AimHoldHandler | Receives aim-place-on-hold and aim-release-from-hold messages. Calls AIM HTTP per Phase 0 A6 contract. Retries per UJ-18 retry policy on transient failures; logs final state. | Gateway message handler | AIM HTTP/SOAP | InterfaceLog per call |
| AimUpdateHandler | Receives aim-update messages (Sort Cage re-pack with new serials per FRS Appendix L). Same retry pattern. | Gateway message handler | AIM HTTP/SOAP | InterfaceLog |
| PrintFailureSafetySweep | Every 5 min: query stranded ShippingLabel rows; re-fire print-shipping-label; mark PrintFailedAt on second strand; alarm if count > 5. | Gateway timer (5 min) | — | OperationLog on recovery; supervisor alarm on count > 5 |
| PrintFailureBroadcaster | Every 5s: query failed prints (PrintFailedAt IS NOT NULL AND BannerAcknowledgedAt IS NULL); fire system.util.sendMessage('mes', 'print-failure-alert', {...}) for each. Perspective sessions filter by their own TerminalLocationId. | Gateway timer (5s) | — | — (read-only broadcast) |

## Perspective Views

| View | Purpose |
| --- | --- |
| Hold Management (purpose-built top-level view) | Filterable lists of open LOTs + open Containers; Flex Repeater for each list; multi-select; AD-elevation modal for Hold_Place / Hold_Release. Couples to FDS-08-007a. |
| Sort Cage Workflow (purpose-built top-level view) | Held source Container shown at top; Flex Repeater per ContainerSerial in the source — each entity is the cross-cutting Cell-Selector-Repeater-Entity adapted for “destination Container + tray position selection.” Bulk-migrate button submits N SortCage_MigrateSerial calls in sequence. |
| Shipping Dock (purpose-built top-level view) | Scan-to-ship; per-scan validates Complete + non-Hold + non-Void; bulk manifest-scan variant. |
| AIM Pool Configuration (admin top-level view) | Read + Update of the single AimPoolConfig row. AD-elevated. Configuration Tool surface, not operator-facing. |
| AIM Pool Wallboard Tile (cross-cutting embedded component) | Renders pool depth + warning/critical state on supervisor dashboards. |
| Print Failure Banner (cross-cutting embedded component, defined Phase 6) | Same component used here; the safety-sweep + broadcaster Gateway scripts produce the events it consumes. |

## Test Coverage

New test suite at sql/tests/0020_PlantFloor_Hold_Sort_Shipping_Aim/:

| File | Covers |
| --- | --- |
| 010_Hold_Place_release.sql | Single-LOT and batch-LOT placement; double-place rejects per B3; release transitions LotStatus correctly; multi-Container batch with mixed pre-shipped (AIM hold path) and not-shipped. |
| 020_SortCage_MigrateSerial.sql | Update-in-place migration writes history row + updates ContainerSerial; multiple serials per source container; deprecated/closed source container handling. |
| 030_Container_Ship.sql | Complete + non-Hold + non-Void succeeds; held container rejects; void label rejects. |
| 040_AimShipperIdPool_Claim.sql | Healthy pool → FIFO order; empty pool → hard-fail per OI-33; per-Part-Number isolation (Part A claim doesn’t draw from Part B’s depth). |
| 050_AimShipperIdPool_Topup.sql | Insert respects UNIQUE; FetchedInterfaceLogId provenance; concurrent topups don’t double-insert. |
| 060_AimPool_alarms.sql | Rising-edge detection at Warning + Critical + Exhausted; clearing alarms on recovery. |
| 070_PrintFailure_safety_sweep.sql | Stranded row recovered on first sweep; double-strand sets PrintFailedAt; > 5 stranded triggers alarm. |
| 080_ShippingLabel_Void_Reprint.sql | Void marks IsVoid + VoidedAt; Reprint inserts new row with PrintReasonCode; original row unchanged. |

Target: 90–120 passing tests in suite 0020.

## Phase 7 complete when

- Migration 0020_arc2_phase7_hold_sort_shipping_aim.sql applied. New tables CREATEd. Seeds in place.

- All Phase 7 procs delivered.

- All tests in sql/tests/0020_PlantFloor_Hold_Sort_Shipping_Aim/ pass.

- Perspective views (Hold Management, Sort Cage Workflow, Shipping Dock, AIM Pool Config) implemented.

- All five Gateway scripts (Topup, AlarmMonitor, AimHoldHandler, AimUpdateHandler, PrintFailureSafetySweep, PrintFailureBroadcaster) implemented and tested.

- End-to-end integration check (hold + Sort Cage + reship): complete a Container in Phase 6 → place hold via Hold Management → AIM PlaceOnHold logs to InterfaceLog → operator at Sort Cage migrates serials to a new Container via Flex Repeater → original ShippingLabel voided → new Container completes + new AIM ID claimed + new ShippingLabel printed → AimUpdate logs to InterfaceLog → ship the new Container.

- End-to-end integration check (pool exhaustion): drain pool to zero → Container_Complete attempt hard-fails → operator banner → topup script refills → retry succeeds.

- End-to-end integration check (stranded print recovery): kill Gateway between Container_Complete commit and print dispatch → safety sweep recovers and dispatches.

- B10 convention rewritten with the chosen UJ-05 final pattern (default direction landed; reverts to void-and-recreate if MPP rejects).

# Phase 8 — Downtime + Shift Boundary (Parallel Track)

Goal: Deliver PLC-driven and manual downtime entry, the FDS-09-013 end-of-shift time-entry workflow (single submission, shift-schedule durations — no minute adjustments), the FDS-09-015 shift-end summary screen, the supervisor dashboard, and the Shift_End semantics that leave open events open across boundaries (UJ-10 Option D / OI-03).

Dependencies: Phase 1 (Shift_Start / Shift_End procs + ShiftBoundaryTicker Gateway script). Independent of Phases 2–7 — runs in parallel as soon as Phase 1 lands.

Status: Blocked on Phase 1.

## Data Model Changes

Migration sql/migrations/versioned/0021_arc2_phase8_downtime_shift.sql (next unclaimed).

- Oee.DowntimeEvent — CREATE per Data Model v1.9l §6 if not already in Phase 1: Id, LocationId BIGINT FK → Location.Location.Id, DowntimeReasonCodeId BIGINT FK → DowntimeReasonCode.Id NULL (per B7 — late-binding reason codes), ShiftId BIGINT FK → Oee.Shift.Id NULL, StartedAt, EndedAt NULL, DowntimeSourceCodeId BIGINT FK → DowntimeSourceCode.Id, AppUserId BIGINT FK → AppUser.Id NULL, ShotCount INT NULL (UJ-14 — warm-up shots when ReasonType=Setup), Remarks NVARCHAR(500) NULL, CreatedAt. Filtered UNIQUE for at-most-one-open per (LocationId) per B3.

- Seed Audit.LogEventType rows: DowntimeStarted, DowntimeEnded, DowntimeReasonAssigned, EndOfShiftSubmitted, ShiftHandoverAcknowledged.

Tables used: Oee.Shift, Oee.ShiftSchedule, Oee.DowntimeEvent, Oee.DowntimeReasonCode, Oee.DowntimeReasonType, Oee.DowntimeSourceCode, Lots.PauseEvent (read at shift end summary), Lots.LotMovement + v_LotDerivedQuantities (read at shift end summary).

## Open Items Affecting This Phase

| Item | Status |
| --- | --- |
| UJ-10 Shift boundary handling | ✅ Closed (Option D). Events span boundaries naturally — no auto-close at Shift_End; the shift-end summary screen surfaces open events for operator awareness. |
| OI-03 Shift runtime adjustments | ✅ Closed. Availability derived from event durations summed against the shift window — no minute-level adjustments. |
| UJ-14 Warm-up shots | ✅ Closed (Option A). DowntimeEvent.ShotCount only — no ProductionEventValue.WarmupShotCount. |
| A4 ShotCount semantics | Pending Phase 0 — affects how ProductionEvent.ShotCount is interpreted; orthogonal to DowntimeEvent.ShotCount (warm-up). |

## State & Workflow

### Manual downtime entry

The Downtime Entry top-level view exposes a list of currently-open downtime events at the operator’s Cell context (or supervisor’s selected scope). The operator can:

- Start a new downtime event: select machine, optionally enter reason code immediately (or leave for late-binding per B7), submit. Oee.DowntimeEvent_Start @LocationId, @DowntimeReasonCodeId NULL, @DowntimeSourceCodeId='Operator', @ShotCount NULL, @AppUserId, @TerminalLocationId.

- End an open event: scan or pick the open event, optionally add remarks, submit. Oee.DowntimeEvent_End @DowntimeEventId, @Remarks NULL, @AppUserId, @TerminalLocationId.

- Assign a reason code to an existing open event (when the PLC opened it without a reason): Oee.DowntimeReasonCode_Assign @DowntimeEventId, @DowntimeReasonCodeId, @AppUserId, @TerminalLocationId. Per B7, this proc refuses to overwrite an already-assigned reason — supervisors correct via other means.

### PLC-driven downtime

The Gateway script DowntimePlcWatcher (per machine) watches PLC stop/run edges. On stop edge: opens a DowntimeEvent with DowntimeSourceCode='PLC' and NULL reason. On run edge: closes the open event with EndedAt = SYSUTCDATETIME(). Operator-facing follow-up assigns the reason later via the manual entry view above.

### End-of-shift time entry (FDS-09-013)

About 15 minutes before the operator’s shift end (window: -15 min to +15 min around Oee.Shift.ScheduledEnd), Perspective surfaces the End-of-Shift Time Entry control on the operator’s terminal. Two UX paths per terminal mode:

- Dedicated terminal: single button — “Submit shift time entry.” Tap once. Submits using shift-schedule defaults — lunch + breaks per the operator’s Oee.ShiftSchedule.LunchMinutes / break configuration. No operator-entered durations.

- Shared terminal: form — initials + time category (Regular default; OT / DoubleOT / etc. per shift-schedule definition) + lunch yes/no + breaks selected (from a checkbox list of breaks defined on the shift schedule). Submit.

Oee.EndOfShiftEntry_Submit @ShiftId, @TimeCategoryCode, @LunchTaken BIT, @BreaksSelectedJson, @AppUserId, @TerminalLocationId: 1. Validate the shift is open (Oee.Shift.ActualEnd IS NULL) and @AppUserId is the operator on this shift. 2. For each selected lunch + break: insert a DowntimeEvent row with StartedAt and EndedAt populated from the shift schedule’s configured break window, DowntimeReasonCodeId set to the appropriate Lunch / Break reason, DowntimeSourceCode='Operator'. No operator-entered durations. 3. Audit EndOfShiftSubmitted.

There is no +30 / +10 / +110 minute adjustment anywhere — runtime is derived from event durations, not entered.

### Shift_End — open events stay open (UJ-10 Option D)

Oee.Shift_End (Phase 1) only updates the Oee.Shift.ActualEnd column. It does not auto-close any open DowntimeEvent, Lots.PauseEvent, or Quality.HoldEvent rows. Open events span shift boundaries naturally — the incoming shift’s operator closes them when the machine resumes (per FDS-09-010 + OI-03).

### Shift-end summary screen (FDS-09-015)

When the operator submits the End-of-Shift Time Entry (Dedicated single-button or Shared form), Perspective navigates to the Shift-end Summary view. The view is read-only and surfaces three lists for handover awareness:

- Open downtime events at the operator’s Cell — DowntimeEvent rows with EndedAt IS NULL and LocationId matching.

- Open paused LOTs at the operator’s Cell — LotPause_GetByLocation @LocationId.

- In-process LOTs at the operator’s Cell — read of Lots.Lot filtered by CurrentLocationId = operator’s Cell, joined to Lots.v_LotDerivedQuantities for header counts.

Operator-acknowledgement (a button at the bottom) writes ShiftHandoverAcknowledged to Audit.OperationLog. Acknowledgement is optional — the Submit step on the End-of-Shift Time Entry already commits the shift-time data; Acknowledge just confirms the operator reviewed the open-event lists.

Performance. The Shift-end Summary’s three lists scale with the operator’s Cell scope. The Lots.LotMovement recommended index (ToLocationId, MovedAt DESC) covers the in-process LOTs query. Per OI-35 architectural decisions, this index lives in the Phase 1 migration alongside the LotMovement table CREATE.

### Supervisor dashboard

The Supervisor Dashboard top-level view aggregates across multiple Cells (parent Area or WorkCenter scope). Surfaces: - Open downtime events with reason / no-reason breakdown (couples to B7 — unclassified downtime is a triage signal). - Open paused LOTs by Cell. - Shift availability vs target — derived from event durations per OI-03. - AIM pool depth per Part Number (couples to Phase 7’s AIM Pool Wallboard Tile). - Print failure stranded count (couples to Phase 6/7 Print Failure Banner).

## API Layer

| Procedure | Parameters | Notes | Output |
| --- | --- | --- | --- |
| Oee.DowntimeEvent_Start | @LocationId, @DowntimeReasonCodeId NULL, @DowntimeSourceCodeId, @ShotCount NULL, @AppUserId, @TerminalLocationId | Inserts a new event. Per B3, rejects if open event exists for this Location. | Status, Message, NewId |
| Oee.DowntimeEvent_End | @DowntimeEventId, @Remarks NULL, @AppUserId, @TerminalLocationId | Closes the event. Rejects if already closed. | Status, Message |
| Oee.DowntimeReasonCode_Assign | @DowntimeEventId, @DowntimeReasonCodeId, @AppUserId, @TerminalLocationId | Late-binding reason assignment. Refuses overwrite (B7). | Status, Message |
| Oee.EndOfShiftEntry_Submit | @ShiftId, @TimeCategoryCode, @LunchTaken BIT, @BreaksSelectedJson, @AppUserId, @TerminalLocationId | Per FDS-09-013 — writes DowntimeEvent rows for each selected lunch/break with shift-schedule durations. | Status, Message, EventCountInserted INT |
| Oee.Shift_GetEndOfShiftSummary | @ShiftId, @CellLocationId NULL (defaults to terminal’s active Cell) | Returns the three lists (open downtime, open pauses, in-process LOTs). | Multi-row: open-downtime rows + open-pause rows + in-process-LOT rows |

## Gateway Scripts

| Script | Purpose | Trigger | External | Audit |
| --- | --- | --- | --- | --- |
| DowntimePlcWatcher (per machine) | Watches PLC stop/run edges. Opens DowntimeEvent on stop with NULL reason; closes on run. | PLC tag edge | PLC (TOPServer) | OperationLog via the procs |
| EndOfShiftWindowTrigger (Perspective view-side) | Surfaces the End-of-Shift Time Entry control 15 min before scheduled shift end. View-side timer; no DB state. | Perspective view tick | — | — |

## Perspective Views

| View | Purpose |
| --- | --- |
| Downtime Entry (purpose-built top-level view) | List of open events at scope; Flex Repeater for the list (per-event embedded view: machine, source, reason-or-NULL, started-at, “End” / “Assign Reason” buttons); Start-new form. |
| End-of-Shift Time Entry (purpose-built top-level view) | Two UX paths via session.custom.terminal.terminalMode: Dedicated → single button submit; Shared → form (initials + time category + lunch/break selection). Routes to Shift-end Summary on success. |
| Shift-end Summary (purpose-built top-level view, FDS-09-015) | Three Flex Repeaters — open downtime, open paused LOTs, in-process LOTs at the operator’s Cell. Read-only. Acknowledge button writes ShiftHandoverAcknowledged audit row. |
| Supervisor Dashboard (purpose-built top-level view) | Composes wallboard tiles — DowntimeOpenSummary, PausedLotsSummary, ShiftAvailabilityTile, AimPoolWallboardTile, PrintFailureStrandedTile. |

## Test Coverage

New test suite at sql/tests/0021_PlantFloor_Downtime_Shift/:

| File | Covers |
| --- | --- |
| 010_DowntimeEvent_lifecycle.sql | Start + End; double-start rejects per B3; end-with-no-open rejects. |
| 020_DowntimeReasonCode_Assign.sql | Late-binding assignment succeeds; overwrite rejects per B7. |
| 030_DowntimeEvent_PLC_pattern.sql | PLC source code; NULL reason at start; reason assigned later. |
| 040_DowntimeEvent_warmup_shotcount.sql | UJ-14 — DowntimeEvent.ShotCount on Setup-type events. |
| 050_EndOfShiftEntry_Submit.sql | Lunch + selected breaks insert correct DowntimeEvent rows with shift-schedule durations; no operator-entered durations accepted; multiple submissions rejected. |
| 060_Shift_GetEndOfShiftSummary.sql | Three lists return correctly; in-process LOTs query uses the LotMovement (ToLocationId, MovedAt DESC) index. |
| 070_OpenEvents_span_boundary.sql | Shift_End leaves open DowntimeEvent / PauseEvent / HoldEvent rows untouched per UJ-10 / OI-03. |

Target: 60–80 passing tests in suite 0021.

## Phase 8 complete when

- Migration 0021_arc2_phase8_downtime_shift.sql applied. DowntimeEvent CREATEd if not already. Seeds in place.

- All Phase 8 procs delivered.

- All tests in sql/tests/0021_PlantFloor_Downtime_Shift/ pass.

- Perspective views (Downtime Entry, End-of-Shift Time Entry, Shift-end Summary, Supervisor Dashboard) implemented.

- Gateway DowntimePlcWatcher per machine implemented and tested against PLC simulator.

- End-to-end integration check: PLC opens a downtime event with NULL reason → operator assigns reason via Downtime Entry view → operator runs shift → 15 min before scheduled end, EndOfShiftWindowTrigger surfaces the time-entry control → operator submits (Dedicated single-button) → DowntimeEvent rows for lunch + breaks inserted → Shift-end Summary shows open events; operator acknowledges → next shift’s operator closes the open downtime when the machine resumes.

## Out of Scope

Explicitly excluded from this plan — handled elsewhere or deferred:

- OEE Snapshot calculation. Oee.OeeSnapshot table exists in the data model as FUTURE scope. No Phase is dedicated to it; no stored procs, no Gateway scripts. Post-MVP workstream.

- PD Reports replacement. The four legacy Productivity Database reports (Die Shot, Rejects, Downtime, Production) are a separate Reporting workstream driven from the data captured here. Ignition Reporting module or an equivalent tool will consume the ProductionEvent, RejectEvent, DowntimeEvent, and Shift tables directly. Couples to UJ-19 + OI-30 Reports tile contents.

- Macola integration. FUTURE — not in this plan.

- Intelex integration. FUTURE — NCM / Failure Analysis remains in Intelex separately. Phase 7’s hold mechanism is the operational disposition tool in MVP; formal NCM workflows stay in Intelex.

- Pixel-level Perspective mockups and Perspective JSON project exports. Functional view descriptions only. Mockup production, if done, is a parallel workstream.

- Bit-level OPC tag addresses and PLC ladder logic. See reference/5GO_AP4_Automation_Touchpoint_Agreement.pdf and FRS Appendix C.

- Production-grade PLC firmware changes. Assumed complete by PLC integrator before Phase 6 commissioning.

- Material Allocation pre-production workflow (OI-32). Pending Phase 0 confirmation; default closure direction is “not reproduced — Flexware concept collapses into our existing LOT-at-Lineside-Cell + ConsumptionEvent model.”

- Production schedule advanced uses (OI-34). Current minimal use (shift-window timing only) is in scope; advanced uses (per-shift target quotas, drift detection, throughput planning) are Phase 0 / post-MVP.

## Open Items Affecting This Plan

| Item | Status as of 2026-04-29 | Phase affected | Resolution path |
| --- | --- | --- | --- |
| OI-31 Identifier sequence + rollout shape | ⬜ Open | Phase 1 | Phase 0 Track A workshop |
| OI-33 AIM pool empty-pool hard-fail | ⬜ Open (HIGH — customer validation) | Phase 6 + Phase 7 | Phase 0 Track A workshop |
| OI-34 Production schedule leverage | ⬜ Open (MEDIUM) | Phase 8 + post-MVP | Phase 0 Track A workshop |
| OI-35 Long-horizon scaling / retention / archiving | ⬜ Open (HIGH — gates Phase 1 SQL build) | Phase 0 → Phase 1 migration shape | Phase 0 Track B workshop |
| FDS-06-030 WorkOrder BIT flags | ⬜ Pending | Phase 1 | Phase 0 Track A workshop |
| Historical data migration | ⬜ Pending | Phase 1 | Phase 0 Track A workshop |
| A4 ShotCount semantics | ⬜ Pending | Phases 3 + 8 | Phase 0 Track A workshop |
| A5 DefaultScreen + ConfirmationMethod seeding | ⬜ Pending | Phase 1 | Phase 0 Track A workshop |
| A6 AIM Hold/Update contract detail | ⬜ Pending | Phase 7 | Phase 0 Track A workshop |
| A7 Label template scope | ⬜ Pending | Phase 6 + Phase 7 | Phase 0 Track A walkthrough; couples to S-09 |
| A8 OI-32 Material Allocation walkthrough | ⬜ Pending | Phase 6 | Phase 0 Track A walkthrough |
| UJ-03 Sublot trigger default quantities | 🔶 In Review (Ben) | Phase 5 | Split fires at Machining OUT (per MPP, 2026-06). Default direction shipped (RequiresSubLotSplit BIT on MachiningOut template + N=2 even default); Ben confirms post-MVP whether per-Item override needed |
| UJ-05 Sort Cage serial migration | ⬜ Open (default direction committed) | Phase 7 | Update-in-place + ContainerSerialHistory is built; awaits MPP Quality + Honda compliance affirmation. Reverts to void-and-recreate if rejected. |
| UJ-19 PD reports replacement | ⬜ Open | Post-MVP Reporting workstream | Phase 0 Track A enumerates reports; build is separate |
| OI-24..30 discovery items | ⬜ Open | Various phases | Handled in respective phase walkthroughs as MPP brings input |

See MPP_MES_Open_Issues_Register.docx v2.16 for full text and decision history.

## Related Documents

| Document | Version (2026-04-29) | Relevance |
| --- | --- | --- |
| MPP_MES_SUMMARY.md | current | Project index, scope matrix overview |
| MPP_MES_DATA_MODEL.docx | v1.9l | Every table + view + column referenced in this plan |
| MPP_MES_FDS.docx | v0.11m | Functional Design Specification — every FDS-XX-NNN cited |
| MPP_MES_FDS_CHANGELOG.docx | tracks v0.11m | Pre-release revision history companion to the FDS |
| MPP_MES_USER_JOURNEYS.docx | v0.9 | Arc 2 narrative — this plan is the execution map for the Arc 2 journey |
| MPP_MES_Open_Issues_Register.docx | v2.16 | Open items tracking (OI-XX, UJ-XX) |
| MPP_MES_SEEDING_REGISTRY.docx | v1.0 | External-data items S-01..S-11 and their phase coupling |
| MPP_MES_ERD.html | v1.9i (regen pending v1.9j+l) | Visual ERD — confirm FK linkages |
| MPP_MES_PHASED_PLAN_CONFIG_TOOL.docx | v1.7 | Arc 1 plan — predecessor and source of Cross-Cutting Concerns base + Stored Procedure Template |
| sql_best_practices_mes.md | current | SQL conventions |
| sql_version_control_guide.md | current | Migration + reset workflow |
| Meeting_Notes/2026-04-28_DataModel_Indexing_Scaling_Review.md | 2026-04-29 update | Drives Phase 0 Track B (OI-35) decisions |
| Meeting_Notes/2026-04-24_OI-31_Single-Line_Deployment_Impact.md | 2026-04-24 | Background memo for OI-31 rollout-shape decision |
| reference/5GO_AP4_Automation_Touchpoint_Agreement.pdf | source | PLC / MIP bit-level protocol |
| reference/MPP_FRS_Draft.pdf | Flexware v1.0 | Source FRS — Appendix C (OPC tags), Appendix L (AIM methods), Appendix B (machines), Appendix D (defect codes), Appendix E (downtime codes) |